## Table 1
CA 2020 WMP
Section | 2.2 | Recent performance on progress metrics, last 5 years
Table | 1 | Recent performance on progress metrics, last 5 years
| # | Progress metric name | Inspection Type | Annual Performance |  |  |  |  | Unit(s) | Comments
|  |  |  | 2015 | 2016 | 2017 | 2018 | 2019
| 1.a. | Grid condition findings per mile of HFTD | Patrol | 0.01 | 0.02 | 0.04 | 0.06 | 0.04 | Findings per mile of circuit in HFTD | PacifiCorp implemented its HFTD mapping as well as fire threat condition programs 2019. Therefore, grid condition findings per HFTD were available in 2019. PacifiCorp has included the number of grid condition findings for 2015-2018 assuming that the HFTD zones are equivalent to those in 2019/2020. Additionally, PacifiCorp plans, tracks, and reports inspections and corrections per facility point as opposed to per line mile. However, equivalent inspection miles were extrapolated in years 2015-2019 assuming little to no changes in grid topology. While these values reflect best estimates or equivalent line-miles, slight difference may exist when comparing to other data sets. Furthermore, the evolution of PacifiCorp’s electronic database requires extrapolation when determining condition findings per inspection type. However, PacifiCorp's programmatic inspection results were generally extrapolated and categorized as either "Detailed" or "Safety" inspection results. "Other" inspection types might include the results of internal audits or administrative changes described in Section 5.3.4.14.
|  |  | Detailed | 9 | 14 | 15 | 9 | 7
|  |  | Other | 0.03 | 0.02 | 0.06 | 0.02 | 0.01
| 1.b. | Grid condition findings per total miles | Patrol | 0.11 | 0.14 | 0.05 | 0.17 | 0.11 | Findings per total miles of circuit
|  |  | Detailed | 13 | 17 | 14 | 12 | 16
|  |  | Other | 0.05 | 0.05 | 0.04 | 0.03 | 0.02
| 2 | Vegetation clearance findings from inspection |  | - | - | - | - | - | Percent of right of way with noncompliant clearance based on application rules and regulations at the time of inspection, as percentage of all right of way inspected | While PacifiCorp's programs include clearance inspections and correction of findings, the company does not currently have an electronic database that preserves the data in a way required to answer this question. However, PacifiCorp has incorporated the need for an electronic solution into a program described in Section 5.3.5.6.
| 3 | Extent of grid modularization |  | N/A | N/A | N/A | N/A | 17.08 | Number of sectionalizing and automated grid control devices per circuit mile
|  | Extent of grid modularization in HFTD |  | N/A | N/A | N/A | N/A | 11.35
| 4 | Data collection and reporting | [5 empty] | 75% | Percent of data requested in SDR and WMP Collected in initial submission | Qualitative answer which takes into consideration not applicable sections noted throughout the WMP

## Table 2
CA 2020 WMP
Section | 2.3 | Percent performance on outcome metrics, annual and normalized for weather, last 5 years
Table | 2 | Recent performance on outcome metrics, last 5 years
| Metric Type | # | Outcome Metric Name | Annual Performance |  |  |  |  | Unit(s) | Comments
|  |  |  | 2015 | 2016 | 2017 | 2018 | 2019
| Near Misses | 1.a. | Number of all events (such as unplanned outages, faults, conventional blown fuses, etc.) that could result in ignition, by type according to utility-provided list (total) | 1257 | 796 | 1096 | 777 | 1122 | Number per year | Not limited to fire season and includes major events
|  | 1.b. | Number of all events (such as unplanned outages, faults, conventional blown fuses, etc.) that could result in ignition, by type according to utility-provided list (normalized) | 0.061487 | 0.21697 | 0.048399 | 0.063819 | 0.11472 | Number per RFW circuit mile day per year
|  | 1.c. | Number of wires down (total) | 47 | 53 | 81 | 32 | 80 | Number of wires down per year | Not limited to fire season and includes major events and potential ignition sources
|  | 1.d. | Number of wires down (normalized) | 0.002299 | 0.014447 | 0.0035769 | 0.0026283 | 0.0081795 | Number of RFP circuit mile day per year
| Near Misses (limited to fire season) | 1.a.2 | Number of all events (such as unplanned outages, faults, conventional blown fuses, etc.) that could result in ignition, by type according to utility-provided list (total) | 417 | 191 | 277 | 260 | 311 | Number per year | Limited to fire season and includes major events
|  | 1.b.2 | Number of all events (such as unplanned outages, faults, conventional blown fuses, etc.) that could result in ignition, by type according to utility-provided list (normalized) | 0.020398 | 0.052062 | 0.012232 | 0.021355 | 0.031798 | Number per RFW circuit mile day per year
|  | 1.c.2 | Number of wires down (total) | 7 | 6 | 8 | 8 | 19 | Number per year | Limited to fire season and includes major events and potential ignition sources
|  | 1.d.2 | Number of wires down (normalized) | 0.00034241 | 0.0016355 | 0.00035328 | 0.00065709 | 0.0019426 | Number per RFW circuit mile day per year
| Utility Inspection Findings | 2.a. | Number of Level 1 findings that could increase the probability of ignition discovered per circuit mile inspected | 0.03 | 0.07 | 0.05 | 0.14 | 0.1 | Average number of Level 1 findings that could increase the probability of ignition discovered by all inspections per circuit mile per year | PacifiCorp schedules, completes, and tracks inspection performance on a "per facility" basis as opposed to a "per mile" basis. However, equivalent inspection miles were extrapolated in years 2015-2019 assuming little to no changes in grid topology. Furthermore, PacifiCorp implemented its HFTD mapping as well as fire threat condition programs fully in 2019. PacifiCorp has attempted to interpret current day policies and apply to previous inspection and correction programs. However, sometimes this was not possible due to lack of specific data. Therefore, all data from 2015-2019 should be viewed as qualitative and not absolute.
|  | 2.b | Number of Level 2 findings that could increase the probability of ignition discovered per circuit mile inspected | 0.33 | 0.25 | 0.19 | 0.26 | 0.18 | Average number of Level 2 findings that could increase the probability of ignition discovered by all inspections per circuit mile per year
|  | 2.c. | Number of Level 3 findings that could increase the probability of ignition discovered per circuit mile inspected | 0 | 0 | 0 | 0 | 0 | Average number of Level 3 findings that could increase the probability of ignition discovered by all inspections per circuit mile per year | PacifiCorp interprets all fire threats to be of either immediate or medium level of risk. Therefore, all conditions that could increase the probability of ignition are included as either Level 1 or Level 2 conditions.
| Customer Hours of PSPS and other outages | 3.a. | Customer hours of planned outage including PSPS (total) | 47594.8019 | 60799.4632 | 58404.9364 | 70908.5707 | 80070.5856 | Total customer hours of planned outages per year | Only planned outages, not limited to fire season and includes major events
|  | 3.b. | Customer hours of planned outages including PSPS (normalized) | 2.3281 | 16.5725 | 2.5791 | 5.8241 | 8.1867 | Total customer hours of planned outages per RFW circuit mile day per year
|  | 3.c. | Customer hours of unplanned outages, not including PSPS (total) | 215935.6581 | 81069.2757 | 297749.2477 | 91501.8682 | 291163.7159 | Total customer hours of unplanned outages per year | Excludes planned outages, not limited to fire season and includes major events
|  | 3.d. | Customer hours of unplanned outages, not including PSPS (normalized) | 10.5626 | 22.0976 | 13.1484 | 7.5156 | 29.7696 | Total customer hours of unplanned outages per RFW circuit mile day per year
|  | 3.e. | Increase in System Average Interruption Duration Index (SAIDI) | -51.6286 | -39.2413 | -20.5055 | -13.241 | -3.3971 | Change in minutes as compared to the previous year | Excludes Major events and planned outages, not limited to fire season
|  | 3.f. | Customer hours of unplanned outages not including PSPS or Major Events (total) | 75364.1163 | 66115.3042 | 53724.3699 | 42709.4212 | 50376.3054 | Total customer hours of unplanned outages per year | Excludes planned outages, not limited to fire season and excludes major events No PSPS events have occurred.
|  | 3.g. | Customer hours of unplanned outages not including PSPS or Major Events (normalized) | 3.6865 | 18.0215 | 2.3724 | 3.508 | 5.1506 | Total customer hours of unplanned outages per RFW circuit mile day per year
| Customer Hours of PSPS and other outages (limited to fire season) | 3.a.1 | Customer hours of planned outage including PSPS (total) | 12769.0272 | 27160.8183 | 14389.7819 | 45531.6675 | 24591.1247 | Total customer hours of planned outages per year | Only planned outages, limited to fire season and includes major events
|  | 3.b.1 | Customer hours of planned outages including PSPS (normalized) | 0.6246 | 7.4034 | 0.63544 | 3.7398 | 2.5143 | Total customer hours of planned outages per RFW circuit mile day per year
|  | 3.c.1 | Customer hours of unplanned outages, not including PSPS (total) | 31141.9415 | 16386.2397 | 8298.2782 | 47840.5692 | 20950.3061 | Total customer hours of unplanned outages per year | Excludes planned outages, limited to fire season and includes major events
|  | 3.d.1 | Customer hours of unplanned outages, not including PSPS (normalized) | 1.5233 | 4.4665 | 0.36645 | 3.9294 | 2.142 | Total customer hours of unplanned outages per RFW circuit mile day per year
|  | 3.e.1 | Increase in System Average Interruption Duration Index (SAIDI) | 9.5656 | -49.7258 | -1.1265 | 0.86274 | 14.2861 | Change in minutes as compared to the previous year | Excludes Major events and planned outages, limited to fire season
|  | 3.f.1 | Customer hours of unplanned outages not including PSPS or Major Events (total) | 20991.4023 | 15922.4744 | 8279.5771 | 9208.2795 | 20827.4611 | Total customer hours of unplanned outages per year | Excludes planned outages, limited to fire season and excludes major events. No PSPS events have occurred.
|  | 3.g.1 | Customer hours of unplanned outages not including PSPS or Major Events (normalized) | 1.0268 | 4.3401 | 0.36562 | 0.75633 | 2.1295 | Total customer hours of unplanned outages per RFW circuit mile day per year
| Utility Ignited wildfire fatalities | 4.a. | Fatalities due to utility-ignited wildfire (total) | 0 | 0 | 0 | 0 | 0 | Number of fatalities per year
|  | 4.b. | Fatalities due to utility-ignited wildfire (normalized) | 0 | 0 | 0 | 0 | 0 | Number of fatalities per RFW circuit mile day per year
| Accidental deaths resulting from utility wildfire mitigation activities | 5.a. | Deaths due to utility wildfire mitigation activities (total) | 0 | 0 | 0 | 0 | 0 | Number of fatalities per year
| OSHA reportable injuries from utility wildfire mitigation initiatives | 6.a. | OSHA-reportable injuries due to utility wildfire mitigation activities (total) | N/A | N/A | N/A | N/A | 0 | Number of OSHA-reportable injuries per year | PacifiCorp tracks all safety statistics including but not limited to accidental deaths, OSHA-reportable, or near misses. However, as PacifiCorp is early it its WMP implementation, it is challenging to report historic safety statistics regarding wildfire mitigation programs as requested, specifically any values prior to 2019 as these programs did not exist. Therefore, PacifiCorp was not able to populate all cells within the applicable tables.
|  | 6.b. | OSHA-reportable injuries due to utility wildfire mitigation activities (normalized) | N/A | N/A | N/A | N/A | 0 | Number of OSHA-reportable injuries per year per 1000 line miles of grid | PacifiCorp tracks all safety statistics including but not limited to accidental deaths, OSHA-reportable, or near misses. However, as PacifiCorp is early it its WMP implementation, it is challenging to report historic safety statistics regarding wildfire mitigation programs as requested, specifically any values prior to 2019 as these programs did not exist. Therefore, PacifiCorp was not able to populate all cells within the applicable tables.
| Value of assets destroyed by utility-ignited wildfire, listed by asset type | 7.a. | Value of assets destroyed by utility-ignited wildfire (total) | 98492.46 | 0 | 0 | 0 | 225692 | Dollars of damage or destruction per year
|  | 7.b. | Value of assets destroyed by utility-ignited wildfire (normalized) | 4.8178 | 0 | 0 | 0 | 23.0755 | Dollars of damage or destruction per RFW circuit mile day per year
| Structures damages of destroyed by utility ignited wildfire | 8.a. | Value of structures destroyed by utility-ignited wildfire (total) | 85728.21 | 0 | 0 | 0 | 15000 | Number of structures destroyed per year
|  | 8.b. | Value of structures destroyed by utility-ignited wildfire (normalized) | 4.1934 | 0 | 0 | 0 | 1.5337 | Number of structures destroyed per RFW circuit mile day per year
| Acreage burned by utility-ignited wildfire | 9.a. | Acreage burned by utility ignited wildfire (total) | 16 | 5 | 3 | 1 | 126 | Acres burned per year | Acreage burned is an approximate value, and is not limited to wildfire. In some cases the field references the burn area as a small fire (typically a small grass fire), these fires are often under a half acre in size. For calculation purposes, fires with this designation were calculated as a half-acre. In addition CAL FIRE fire perimeters were also evaluated for utility ignitions from 2015-2018 (2019 has yet to be released), and no utility caused outages occurred in PacifiCorp’s Service territory
|  | 9.b. | Acreage burned by utility-ignited wildfire (normalized) | 0.00078265 | 0.0013629 | 0.00013248 | 8.2136e-05 | 0.012883 | Acres burned per RFW circuit year
| Number of utility wildfire ignitions | 10.a. | Number of ignitions (total) according to existing ignition data reporting requirement | 2 | 6 | 4 | 4 | 14 | Number per year | Fire locations are mapped to the best known location. Actual locations may vary given the data provided by the field. In some cases an address was unknown and therefore the fire was mapped to the closest known outage location.
|  | 10.b. | Number of ignitions (normalized) | 9.7831e-05 | 0.0016355 | 0.00017664 | 0.00032854 | 0.0014314 | Number per RFW circuit mile per year
|  | 10.c. | Number of ignitions in HFTD (subtotal) | 2 | 2 | 1 | 3 | 5 | Number in HFTD per year
|  | 10.c.i | Number of ignitions in HFTD Zone 1 | 0 | 0 | 0 | 0 | 0 | Number in HFTD Zone 1 per year
|  | 10.c.ii | Number of ignitions in HFTD Tier 2 | 2 | 2 | 1 | 3 | 5 | Number in HFTD Tier 2 per year
|  | 10.c.iii | Number of ignitions in HFTD Tier 3 | 0 | 0 | 0 | 0 | 0 | Number in HFTD Tier 3 per year
|  | 10.d. | Number of ignitions in HFTD (subtotal, normalized) | 9.7831e-05 | 0.00054515 | 4.4159e-05 | 0.00024641 | 0.00051122 | Number in HFTD per RFW circuit mile day per year
|  | 10.d.i. | Number of ignitions in HFTD Zone 1 (normalized) | 0 | 0 | 0 | 0 | 0 | Number in HFTD Zone 1 per RFW circuit mile day per year
|  | 10.d.ii. | Number of ignitions in HFTD Tier 2 (normalized) | 9.7831e-05 | 0.00054515 | 4.4159e-05 | 0.00024641 | 0.00051122 | Number in HFTD Tier 2 per RFW circuit mile day per year
|  | 10.d.iii. | Number of ignitions in HFTD Tier 3 (normalized) | 0 | 0 | 0 | 0 | 0 | Number in HFTD Tier 3 per RFW circuit mile day per year
|  | 10.e. | Number of ignitions in non-HFTD (subtotal) | 0 | 4 | 3 | 1 | 9 | Number in non-HFTD per year
|  | 10.f. | Number of ignitions in non-HFTD (normalized) | 0 | 0.0010903 | 0.00013248 | 8.2136e-05 | 0.00092019 | Number in non-HFTD per RFW circuit mile day per year
| Critical infrastructure impacted | 11.a. | Critical infrastructure impacted by PSPS | 0 | 0 | 0 | 0 | 0 | Number in non-HFTD per RFW circuit mile day per year Number of critical infrastructure (in accordance with D.19-05-042) locations impacted per hour multiplied by hours offline per year
|  | 11.b. | Critical infrastructure impacted by PSPS (normalized) | 0 | 0 | 0 | 0 | 0 | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted per hour multiplied by hours offline per RFW circuit mile day per year

## Table 3
CA 2020 WMP
Section | 2.4 | Description of additional metrics
Table | 3 | List and description of additional metrics, last 5 years
| Metric | Performance |  |  |  |  | Unit(s) | Underlying Assumptions | Third-party Validation
|  | 2015 | 2016 | 2017 | 2018 | 2019
| PC3a.Events Recorded with Fire Reference: Not Fire Season | 14 | 10 | 1 | 7 | 20 | Outage event(s) | Data source is outage reporting system in which outage makes reference to fire in comment or outage cause | As noted in previous filings, PacifiCorp will make data available upon request to pertinent entities or individuals, such as universities or researchers. PacifiCorp also includes progress reports regarding any WMP programs or initiatives on the company’s public website. PacifiCorp also viewed participation in regulatory proceedings, discovery requests, and workshops as opportunity to present data, engage third parties, solicit feedback, and, where appropriate, seek validation or make necessary changes to any program or initiative. This general approach has been applied to all metrics or data sets, including those in this table.
| PC3b.Events Recorded with Fire Reference: Fire Season | 13 | 12 | 5 | 23 | 19 | Outage event(s)
| PC4a. Events Recorded with Fire Reference: damage fire, equipment fire, pole fire: Not Fire Season | 6 | 6 | 0 | 1 | 7 | Outage event(s) | Subset of PC3 where record makes reference to utility equipment or key components
| PC4b. Events Recorded with Fire Reference: damage fire, equipment fire, pole fire: Fire Season | 5 | 3 | 4 | 5 | 5 | Outage event(s)
| PC5. Wire down risks | 9 | 7 | 8 | 8 | 20 | Outage event(s) | Data source is outage reporting system in which cause code or comments would result in downed conductor during fire season
| PC6. Wire down trend | NA | -2 | 1 | 0 | 12 | Outage event(s) | Reduction in quantity of wire down events, year over year, during the designated fire season period

## Table 4
CA 2020 WMP
Section | 2.5 | Description of program targets
Table | 4 | List and description of program targets, last 5 years 2019 per WMP Clariifcation Document issued 1/15/2020
| Program Details |  |  | Program Target |  | Progress |  | Underlying Assumptions
| Program | Initiative | Duration | Total Planned Unit(s) | Anticipated Completion | 2019 Performance / Update | Cumulative Percent Complete of Total Plan (%)
| Situational Awareness | Weather Station Installation | Multi-year (4 yr) | 35 stations | 2022 | 10 stations | 29% | See Section 5.3.2.1
| Asset management and inspections | Enhanced transmission inspections using IR/alternate technologies | Single pilot project (2-yr) | 1 Pilot Project | 2020 | Implemented pilot project; 100% of data collection complete | 75% | See Section 5.3.4.5
|  | Complete planned inspections, including additional HFTD inspections | Annual program/target | 3,311 equivalent line miles | Annual / on-going | 3,310 equivalent line-miles | 99.9% in 2019 | See Section 5.3.4.3
|  | Implement LiDAR inspection pilot project for distribution and transmission lines | Single pilot project (2-yr) | 1 Pilot Project | 2020 | Completed flights and collection of data | 75% | See Section 5.3.4.7
| System Hardening: | Installation of Covered Conductor | Multi-year (5 yr) | 221 line-miles | 2023 | Engineering and scoping completed for 38 line-miles planned in 2020 | 10% | See Section 5.3.3.3
|  | Replacement of Cu Conductor | Multi-year (5 yr) | 53 line miles | 2023 | Engineering specification and scope completed for 3 line miles planned in 2020; | 3% | See Section 5.3.3.18
|  | Installation of System Automation Equipment | Multi-year (4 yr) | 68 projects | 2022 | 10 projects complete | 15% | See Section 5.3.3.9
|  | Proactive Wood Pole Replacement | Multi-year (5 yr) | 4000 | 2023 | Engineering standard and specification completed; | 10% | See Section 5.3.3.6
| Vegetation Management and Inspections: | Perform annual inspections on all lines in the HFTD | Annual program/target | 1,170 line miles | Annual / on-going | 1,170 line miles | 100% in 2019 | See Section 5.3.5.2 & Section 5.3.5.3
|  | Implement radial pole clearing program | Annual program/target | 15,060 poles | Annual / on-going | 14,132 poles expanded program in 2019, full program in 2020 | 94% in 2019 | See Section 5.3.5.9

## Table 5
CA 2020 WMP
Section | 2.6 | Detailed information supporting outcome metrics
Table | 5 | Accidental deaths due to utility wildfire mitigation initiatives, last 5 years
| Activity | Victim | [14 empty] | Total
|  | Full-Time Employee |  |  |  |  | Contractor |  |  |  |  | Member of Public
| Year | 2015 | 2016 | 2017 | 2018 | 2019 | 2015 | 2016 | 2017 | 2018 | 2019 | 2015 | 2016 | 2017 | 2018 | 2019
| Inspection | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0
| Vegetation Management | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0
| Utility Fuel Management | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0
| Grid Hardening | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0
| Other | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0
| Total | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0

## Table 6
CA 2020 WMP
Section | 2.6 | Detailed information supporting outcome metrics
Table | 6 | OSHA-reportable injuries due to utility wildfire mitigation initiatives, last 5 years
| Activity | Victim | [14 empty] | Total
|  | Full-Time Employee |  |  |  |  | Contractor |  |  |  |  | Member of Public
| Year | 2015 | 2016 | 2017 | 2018 | 2019 | 2015 | 2016 | 2017 | 2018 | 2019 | 2015 | 2016 | 2017 | 2018 | 2019
| Inspection | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0
| Vegetation Management | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0
| Utility Fuel Management | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0
| Grid Hardening | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0
| Other | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0
| Total | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 0 | 0

## Table 7
CA 2020 WMP
Section | 2.6 | Detailed information supporting outcome metrics
Table | 7 | Methodology for potential impact of ignitions
| List of all data inputs used in impact simulation | Sources of data inputs | Data selection and treatment methodologies | Assumptions, including SME input | Equation(s), functions, or other algorithms used to obtain output | Output type(s), e.g. wind speed model | Comments
| Historic fire weather | CalFIRE shape files, USFS map products, cause data | 2007 thru 2019 | Historic perimeters serve as potential future fire risk areas | N/A | Map of elevated areas
| Terrain | GIS data | All geography served by company | Terrain constant over time | N/A | N/A
| Fuel conditions | Landfire data | All geography served by company | Fuel not substantially different over long time continuum | N/A | N/A
| Historic egress/access issues | Map products (Tiger, Google) | All geography served by company | Local operational input; map review of egress and fire history | N/A | Elevation of CalFire led map product

## Table 8
CA 2020 WMP
Section | 2.7 | Mapping recent, modelled, and baseline conditions
Table | 8 | Map file requirements for recent and modelled conditions of utility service territory, last 5 years
| Layer name | Measurements | Units | Attachment location | GIS File-geodatabase file name | GIS Layer Name
| Recent weather patterns | Average annual number of Red Flag Warning days per square mile across service territory | Area, days, square mile resolution | 6.1 | Data_Table8.gdb | WWA_PAC_FW_2015-2019_Durations_Grid
|  | Average 95th and 99th percentile wind speed and prevailing direction (actual) | Area, miles per hour, at a square mile resolution or better, noting where measurements are actual or interpolated |  | Data_Table8.gdb | Ave95_99th_PercentileWind_Grid
| Recent drivers of ignition probability | Date of recent ignitions categorized by ignition probability driver | Point, GPS coordinate, days, square mile resolution | 6.2 | Data_Table8.gdb | Ignition_Probability_Grid
| Recent use of PSPS | Duration of PSPS events and area of the grid affected in customer hours per year | Area, customer hours, square mile resolution | 6.3 | N/A [No PSPS data to report] | N/A [No PSPS data to report]

## Table 9
CA 2020 WMP
Section | 2.7 | Mapping recent, modelled, and baseline conditions
Table | 9 | Map file requirements for baseline condition of utility service territory projected for 2020
| Layer name | Measurements | Units | Attachment location | file-geodatabase name | GIS Layer Name
| Current baseline state of service territory and utility equipment | Non-HFTD vs HFTD (Zone 1, Tier 2, Tier 3) regions of utility service territory | Area, square mile resolution per type | 6.4 | Data_Table9MapLayer1.gdb | HFTD_Grid
|  | Urban vs. rural vs. highly rural regions of utility service territory | Area, square mile resolution per type |  |  | LANDUSE_Grid
|  | WUI regions of utility service territory | Area, square mile resolution |  |  | WUI_Grid
|  | Number and location of critical facilities | Point, GPS coordinate |  |  | Critical_Facilities
|  | Number and location of customers | Area, number of people, square mile resolution |  |  | Customer_Grid
|  | Number and location of customers belonging to access and functional needs populations functional needs populations | Area, number of people, square mile resolution |  |  | CustomerAFN_Grid
|  | Overhead transmission lines | Line, quarter mile resolution |  |  | Distirbution_Line_OH
|  | Overhead distribution lines | Line, quarter mile resolution |  |  | Transmission_Line
|  | Location of substations | Point, GPS coordinate |  |  | Distribution_Sub & Transmission_Sub
|  | Location of weather stations | Point, GPS coordinate |  |  | Weather_Stations
|  | All utility assets by asset type, model, age, specifications, and condition | Point, GPS coordinate |  |  | All_poles
| Location of planned utility equipment additions or removal | Non-HFTD vs HFTD (Zone 1, Tier 2, Tier 3) regions of utility service territpry | Line, quarter mile resolution | 6.5 | Data_Table9MapLayer2.gdb | Lines_HFTD
|  | Urban vs. rural vs. highly rural regions of utility service territory | Line, quarter mile resolution |  |  | Lines_LandUse
|  | WUI regions of utility service territory | Line, quarter mile resolution |  |  | Lines_LandUse00
|  | Circuit miles of overhead transmission lines | Line, quarter mile resolution |  |  | Transmission_Line
|  | Circuit miles of overhead distribution lines | Line, quarter mile resolution |  |  | Distirbution_Line
|  | Location of substations | Point, GPS coordinate |  |  | Substaton
| Planned 2020 WMP initiative activity per year | Location of 2020 WMP initiative activity for each activity as planned to be completed by the end of each year of the plan term | Line, quarter mile resolution | 6.6* | Data_Table9MapLayer3.gdb | Distirbution_Line/Substations
*Interpreted as 6.6 as there was no 7.6 - typo

## Table 10
CA 2020 WMP
Section | 3.1 | Recent weather patterns, last 5 years
Table | 10 | Weather patterns, last 5 years
| Weather Measurement | 2015 | 2016 | 2017 | 2018 | 2019 | 5 yr historical Average | Unit(s)
| Red Flag Warning days | 20443.4827 | 3668.6965 | 22645.2411 | 12174.9679 | 9780.5874 | 13742.5951 | RFW circuit mile days per year
| Days rated at the top 30% of proprietary fire potential index or similar fire risk index measure | NA | NA | NA | NA | 1391 | 1391 | Circuit mile days where proprietary measure rated above top 30% threshold1 per year
| 95th percentile wind conditions | 11811 | 20069 | 15625 | 13541 | 13215 | 14852 | Circuit mile days with wind gusts over 95th percentile historical (meaning the prior 10 years, 2005-2014) conditions per year
| 99th percentile wind conditions | 1106 | 3031 | 1420 | 197 | 1003 | 1351 | Circuit mile days with wind gusts over 99th percentile historical (meaning the prior 10 years, 2005-2014) conditions per year
| Other | NA | NA | NA | NA | NA | NA

## Table 11a-d
CA 2020 WMP
Section | 3.2 | Recent drivers of ignition probability
Table | 11a | Key recent drivers of ignition probability transmission lines, last 5 years
All Seasons
Transmission
| Incident Type by ignition probability driver |  | Near misses tracked [y/n] | Number of incidents per year | [5 empty] | Average percentage probability of ignition per incident | [5 empty] | Number of ignitions per year from this driver
|  |  |  | 2015 | 2016 | 2017 | 2018 | 2019 | Average | 2015 | 2016 | 2017 | 2018 | 2019 | Average | 2015 | 2016 | 2017 | 2018 | 2019 | Average
| Contact from object | Animal contact | n | 3 | 0 | 0 | 2 | 1 | 1.2 | 0% | 0% | 0% | 0% | 100% | 16.67% | 0 | 0 | 0 | 0 | 1 | 0.2
|  | Balloon contact | n | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Other | n | 18 | 3 | 11 | 2 | 2 | 7.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Unknown | n | 0 | 1 | 0 | 1 | 0 | 0.4 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Veg. contact | n | 5 | 1 | 5 | 1 | 7 | 3.8 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Vehicle contact | n | 1 | 0 | 0 | 1 | 0 | 0.4 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| Contamination |  | n | 1 | 2 | 1 | 3 | 2 | 1.8 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| All typed of Equipment/ Facility failure | Conductor | n | 3 | 6 | 1 | 0 | 1 | 2.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Crossarm | n | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Fuse | n | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Insulator | n | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Lightning arrestor | n | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Other | n | 2 | 0 | 1 | 4 | 0 | 1.4 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Pole | n | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Sectionalizer | n | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Splice/clamp/connector | n | 0 | 0 | 0 | 0 | 1 | 0.2 | 0% | 0% | 0% | 0% | 100% | 100% | 0 | 0 | 0 | 0 | 1 | 0.2
|  | Switch | n | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformer | n | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Voltage regulator | n | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| Normal Operation |  | n | 3 | 2 | 1 | 1 | 0 | 1.4 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| Other |  | n | 17 | 7 | 24 | 10 | 8 | 13.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| Unknown |  | n | 32 | 12 | 19 | 17 | 30 | 22 | 0% | 0% | 0% | 0% | 3.333% | 0.9091% | 0 | 0 | 0 | 0 | 1 | 0.2
| Vandalism/Theft |  | n | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| Wire-to-wire contact |  | n | 2 | 0 | 0 | 0 | 0 | 0.4 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| Contact from 3rd party |  | n | 1 | 0 | 0 | 0 | 1 | 0.4 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
Section | 3.2 | Recent drivers of ignition probability
Table | 11b | Key recent drivers of ignition probability distribution lines, last 5 years
All Seasons
Distribuiton
| Incident Type by ignition probability driver |  | Near misses tracked [y/n] | Number of incidents per year | [5 empty] | Average percentage probability of ignition per incident | [5 empty] | Number of ignitions per year from this driver
|  |  |  | 2015 | 2016 | 2017 | 2018 | 2019 | Average | 2015 | 2016 | 2017 | 2018 | 2019 | Average | 2015 | 2016 | 2017 | 2018 | 2019 | Average
| Contact from object | Animal contact | n | 55 | 32 | 34 | 42 | 53 | 43.2 | 1.818% | 0% | 0% | 2.381% | 1.887% | 1.389% | 1 | 0 | 0 | 1 | 1 | 0.6
|  | Balloon contact | n | 2 | 0 | 0 | 1 | 0 | 0.6 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Other | n | 88 | 23 | 32 | 34 | 37 | 42.8 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Unknown | n | 0 | 4 | 5 | 4 | 1 | 2.8 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Veg. contact | n | 127 | 118 | 159 | 79 | 174 | 131.4 | 0% | 0.8475% | 0.6289% | 2.532% | 1.149% | 0.9132% | 0 | 1 | 1 | 2 | 2 | 1.2
|  | Vehicle contact | n | 15 | 9 | 11 | 18 | 9 | 12.4 | 0% | 0% | 0% | 5.556% | 0% | 1.613% | 0 | 0 | 0 | 1 | 0 | 0.2
| Contamination |  | n | 4 | 2 | 5 | 6 | 2 | 3.8 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| All typed of Equipment/ Facility failure | Conductor | n | 43 | 29 | 39 | 25 | 27 | 32.6 | 2.326% | 0% | 2.564% | 0% | 3.704% | 1.84% | 1 | 0 | 1 | 0 | 1 | 0.6
|  | Crossarm | n | 5 | 4 | 3 | 2 | 7 | 4.2 | 0% | 0% | 0% | 0% | 14.29% | 4.762% | 0 | 0 | 0 | 0 | 1 | 0.2
|  | Fuse | n | 122 | 130 | 156 | 127 | 118 | 130.6 | 0% | 0% | 0.641% | 0% | 0.8475% | 0.3063% | 0 | 0 | 1 | 0 | 1 | 0.4
|  | Insulator | n | 3 | 5 | 2 | 5 | 6 | 4.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Lightning arrestor | n | 10 | 12 | 13 | 14 | 8 | 11.4 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Other | n | 13 | 10 | 19 | 35 | 32 | 21.8 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Pole | n | 4 | 5 | 8 | 3 | 9 | 5.8 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Sectionalizer | n | 0 | 1 | 0 | 0 | 0 | 0.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Splice/clamp/connector | n | 137 | 60 | 100 | 41 | 71 | 81.8 | 0% | 1.667% | 0% | 0% | 0% | 0.2445% | 0 | 1 | 0 | 0 | 0 | 0.2
|  | Switch | n | 0 | 1 | 1 | 0 | 0 | 0.4 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformer | n | 61 | 34 | 54 | 29 | 48 | 45.2 | 0% | 0% | 1.852% | 0% | 0% | 0.4425% | 0 | 0 | 1 | 0 | 0 | 0.2
|  | Voltage regulator | n | 0 | 0 | 0 | 1 | 0 | 0.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| Normal Operation |  | n | 31 | 13 | 19 | 18 | 27 | 21.6 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| Other |  | n | 175 | 43 | 194 | 73 | 224 | 141.8 | 0% | 0% | 0% | 0% | 0.4464% | 0.141% | 0 | 0 | 0 | 0 | 1 | 0.2
| Unknown |  | n | 132 | 116 | 88 | 85 | 108 | 105.8 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| Vandalism/Theft |  | n | 1 | 0 | 1 | 2 | 0 | 0.8 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| Wire-to-wire contact |  | n | 10 | 12 | 6 | 7 | 9 | 8.8 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| Contact from 3rd party |  | n | 4 | 3 | 4 | 1 | 8 | 4 | 0% | 0% | 0% | 0% | 12.5% | 5% | 0 | 0 | 0 | 0 | 1 | 0.2
Section | 3.2 | Recent drivers of ignition probability
Table | 11c | Key recent drivers of ignition probability during fire season, transmission lines, last 5 years
Fire Season ONLY
Transmission
| Incident Type by ignition probability driver |  | Near misses tracked [y/n] | Number of incidents per year | [5 empty] | Average percentage probability of ignition per incident | [5 empty] | Number of ignitions per year from this driver
|  |  |  | 2015 | 2016 | 2017 | 2018 | 2019 | Average | 2015 | 2016 | 2017 | 2018 | 2019 | Average | 2015 | 2016 | 2017 | 2018 | 2019 | Average
| Contact from object | Animal contact | n | 2 | 0 | 0 | 2 | 1 | 1 | 0% | 0% | 0% | 0% | 100% | 20% | 0 | 0 | 0 | 0 | 1 | 0.2
|  | Balloon contact | n | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Other | n | 16 | 2 | 11 | 0 | 2 | 6.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Unknown | n | 0 | 0 | 0 | 1 | 0 | 0.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Veg. contact | n | 2 | 0 | 2 | 0 | 0 | 0.8 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Vehicle contact | n | 1 | 0 | 0 | 0 | 0 | 0.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| Contamination |  | n | 1 | 2 | 1 | 3 | 2 | 1.8 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| All typed of Equipment/ Facility failure | Conductor | n | 1 | 0 | 0 | 0 | 0 | 0.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Crossarm | n | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Fuse | n | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Insulator | n | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Lightning arrestor | n | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Other | n | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Pole | n | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Sectionalizer | n | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Splice/clamp/connector | n | 0 | 0 | 0 | 0 | 1 | 0.2 | 0% | 0% | 0% | 0% | 100% | 100% | 0 | 0 | 0 | 0 | 1 | 0.2
|  | Switch | n | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformer | n | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Voltage regulator | n | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| Normal Operation |  | n | 2 | 0 | 1 | 0 | 0 | 0.6 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| Other |  | n | 2 | 1 | 5 | 3 | 0 | 2.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| Unknown |  | n | 8 | 0 | 4 | 6 | 10 | 5.6 | 0% | 0% | 0% | 0% | 10% | 3.571% | 0 | 0 | 0 | 0 | 1 | 0.2
| Vandalism/Theft |  | n | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| Wire-to-wire contact |  | n | 1 | 0 | 0 | 0 | 0 | 0.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| Contact from 3rd party |  | n | 1 | 0 | 0 | 0 | 0 | 0.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
Section | 3.2 | Recent drivers of ignition probability
Table | 11d | Key recent drivers of ignition probability during fire season, distribution lines, last 5 years
Fire Season ONLY
Distribuiton
| Incident Type by ignition probability driver |  | Near misses tracked [y/n] | Number of incidents per year | [5 empty] | Average percentage probability of ignition per incident | [5 empty] | Number of ignitions per year from this driver
|  |  |  | 2015 | 2016 | 2017 | 2018 | 2019 | Average | 2015 | 2016 | 2017 | 2018 | 2019 | Average | 2015 | 2016 | 2017 | 2018 | 2019 | Average
| Contact from object | Animal contact | n | 32 | 17 | 18 | 18 | 26 | 22.2 | 3.125% | 0% | 0% | 5.556% | 0% | 1.802% | 1 | 0 | 0 | 1 | 0 | 0.4
|  | Balloon contact | n | 1 | 0 | 0 | 1 | 0 | 0.4 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Other | n | 70 | 5 | 27 | 20 | 30 | 30.4 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Unknown | n | 0 | 0 | 2 | 2 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Veg. contact | n | 23 | 14 | 16 | 20 | 33 | 21.2 | 0% | 0% | 6.25% | 5% | 3.03% | 2.83% | 0 | 0 | 1 | 1 | 1 | 0.6
|  | Vehicle contact | n | 5 | 4 | 4 | 10 | 2 | 5 | 0% | 0% | 0% | 10% | 0% | 4% | 0 | 0 | 0 | 1 | 0 | 0.2
| Contamination |  | n | 3 | 1 | 1 | 5 | 1 | 2.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| All typed of Equipment/ Facility failure | Conductor | n | 9 | 7 | 8 | 3 | 7 | 6.8 | 0% | 0% | 12.5% | 0% | 14.29% | 5.882% | 0 | 0 | 1 | 0 | 1 | 0.4
|  | Crossarm | n | 1 | 2 | 0 | 0 | 1 | 0.8 | 0% | 0% | 0% | 0% | 100% | 25% | 0 | 0 | 0 | 0 | 1 | 0.2
|  | Fuse | n | 34 | 26 | 52 | 30 | 41 | 36.6 | 0% | 0% | 1.923% | 0% | 2.439% | 1.093% | 0 | 0 | 1 | 0 | 1 | 0.4
|  | Insulator | n | 0 | 1 | 1 | 2 | 2 | 1.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Lightning arrestor | n | 5 | 1 | 3 | 4 | 5 | 3.6 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Other | n | 5 | 3 | 4 | 11 | 6 | 5.8 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Pole | n | 0 | 2 | 4 | 3 | 2 | 2.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Sectionalizer | n | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Splice/clamp/connector | n | 33 | 11 | 16 | 10 | 16 | 17.2 | 0% | 9.091% | 0% | 0% | 0% | 1.163% | 0 | 1 | 0 | 0 | 0 | 0.2
|  | Switch | n | 0 | 0 | 1 | 0 | 0 | 0.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformer | n | 31 | 10 | 26 | 17 | 18 | 20.4 | 0% | 0% | 3.846% | 0% | 0% | 0.9804% | 0 | 0 | 1 | 0 | 0 | 0.2
|  | Voltage regulator | n | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| Normal Operation |  | n | 22 | 1 | 1 | 6 | 7 | 7.4 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| Other |  | n | 6 | 4 | 3 | 15 | 13 | 8.2 | 0% | 0% | 0% | 0% | 7.692% | 2.439% | 0 | 0 | 0 | 0 | 1 | 0.2
| Unknown |  | n | 39 | 28 | 23 | 27 | 33 | 30 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| Vandalism/Theft |  | n | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| Wire-to-wire contact |  | n | 0 | 0 | 1 | 0 | 3 | 0.8 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| Contact from 3rd party |  | n | 1 | 1 | 2 | 0 | 2 | 1.2 | 0% | 0% | 0% | 0% | 50% | 16.67% | 0 | 0 | 0 | 0 | 1 | 0.2

## Table 12
CA 2020 WMP
Section | 3.3 | Recent use of PSPS, last 5 years
Table | 12 | Recent use of PSPS, last 5 years
| PSPS characteristic | 2015 | 2016 | 2017 | 2018 | 2019 | Unit(s)
| Frequency of PSPS events (total) | N/A | N/A | N/A | N/A | 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability, per year
| Frequency of PSPS events (normalized) | N/A | N/A | N/A | N/A | 0 | Number of instances where utility operating protocol requires de-energization of a circuit or portion thereof in order to reduce ignition probability, per RFW circuit mile day per year
| Scope of PSPS events (total) | N/A | N/A | N/A | N/A | 0 | Circuit-events, measured in number of events multiplied by number of circuits de-energized per year
| Scope of PSPS events (normalized) | N/A | N/A | N/A | N/A | 0 | Circuit-events, measured in number of events multiplied by number of circuits targeted for de- energization per RFW circuit mile day per year
| Duration of PSPS events (total) | N/A | N/A | N/A | N/A | 0 | Customer hours per year
| Duration of PSPS events (normalized) | N/A | N/A | N/A | N/A | 0 | Customer hours per RFW circuit mile day per year
| Other | N/A | N/A | N/A | N/A | N/A

## Table 13
CA 2020 WMP
Section | 3.4.1 | Current baseline state of service territory and utility equipment
Table | 13 | Current baseline state of service territory and utility equipment
| Land use | Characteristic tracked | In non-HFTD | In HFTD Zone 1 | In HFTD Tier 2 | In HFTD Tier 3
| In urban areas | Circuit miles | 55.2 | 0 | 6.7 | 0
|  | Circuit miles in WUI | 0.03 | 0 | 3.2 | 0
|  | Number of critical facilities | 75 | 0 | 5 | 0
|  | Number of critical facilities in WUI | 0 | 0 | 1 | 0
|  | Number of customers | 4656 | 0 | 151 | 0
|  | Number of customers in WUI | 0 | 0 | 24 | 0
|  | Number of customers belonging to access and functional needs populations | 6 | 0 | 0 | 0
|  | Number of customers belonging to access and functional needs populations in WUI | 0 | 0 | 0 | 0
|  | Circuit miles of overhead transmission lines | 2.2 | 0 | 0.7 | 0
|  | Circuit miles of overhead transmission lines in WUI | 0 | 0 | 0.2 | 0
|  | Circuit miles of overhead distribution lines | 32.9 | 0 | 4.6 | 0
|  | Circuit miles of overhead distribution lines in WUI | 0.03 | 0 | 2.3 | 0
|  | Number of substations (distribution/transmission) | 1/0 | 0/0 | 0/0 | 0/0
|  | Number of substations in WUI (distribution/transmission) | 0/0 | 0/0 | 0/0 | 0/0
| In rural areas | Circuit miles | 1022.6 | 0.7 | 814.6 | 115.9
|  | Circuit miles in WUI | 667.1 | 0.5 | 633.2 | 96
|  | Number of critical facilities | 272 | 0 | 262 | 33
|  | Number of critical facilities in WUI | 100 | 0 | 156 | 26
|  | Number of customers | 14505 | 1 | 13383 | 1080
|  | Number of customers in WUI | 6005 | 1 | 6610 | 870
|  | Number of customers belonging to access and functional needs populations | 17 | 0 | 8 | 0
|  | Number of customers belonging to access and functional needs populations in WUI | 11 | 0 | 6 | 0
|  | Circuit miles of overhead transmission lines | 164.5 | 0.2 | 150.9 | 23.3
|  | Circuit miles of overhead transmission lines in WUI | 127.6 | 0.2 | 116.1 | 15.9
|  | Circuit miles of overhead distribution lines | 728.4 | 0.5 | 419.8 | 38.5
|  | Circuit miles of overhead distribution lines in WUI | 458.5 | 0.3 | 323 | 29.3
|  | Number of substations (distribution/transmission) | 14/8 | 0/0 | 9/9 | 1/1
|  | Number of substations in WUI (distribution/transmission) | 5/4 | 0/0 | 7/9 | 1/0
| In highly rural areas | Circuit miles | 1231.6 | 6.1 | 614.2 | 0
|  | Circuit miles in WUI | 498.4 | 5.3 | 429.4 | 0
|  | Number of critical facilities | 198 | 0 | 139 | 0
|  | Number of critical facilities in WUI | 64 | 0 | 111 | 0
|  | Number of customers | 7663 | 14 | 4577 | 0
|  | Number of customers in WUI | 2841 | 13 | 3965 | 0
|  | Number of customers belonging to access and functional needs populations | 7 | 0 | 2 | 0
|  | Number of customers belonging to access and functional needs populations in WUI | 1 | 0 | 2 | 0
|  | Circuit miles of overhead transmission lines | 217.3 | 1 | 169.3 | 0
|  | Circuit miles of overhead transmission lines in WUI | 90.1 | 0.6 | 77.5 | 0
|  | Circuit miles of overhead distribution lines | 937.9 | 4.8 | 356.7 | 0
|  | Circuit miles of overhead distribution lines in WUI | 378 | 4.4 | 275.6 | 0
|  | Number of substations (distribution/transmission) | 15/21 | 0/0 | 12/2 | 0/0
|  | Number of substations in WUI (distribution/transmission) | 4/2 | 0/0 | 8/1 | 0/0

## Table 14
CA 2020 WMP
Section | 3.4.1 | Current baseline state of service territory and utility equipment
Table | 14 | Summary data on weather station count
| Weather station count type | Current count | Unit(s)
| Number of weather stations (total) | 10 | Total number located in service territory and operated by utility
| Number of weather stations (normalized) | 0.003075 | Total number located in service territory and operated by utility, divided by total number of circuit miles in utility service territory
| Number of weather stations in non- HFTD (total) | 0 | Total number located in non-HFTD service territory and operated by utility
| Number of weather stations in non-HFTD (normalized) | 0 | Total number located in non-HFTD service territory and operated by utility, divided by total number of circuit miles in non-HFTD service territory
| Number of weather stations in HFTD Zone 1 (total) | 0 | Total number located in HFTD Zone 1 service territory and operated by utility
| Number of weather stations in HFTD Zone 1 (normalized) | 0 | Total number located in HFTD Zone 1 service territory and operated by utility, divided by total number of circuit miles in HFTD Zone 1 service territory
| Number of weather stations in HFTD Tier 2 (total) | 8 | Total number located in HFTD Tier 2 service territory and operated by utility
| Number of weather stations in HFTD Tier 2 (normalized) | 0.0072595 | Total number located in HFTD Tier 2 service territory and operated by utility, divided by total number of circuit miles in HFTD Tier 2 service territory
| Number of weather stations in HFTD Tier 3 (total) | 2 | Total number located in HFTD Tier 3 service territory and operated by utility
| Number of weather stations in HFTD Tier 3 (normalized) | 0.032787 | Total number located in HFTD Tier 3 service territory and operated by utility, divided by total number of circuit miles in HFTD Tier 3 service territory

## Table 15
CA 2020 WMP
Section | 3.4.1 | Current baseline state of service territory and utility equipment
Table | 15 | Summary data on weather station count
|  | Fault indicator count type | Current count | Unit(s)
|  | Number of fault indicators (total) | 45709 | Total number located in service territory and operated by utility
|  | Number of fault indicators (normalized) | 13.69 | Total number located in service territory and operated by utility, divided by total number of circuit miles in utility service territory
|  | Number of fault indicators in non-HFTD (total) | 22466 | Total number located in non-HFTD service territory and operated by utility
|  | Number of fault indicators in non-HFTD (normalized) | 11.35 | Total number located in non-HFTD service territory and operated by utility, divided by total number of circuit miles in non-HFTD service territory
|  | Number of fault indicators in HFTD Zone 1 (total) | 46 | Total number located in HFTD Zone 1 service territory and operated by utility
|  | Number of fault indicators in HFTD Zone 1 (normalized) | 6.42 | Total number located in HFTD Zone 1 service territory and operated by utility, divided by total number of circuit miles in HFTD Zone 1 service territory
|  | Number of fault indicators in HFTD Tier 2 (total) | 21312 | Total number located in HFTD Tier 2 service territory and operated by utility
|  | Number of fault indicators in HFTD Tier 2 (normalized) | 17.18 | Total number located in HFTD Tier 2 service territory and operated by utility, divided by total number of circuit miles in HFTD Tier 2 service territory
|  | Number of fault indicators in HFTD Tier 3 (total) | 1886 | Total number located in HFTD Tier 3 service territory and operated by utility
|  | Number of fault indicators in HFTD Tier 3 (normalized) | 17.18 | Total number located in HFTD Tier 3 service territory and operated by utility, divided by total number of circuit miles in HFTD Tier 3 service territory

## Table 16
CA 2020 WMP
Section | 3.4.2 | Planned additions, removal, and upgrade of utility equipment by end of 3-year plan term
Table | 16 | Location of planned utility equipment additions or removal by end of 3-yr plan
| Land use | Characteristic tracked | Changes by end-2022
|  |  | In non-HFTD | In HFTD Zone 1 | In HFTD Tier 2 | In HFTD Tier 3
| In urban areas | Circuit miles of overhead transmission lines | 0 | 0 | 0 | 0
|  | Circuit miles of overhead distribution lines | 0 | 0 | 0 | 0
|  | Circuit miles of overhead transmission lines in WUI | 0 | 0 | 0 | 0
|  | Circuit miles of overhead distribution lines in WUI | 0 | 0 | 0 | 0
|  | Number of substations | 0 | 0 | 0 | 0
|  | Number of substations in WUI | 0 | 0 | 0 | 0
|  | Number of weather stations | 0 | 0 | 0 | 0
|  | Number of weather stations in WUI | 0 | 0 | 0 | 0
| In rural areas | Circuit miles of overhead transmission lines | 0 | 0 | 0.9 | 0
|  | Circuit miles of overhead distribution lines | 0 | 0 | 0 | 0
|  | Circuit miles of overhead transmission lines in WUI | 0 | 0 | 0.6 | 0
|  | Circuit miles of overhead distribution lines in WUI | 0 | 0 | 0 | 0
|  | Number of substations | 0 | 0 | 1 | 0
|  | Number of substations in WUI | 0 | 0 | 0 | 0
|  | Number of weather stations | 0 | 0 | 0 | 0
|  | Number of weather stations in WUI | 0 | 0 | 0 | 0
| In highly rural areas | Circuit miles of overhead transmission lines | 0 | 0 | 0 | 0
|  | Circuit miles of overhead distribution lines | 0 | 0 | 0 | 0
|  | Circuit miles of overhead transmission lines in WUI | 0 | 0 | 0 | 0
|  | Circuit miles of overhead distribution lines in WUI | 0 | 0 | 0 | 0
|  | Number of substations | 0 | 0 | 0 | 0
|  | Number of substations in WUI | 0 | 0 | 0 | 0
|  | Number of weather stations | 0 | 0 | 0 | 0
|  | Number of weather stations in WUI | 0 | 0 | 0 | 0

## Table 17
CA 2020 WMP
Section | 3.4.2 | Planned additions, removal, and upgrade of utility equipment by end of 3-year plan term
Table | 17 | Location of planned utility infrastructure upgrades
| Land use | Characteristic tracked | In non-HFTD |  |  | In HFTD Zone 1 |  |  | In HFTD Tier 2 |  |  | In HFTD Tier 3
|  |  | 2020 | 2021 | 2022 | 2020 | 2021 | 2022 | 2020 | 2021 | 2022 | 2020 | 2021 | 2022
| Total circuit miles planned for hardening each year, all types and locations |  | In non-HFTD 2020: 0; In HFTD Zone 1 2020: 0; In HFTD Tier 2 2020: 33.8; In HFTD Tier 3 2020: 10.3
| Total number of substations planned for hardening each year, all locations |  | In non-HFTD 2020: 2; In HFTD Zone 1 2020: 0; In HFTD Tier 2 2020: 11; In HFTD Tier 3 2020: 2
| In urban areas | Circuit miles planned for grid hardening of overhead transmission lines | In non-HFTD 2020: 0; In HFTD Zone 1 2020: 0; In HFTD Tier 2 2020: 0; In HFTD Tier 3 2020: 0
|  | Circuit miles of overhead transmission lines in WUI to harden | In non-HFTD 2020: 0; In HFTD Zone 1 2020: 0; In HFTD Tier 2 2020: 0; In HFTD Tier 3 2020: 0
|  | Circuit miles of overhead distribution lines to harden | In non-HFTD 2020: 0; In HFTD Zone 1 2020: 0; In HFTD Tier 2 2020: 0; In HFTD Tier 3 2020: 0
|  | Circuit miles of overhead distribution lines in WUI to harden | In non-HFTD 2020: 0; In HFTD Zone 1 2020: 0; In HFTD Tier 2 2020: 0; In HFTD Tier 3 2020: 0
|  | Circuit miles of overhead transmission lines in WUI to harden | In non-HFTD 2020: 0; In HFTD Zone 1 2020: 0; In HFTD Tier 2 2020: 0; In HFTD Tier 3 2020: 0
|  | Number of substations to harden | In non-HFTD 2020: 0; In HFTD Zone 1 2020: 0; In HFTD Tier 2 2020: 0; In HFTD Tier 3 2020: 0
|  | Number of substations in WUI to harden | In non-HFTD 2020: 0; In HFTD Zone 1 2020: 0; In HFTD Tier 2 2020: 0; In HFTD Tier 3 2020: 0
| In rural areas | Circuit miles of overhead transmission lines to harden | In non-HFTD 2020: 0; In HFTD Zone 1 2020: 0; In HFTD Tier 2 2020: 0; In HFTD Tier 3 2020: 0
|  | Circuit miles of overhead transmission lines in WUI to harden | In non-HFTD 2020: 0; In HFTD Zone 1 2020: 0; In HFTD Tier 2 2020: 0; In HFTD Tier 3 2020: 0
|  | Circuit miles of overhead distribution lines to harden | In non-HFTD 2020: 0; In HFTD Zone 1 2020: 0; In HFTD Tier 2 2020: 31.8; In HFTD Tier 3 2020: 10.3
|  | Circuit miles of overhead distribution lines in WUI to harden | In non-HFTD 2020: 0; In HFTD Zone 1 2020: 0; In HFTD Tier 2 2020: 14.5; In HFTD Tier 3 2020: 5.8
|  | Circuit miles of overhead transmission lines in WUI to harden | In non-HFTD 2020: 0; In HFTD Zone 1 2020: 0; In HFTD Tier 2 2020: 0; In HFTD Tier 3 2020: 0
|  | Number of substations to harden | In non-HFTD 2020: 2; In HFTD Zone 1 2020: 0; In HFTD Tier 2 2020: 8; In HFTD Tier 3 2020: 2
|  | Number of substations in WUI to harden | In non-HFTD 2020: 0; In HFTD Zone 1 2020: 0; In HFTD Tier 2 2020: 7; In HFTD Tier 3 2020: 1
| In highly rural areas | Circuit miles of overhead transmission lines to harden | In non-HFTD 2020: 0; In HFTD Zone 1 2020: 0; In HFTD Tier 2 2020: 0; In HFTD Tier 3 2020: 0
|  | Circuit miles of overhead transmission lines in WUI to harden | In non-HFTD 2020: 0; In HFTD Zone 1 2020: 0; In HFTD Tier 2 2020: 0; In HFTD Tier 3 2020: 0
|  | Circuit miles of overhead distribution lines to harden | In non-HFTD 2020: 0; In HFTD Zone 1 2020: 0; In HFTD Tier 2 2020: 2; In HFTD Tier 3 2020: 0
|  | Circuit miles of overhead distribution lines in WUI to harden | In non-HFTD 2020: 0; In HFTD Zone 1 2020: 0; In HFTD Tier 2 2020: 1; In HFTD Tier 3 2020: 0
|  | Circuit miles of overhead transmission lines in WUI to harden | In non-HFTD 2020: 0; In HFTD Zone 1 2020: 0; In HFTD Tier 2 2020: 0; In HFTD Tier 3 2020: 0
|  | Number of substations to harden | In non-HFTD 2020: 0; In HFTD Zone 1 2020: 0; In HFTD Tier 2 2020: 3; In HFTD Tier 3 2020: 0
|  | Number of substations in WUI to harden | In non-HFTD 2020: 0; In HFTD Zone 1 2020: 0; In HFTD Tier 2 2020: 1; In HFTD Tier 3 2020: 0

## Table 18-18d
CA 2020 WMP
Section | 3.4.3 | Status quo ignition probability drivers by service territory
Table | 18 | Key drivers of ignition probability - transmission
All Seasons
Transmission
| Incident Type by ignition probability driver |  | Number of incidents per year (according to 5-year Historical Average) | Average likelihood of ignition per Incident | Ignitions from this driver (according to 5-year historical average)
[5 empty] | Total | In non-HFTD | In HFTD - Zone 1 | In HFTD - Tier 2 | In HFTD - Tier 3
| Contact from object | Animal contact | 1.2 | 16.67% | 1 | 1 | 0 | 0 | 0
|  | Balloon contact | 0 | 0% | 0 | 0 | 0 | 0 | 0
|  | Other | 7.2 | 0% | 0 | 0 | 0 | 0 | 0
|  | Unknown | 0.4 | 0% | 0 | 0 | 0 | 0 | 0
|  | Veg. contact | 3.8 | 0% | 0 | 0 | 0 | 0 | 0
|  | Vehicle contact | 0.4 | 0% | 0 | 0 | 0 | 0 | 0
| Contamination |  | 1.8 | 0% | 0 | 0 | 0 | 0 | 0
| All typed of Equipment/ Facility failure | Conductor | 2.2 | 0% | 0 | 0 | 0 | 0 | 0
|  | Crossarm | 0 | 0% | 0 | 0 | 0 | 0 | 0
|  | Fuse | 0 | 0% | 0 | 0 | 0 | 0 | 0
|  | Insulator | 0 | 0% | 0 | 0 | 0 | 0 | 0
|  | Lightning arrestor | 0 | 0% | 0 | 0 | 0 | 0 | 0
|  | Other | 1.4 | 0% | 0 | 0 | 0 | 0 | 0
|  | Pole | 0 | 0% | 0 | 0 | 0 | 0 | 0
|  | Sectionalizer | 0 | 0% | 0 | 0 | 0 | 0 | 0
|  | Splice/clamp/connector | 0.2 | 100% | 1 | 0 | 0 | 1 | 0
|  | Switch | 0 | 0% | 0 | 0 | 0 | 0 | 0
|  | Transformer | 0 | 0% | 0 | 0 | 0 | 0 | 0
|  | Voltage regulator | 0 | 0% | 0 | 0 | 0 | 0 | 0
| Normal Operation |  | 1.4 | 0% | 0 | 0 | 0 | 0 | 0
| Other |  | 13.2 | 0% | 0 | 0 | 0 | 0 | 0
| Unknown |  | 22 | 0.9091% | 1 | 0 | 0 | 1 | 0
| Vandalism/Theft |  | 0 | 0% | 0 | 0 | 0 | 0 | 0
| Wire-to-wire contact |  | 0.4 | 0% | 0 | 0 | 0 | 0 | 0
| Contact from 3rd party |  | 0.4 | 0% | 0 | 0 | 0 | 0 | 0
Section | 3.4.3 | Status quo ignition probability drivers by service territory
Table | 18b | Key drivers of ignition probability – distribution
All Seasons
Distribuiton
| Incident Type by ignition probability driver |  | Number of incidents per year (according to 5-year Historical Average) | Average likelihood of ignition per Incident | Ignitions from this driver (according to 5-year historical average)
[5 empty] | Total | In non-HFTD | In HFTD - Zone 1 | In HFTD - Tier 2 | In HFTD - Tier 3
| Contact from object | Animal contact | 43.2 | 1.389% | 3 | 2 | 0 | 1 | 0
|  | Balloon contact | 0.6 | 0% | 0 | 0 | 0 | 0 | 0
|  | Other | 42.8 | 0% | 0 | 0 | 0 | 0 | 0
|  | Unknown | 2.8 | 0% | 0 | 0 | 0 | 0 | 0
|  | Veg. contact | 131.4 | 0.9132% | 6 | 3 | 0 | 3 | 0
|  | Vehicle contact | 12.4 | 1.613% | 1 | 1 | 0 | 0 | 0
| Contamination |  | 3.8 | 0% | 0 | 0 | 0 | 0 | 0
| All typed of Equipment/ Facility failure | Conductor | 32.6 | 1.84% | 3 | 2 | 0 | 1 | 0
|  | Crossarm | 4.2 | 4.762% | 1 | 1 | 0 | 0 | 0
|  | Fuse | 130.6 | 0.3063% | 2 | 2 | 0 | 0 | 0
|  | Insulator | 4.2 | 0% | 0 | 0 | 0 | 0 | 0
|  | Lightning arrestor | 11.4 | 0% | 0 | 0 | 0 | 0 | 0
|  | Other | 21.8 | 0% | 0 | 0 | 0 | 0 | 0
|  | Pole | 5.8 | 0% | 0 | 0 | 0 | 0 | 0
|  | Sectionalizer | 0.2 | 0% | 0 | 0 | 0 | 0 | 0
|  | Splice/clamp/connector | 81.8 | 0.2445% | 1 | 1 | 0 | 0 | 0
|  | Switch | 0.4 | 0% | 0 | 0 | 0 | 0 | 0
|  | Transformer | 45.2 | 0.4425% | 1 | 1 | 0 | 0 | 0
|  | Voltage regulator | 0.2 | 0% | 0 | 0 | 0 | 0 | 0
| Normal Operation |  | 21.6 | 0% | 0 | 0 | 0 | 0 | 0
| Other |  | 141.8 | 0.141% | 1 | 1 | 0 | 0 | 0
| Unknown |  | 105.8 | 0% | 0 | 0 | 0 | 0 | 0
| Vandalism/Theft |  | 0.8 | 0% | 0 | 0 | 0 | 0 | 0
| Wire-to-wire contact |  | 8.8 | 0% | 0 | 0 | 0 | 0 | 0
| Contact from 3rd party |  | 4 | 5% | 1 | 0 | 0 | 1 | 0
Section | 3.4.3 | Status quo ignition probability drivers by service territory
Table | 18c | Key drivers of ignition probability during fire season – transmission
Fire Seasons
Transmission
| Incident Type by ignition probability driver |  | Number of incidents per year (according to 5-year Historical Average) | Average likelihood of ignition per Incident | Ignitions from this driver (according to 5-year historical average)
[5 empty] | Total | In non-HFTD | In HFTD - Zone 1 | In HFTD - Tier 2 | In HFTD - Tier 3
| Contact from object | Animal contact | 1 | 20% | 1 | 1 | 0 | 0 | 0
|  | Balloon contact | 0 | 0% | 0 | 0 | 0 | 0 | 0
|  | Other | 6.2 | 0% | 0 | 0 | 0 | 0 | 0
|  | Unknown | 0.2 | 0% | 0 | 0 | 0 | 0 | 0
|  | Veg. contact | 0.8 | 0% | 0 | 0 | 0 | 0 | 0
|  | Vehicle contact | 0.2 | 0% | 0 | 0 | 0 | 0 | 0
| Contamination |  | 1.8 | 0% | 0 | 0 | 0 | 0 | 0
| All typed of Equipment/ Facility failure | Conductor | 0.2 | 0% | 0 | 0 | 0 | 0 | 0
|  | Crossarm | 0 | 0% | 0 | 0 | 0 | 0 | 0
|  | Fuse | 0 | 0% | 0 | 0 | 0 | 0 | 0
|  | Insulator | 0 | 0% | 0 | 0 | 0 | 0 | 0
|  | Lightning arrestor | 0 | 0% | 0 | 0 | 0 | 0 | 0
|  | Other | 0 | 0% | 0 | 0 | 0 | 0 | 0
|  | Pole | 0 | 0% | 0 | 0 | 0 | 0 | 0
|  | Sectionalizer | 0 | 0% | 0 | 0 | 0 | 0 | 0
|  | Splice/clamp/connector | 0.2 | 100% | 1 | 0 | 0 | 1 | 0
|  | Switch | 0 | 0% | 0 | 0 | 0 | 0 | 0
|  | Transformer | 0 | 0% | 0 | 0 | 0 | 0 | 0
|  | Voltage regulator | 0 | 0% | 0 | 0 | 0 | 0 | 0
| Normal Operation |  | 0.6 | 0% | 0 | 0 | 0 | 0 | 0
| Other |  | 2.2 | 0% | 0 | 0 | 0 | 0 | 0
| Unknown |  | 5.6 | 3.571% | 1 | 0 | 0 | 1 | 0
| Vandalism/Theft |  | 0 | 0% | 0 | 0 | 0 | 0 | 0
| Wire-to-wire contact |  | 0.2 | 0% | 0 | 0 | 0 | 0 | 0
| Contact from 3rd party |  | 0.2 | 0% | 0 | 0 | 0 | 0 | 0
Section | 3.4.3 | Status quo ignition probability drivers by service territory
Table | 18d | Key drivers of ignition probability during fire season – distribution
Fire Seasons
Distribuiton
| Incident Type by ignition probability driver |  | Number of incidents per year (according to 5-year Historical Average) | Average likelihood of ignition per Incident | Ignitions from this driver (according to 5-year historical average)
[5 empty] | Total | In non-HFTD | In HFTD - Zone 1 | In HFTD - Tier 2 | In HFTD - Tier 3
| Contact from object | Animal contact | 22.2 | 1.802% | 2 | 1 | 0 | 1 | 0
|  | Balloon contact | 0.4 | 0% | 0 | 0 | 0 | 0 | 0
|  | Other | 30.4 | 0% | 0 | 0 | 0 | 0 | 0
|  | Unknown | 1 | 0% | 0 | 0 | 0 | 0 | 0
|  | Veg. contact | 21.2 | 2.83% | 3 | 2 | 0 | 1 | 0
|  | Vehicle contact | 5 | 4% | 1 | 1 | 0 | 0 | 0
| Contamination |  | 2.2 | 0% | 0 | 0 | 0 | 0 | 0
| All typed of Equipment/ Facility failure | Conductor | 6.8 | 5.882% | 2 | 1 | 0 | 1 | 0
|  | Crossarm | 0.8 | 25% | 1 | 1 | 0 | 0 | 0
|  | Fuse | 36.6 | 1.093% | 2 | 2 | 0 | 0 | 0
|  | Insulator | 1.2 | 0% | 0 | 0 | 0 | 0 | 0
|  | Lightning arrestor | 3.6 | 0% | 0 | 0 | 0 | 0 | 0
|  | Other | 5.8 | 0% | 0 | 0 | 0 | 0 | 0
|  | Pole | 2.2 | 0% | 0 | 0 | 0 | 0 | 0
|  | Sectionalizer | 0 | 0% | 0 | 0 | 0 | 0 | 0
|  | Splice/clamp/connector | 17.2 | 1.163% | 1 | 1 | 0 | 0 | 0
|  | Switch | 0.2 | 0% | 0 | 0 | 0 | 0 | 0
|  | Transformer | 20.4 | 0.9804% | 1 | 1 | 0 | 0 | 0
|  | Voltage regulator | 0 | 0% | 0 | 0 | 0 | 0 | 0
| Normal Operation |  | 7.4 | 0% | 0 | 0 | 0 | 0 | 0
| Other |  | 8.2 | 2.439% | 1 | 1 | 0 | 0 | 0
| Unknown |  | 30 | 0% | 0 | 0 | 0 | 0 | 0
| Vandalism/Theft |  | 0 | 0% | 0 | 0 | 0 | 0 | 0
| Wire-to-wire contact |  | 0.8 | 0% | 0 | 0 | 0 | 0 | 0
| Contact from 3rd party |  | 1.2 | 16.67% | 1 | 0 | 0 | 1 | 0

## Table 19
CA 2020 WMP
Section | 4.2.1 | Service territory fire-threat evaluation and ignition risk trends
Table | 19 | Macro trends impacting ignition probability and/or wildfire consequence
| Rank | Macro trends impacting utility ignited ignition probability and estimated wildfire consequence by year 10 | Comments
| 1 | Change in ignition probability and estimated wildfire consequence due to climate change | Reduced live and dead fuel moisture values relative to the historical baseline correlate with increased fire severity. Tree mortality induced by climate change may increase ignitions associated with tree line contact.
| 5 | Change in ignition probability and estimated wildfire consequence due to relevant invasive species, such as bark beetles | Tree mortality induced by disturbances such as beetle kill may increase ignitions associated with tree line contact. The relation between tree mortality and fire behavior is not clear and remains an active research area.
| 2 | Change in ignition probability and estimated wildfire consequence due to other drivers of change in fuel density and moisture | 100+ years of fire suppression and exclusion have contributed to higher fuel loading and a shift from frequent low intensity fires that benefit the landscape to a smaller number of intense fires that have negative effects on the landscape.
| 7 | Population changes (including Access and Functional Needs population) that could be impacted by utility ignition | This macro trend was interpreted to refer to aging population and individuals with limited mobility and/or cognitive impairments and how they could be impacted by utility-caused ignitions. Due to limited urban populations, this is not viewed as a major driver of fire consequence in PacifiCorp's service territory.
| 8 | Population changes in HFTD that could be impacted by utility ignition | Future demographic trends in PacifiCorp's service territory are unknown, but this is not viewed as a major driver of fire consequence in PacifiCorp's service territory
| 6 | Population changes in WUI that could be impacted by utility ignition | Structures in Wildland Urban Interface or Intermix are more vulnerable to fire losses than those in urbanized areas. As more structures are built in WUI/Intermix areas fire losses from all causes, not just utility ignitions, may increase.
| 3 | Utility infrastructure location in HFTD vs non-HFTD | As additional utility infrastructure is added to HFTD areas to serve new development, utility ignition probability may increase due to the presence of utilities in HFTD areas that previously had no utility infrastructure. However, some of this increase in ignition probability may be offset by hardened infrastructure, advanced coordination, improved real-time monitoring of circuits or other fire prevention measures such as proactive de-energization.
| 4 | Utility infrastructure location in urban vs rural vs highly rural areas | As more structures are built in rural & highly rural areas that are connected to the grid, increased presence of utilities may in areas that previously contained no utilities may increase utility ignition probability. However, some of this increase in ignition probability may be offset by hardened infrastructure, advanced coordination, improved real-time monitoring of circuits or other fire prevention measures such as proactive de-energization.

## Table 20
CA 2020 WMP
Section | 4.4 | Directional vision for necessary PSPS
Table | 20 | Macro trends impacting ignition probability and/or wildfire consequence
| Rank Order [1-9] | PSPS Characteristic | Significantly increase, increase, no change, decreased, significantly decrease | Comments
| 4 | Number of customers affected by PSPS events (total) | Decrease | As PacifiCorp’s system hardening programs bias toward customer density, PacifiCorp assumes this will be the second most impactful characteristic.
| 3 | Number of customers affected by PSPS events (normalized by fire weather, e.g., Red Flag Warning line mile days) | Decrease
| 6 | Frequency of PSPS events in number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability (total) | Decrease | PacifiCorp assumes implementation of system hardening projects as well as situational awareness will significantly affect threshold criteria and improve the quality of information used to implement PSPS events.
| 5 | Frequency of PSPS events in number of instances where utility operating protocol requires de-energization of a circuit or portion thereof to reduce ignition probability (normalized by fire weather, e.g., Red Flag Warning line mile days) | Decrease
| 2 | Scope of PSPS events in circuit-events, measured in number of events multiplied by number of circuits targeted for de-energization (total) | Significantly Decrease | PacifiCorp assumes implementation of system hardening projects as well as situational awareness will significantly decrease the scope of potential future PSPS event.
| 1 | Scope of PSPS events in circuit-events, measured in number of events multiplied by number of circuits targeted for de-energization (normalized by fire weather, e.g., | Significantly Decrease
| 8 | Duration of PSPS events in customer hours (total) | Decrease | PacifiCorp assumes implementation of system hardening projects as well as situational awareness will significantly affect threshold criteria and improve the quality of information used to implement PSPS events, including the decision to end a PSPS event affecting duration.
| 7 | Duration of PSPS events in customer hours (normalized by fire weather, e.g., Red Flag | Decrease
| N/A | Other | N/A | N/A

## Table 21
CA 2020 WMP
Section | 5.3.1 | Detailed WMP programs - risk assessment and mapping
Table | 21 | Risk assessment and mapping
| Initiative activity | year | Line miles to be treated | Spend/treated line mile | Ignition probability drivers targeterd | Risk reduction | risk-spend efficiency | Other risk drivers addressed | Existing/new | Existing:What proceeding has reviewed program | If new: Memorandum account | In/exceeding compliance with regulations | Cite associated rule | Comments
| 1. A summarized risk map showing the overall ignition probability and estimated wildfire consequence along electric lines and equipment | 2019 plan | PacifiCorp implemented fully throughout its systems the California High Fire Threat Map, which quantifies specific geography that under historically-viable fire weather conditions, could be subject to elevated fire risk. It created associations between the tier designation to inform inspection, vegetation management, correction timeframes, and prioritized hardening efforts. Wildfire risk mapping is foundational to prioritizing efforts for a variety of activities undertaken throughout the business. With this information certain program locations can be advanced more rapidly, while other locations can be addressed later.
2019 actual
2020
2021
2022
2020-2022 plan total
| 2. Climate-driven risk map modeling based on various | 2019 plan | Develop methods for incorporating climate impacts into wildfire risks into system hardening (long term prioritization) as well as situational awareness (short term response) actions. Specific climate conditions may result in elevated wildfire risk, as is experienced in southern California during Santa Ana wind conditions. To the extent that such a phenomenon exists in PacifiCorp’s service territory, outlining the leading indicators of the condition, the probable effects and the appropriate mitigation measures is an important augmentation of the company’s WMP. PacifiCorp develops such theories engaging peer review to ensure well-vetted rationale and reasonable outcomes. To the extent that a climatological phenomenon is identified it would anticipate reviewing such products with audiences in venues such as the California Utility Forecasters Meeting | NA | Contact from object; All types of equipment/facility failure; Wire-to-wire contact/contamination; Other | NA | NA | NA | NA | NA | NA | NA | NA | NA
|  | 2019 actual | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA
|  | 2020 | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA
|  | 2021 | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA
|  | 2022 | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA
|  | 2020-2022 plan total | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA
| 3. Ignition probability mapping showing the probability of ignition along the electric lines and equipment | 2019 plan | N/A | N/A | Contact from object; All types of equipment/facility failure; Wire-to-wire contact/contamination; Other | Reduced risk due to utility ignition | N/A | Better use of PSPS in light of equipment and weather coincidence | New | N/A | 2019 WMP Memorandum Account | Exceeds current requirements | GO95 Generally | Anticipate one study outcome per year, which is generally cumulative
|  | 2019 actual | N/A | N/A |  |  |  | NA | NA
|  | 2020 | 1 | 25000 |  |  |  | NA | NA
|  | 2021 | 1 | 25000 |  |  |  | NA | NA
|  | 2022 | 1 | 25000 |  |  |  | NA | NA
|  | 2020-2022 plan total | 3 | 25000 |  |  |  | NA | NA
| 4. Initiative mapping and estimation of wildfire and PSPS risk-reduction impact | 2019 plan | N/A | N/A | Improper Application of PSPS Actions | Reduced risk due to utility ignition | N/A | Better informed stakeholder understanding of PSPS | Existing | N/A | 2019 WMP Memorandum Account | Exceeds current requirements | GO95 Generally | Advanced ESRB-8 and HFTD maps to quantify impacted areas; communicated with communities
|  | 2019 actual | [5 empty] | NA | NA
|  | 2020 | [5 empty] | NA | NA
|  | 2021 | [5 empty] | NA | NA
|  | 2022 | [5 empty] | NA | NA
|  | 2020-2022 plan total | [5 empty] | NA | NA
| 5. Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment | 2019 plan | PacifiCorp does not, at this time, have a risk assessment and mapping wildfire mitigation program focused on match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment.
2019 actual
2020
2021
2022
2020-2022 plan total
| 6. Weather-driven risk map an modeling based on various relevant weather scenarios | 2019 plan | N/A | N/A | Contact from object; All types of equipment/facility failure; Wire-to-wire contact/contamination; Other | Reduced risk due to utility ignition | N/A | Better use of PSPS in light of equipment and weather coincidence | Existing | N/A | 2019 WMP Memorandum Account | Exceeds current requirements | GO95 Generally | No specific charges developed for this plan; Assumes annual refresh to support operational and PSPS thresholds
|  | 2019 actual | [5 empty] | NA | NA
|  | 2020 | [5 empty] | NA | NA
|  | 2021 | [5 empty] | NA | NA
|  | 2022 | [5 empty] | NA | NA
|  | 2020-2022 plan total | [5 empty] | NA | NA
| 7.Other/not listen [only is an initiative cannot feasibly be classified within those listen above] | 2019 plan | PacifiCorp, at this time, does not have any additional risk assessment and mapping wildfire mitigation programs.
2019 actual
2020
2021
2022
2020-2022 plan total

## Table 22
CA 2020 WMP
Section | 5.3.2 | Detailed WMP programs
Table | 22 | Situational awareness and forecasting
| Initiative activity | year | Line miles to be treated | Spend/treated line mile | Ignition probability drivers targeted | Risk reduction | risk-spend efficiency | Other risk drivers addressed | Existing/new | Existing: What proceeding has reviewed program | If new: Memorandum account | In/exceeding compliance with regulations | Cite associated rule | Comments
| 1. Advanced weather monitoring and weather stations | 2019 plan | NA | NA | Contact from object; All types of equipment/facility failure; Wire-to-wire contact/contamination; Other | N/A | N/A | N/A | New Proposed 2019 | N/A | 2019 WMP Memorandum Account | N/A (Supports structural loading cases for regular application) | GO95 Section IV | Generally uses microstations with evaluation for RAWS-quality measurements
|  | 2019 actual | 10 | 12833.5
|  | 2020 | 10 | 16600
|  | 2021 | 10 | 13000
|  | 2022 | 5 | 13000
|  | 2020-2022 plan total | 25 | 14440
| 2. Continuous monitoring sensors | 2019 plan | NA | NA | Contact from object; All types of equipment/facility failure; Wire-to-wire contact/contamination; Other | N/A | N/A | Decreases probability of evolving situation culminating in fault event | New Proposed 2020 | N/A | 2019 WMP Memorandum Account | Exceeds Regulation | GO95 Generally | Expansion of technology contingent of successful pilot experiences
|  | 2019 actual | 0 | 0
|  | 2020 | 4 | 28000
|  | 2021 | 8 | 28000
|  | 2022 | 12 | 28000
|  | 2020-2022 plan total | 24 | 28000
| 3. Fault indicators for detecting faults on electric lines and equipment | 2019 plan | While this program is critical to facilitate situational awareness, the overall management of this program is better suited with PacifiCorp’s grid design and system hardening program focused on system automation, additional details have been included in Section 5.3.3.9. Costs and timelines for this program were outlined in Table 23, Initiative Activities 2.
2019 actual
2020
2021
2022
2020-2022 plan total
| 4. Forecast of a fire risk index, fire potential index, or similar | 2019 plan | At this time PacifiCorp has not established a plan to develop a fire risk index beyond that which it is communicated in its 2019 and 2020 WMPs. In addition, no specific incremental spend has been identified.
2019 actual
2020
2021
2022
2020-2022 plan total
| 5. Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | 2019 plan | Additional resources deployed during elevated fire risk conditions is captured in section 5.3.6.3.
2019 actual
2020
2021
2022
2020-2022 plan total
| 6. Weather forecasting and estimating impacts on electric lines and equipment | 2019 plan | N/A | N/A | Contact from object; All types of equipment/facility failure; Wire-to-wire contact/contamination; Other | N/A | N/A | Minimizes PSPS impacts to customers | New Proposed 2019 | N/A | 2019 WMP Memorandum Account | in/Exceeds Regulation | ESRB-8 | Persists approach applied during 2019 fire season; retained forecasting firm with company-establish thresholds
2019 actual
2020
2021
2022
2020-2022 plan total
| 7.Other/not listen [only is an initiative cannot feasibly be classified within those listen above] | 2019 plan | At this time, PacifiCorp does not have any specific situation awarenes and forecasting programs focused not included in other programs.
2019 actual
2020
2021
2022
2020-2022 plan total

## Table 23
CA 2020 WMP
Section | 5.3.3 | Detailed WMP programs
Table | 23 | Grid design and system hardening
| Initiative activity | year | Line miles to be treated | Spend/treated line mile | Ignition probability drivers targeted | Risk reduction | risk-spend efficiency | Other risk drivers addressed | Existing/new | Existing: What proceeding has reviewed program | If new: Memorandum account | In/exceeding compliance with regulations | Cite associated rule | Comments
| 1. Capacitor maintenance and replacement program | 2019 plan | At this time, PacifiCorp does not have a specific grid design and system hardening wildfire mitigation program focused on capacitor maintenance and replacement. Capacitor replacement and maintenance is included in the company’s standard inspection, maintenance, and replacement protocols. Any enhanced inspections or accelerated correction timeframe/replacements are captured in Section 5.3.4.3, Improvement of inspections.
2019 actual
2020
2021
2022
2020-2022 plan total
| 2. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault | 2019 plan | At this time, PacifiCorp does not have a specific grid design and system hardening wildfire mitigation program focused on circuit breaker maintenance and replacement. Circuit breakers are generally installed for all distribution circuits and transmission lines to detect fault current and protect equipment in the event that a fault is detected. Circuit breaker replacement and maintenance is included in the company’s standard inspection, maintenance, and replacement protocols. Any enhanced inspections or accelerated correction timeframe/replacements are captured in Section 5.3.4.3, Improvement of inspections. Replacement of specific, targeted circuit breakers as a part of PacifiCorp’s WMP to support overall advanced coordination and detection efforts are better captured in initiative 5.3.3.9, Installation of system automation equipment.
2019 actual
2020
2021
2022
2020-2022 plan total
| 3. Covered conductor installation - transmission | 2019 plan | N/A | N/A | Contact from object; Wire-to-wire contact / contamination | N/A | N/A | N/A | New Proposed in 2019 | N/A | 2019 WMP Memorandum Account | N/A (exceeds standard design) | N/A | Program can include multiple design types based on installation voltage/ type
|  | 2019 actual | 0 | 0
|  | 2020 | 0 | 0
|  | 2021 | 8 | 725000
|  | 2022 | 8 | 725000
|  | 2020-2022 plan total | 16 | 725000
| 3b. Covered conductor installation - distribution | 2019 plan | N/A | N/A | Contact from object; Wire-to-wire contact / contamination | N/A | N/A | N/A | New Proposed in 2019 | N/A | 2019 WMP Memorandum Account | N/A (exceeds standard design) | N/A | Program can include multiple design types based on installation voltage/ type
|  | 2019 actual | 0 | 0
|  | 2020 | 38 | 207236.8421
|  | 2021 | 52 | 218903.8462
|  | 2022 | 41 | 282439.0244
|  | 2020-2022 plan total | 131 | 235404.5802
| 4. Covered conductor maintenance | 2019 plan | At this time, PacifiCorp does not have any grid design and system hardening programs focused on covered conductor maintenance. As PacifiCorp progresses with implementation of the company wildfire mitigation programs, the company will continue to evaluate covered conductor specific wildfire mitigation maintenance programs.
2019 actual
2020
2021
2022
2020-2022 plan total
| 5. Crossarm maintenance, repair, and replacement | 2019 plan | At this time, PacifiCorp does not have a specific grid design and system hardening wildfire mitigation program focused on crossarm maintenance, repair, and replacement. Routine crossarm maintenance, repair, and replacement are included in the company’s standard inspection and correction programs, with an accelerated timeline for correction under the company’s Inspection program improvement, Section 5.3.4.3.
2019 actual
2020
2021
2022
2020-2022 plan total
| 6. Distribution pole replacement and reinforcement, including with composite poles | 2019 plan | N/A | N/A | Contact from object; All types of equipment / facility failure | N/A | N/A | Facilitates restoration efforts through enhanced resiliency | New Element Proposed in 2019 | CA GO 95 & 165 2018 GRC | 2019 WMP Memorandum Account | Exceeds Regulation | CA GO 95 & 165 | Exceeds regulation to the extent that poles are identified for replacement above and beyond standard inspection programs
|  | 2019 actual | 0 | 0
|  | 2020 | 39 | 8435.8974
|  | 2021 | 300 | 8426.6667
|  | 2022 | 300 | 8426.6667
|  | 2020-2022 plan total | 639 | 8427.23
| 6b. Transmission pole replacement and reinforcement, including with composite poles | 2019 plan | N/A | N/A | Contact from object; All types of equipment / facility failure | N/A | N/A | Facilitates restoration efforts through enhanced resiliency | New Element Proposed in 2019 | CA GO 95 & 165 2018 GRC | 2019 WMP Memorandum Account | Exceeds Regulation | CA GO 95 & 165 | Exceeds regulation to the extent that poles are identified for replacement above and beyond standard inspection programs
|  | 2019 actual | 0 | 0
|  | 2020 | 150 | 24480
|  | 2021 | 180 | 24477.7778
|  | 2022 | 180 | 24477.7778
|  | 2020-2022 plan total | 510 | 24478.4314
| 7.Expulsion fuse replacement | 2019 plan | PacifiCorp is incorporating this element into other system hardening programs to embrace maximum planning and spend efficiency (pole replacement, covered conductor replacement, advanced coordination, etc. PacifiCorp will continue to evaluate the need for an additional overhead expulsion fuse program should all fuses not be replaced through other programs
2019 actual
2020
2021
2022
2020-2022 plan total
| 8. Grid topology improvements to mitigate or reduce PSPS events | 2019 plan | N/A | N/A | N/A - Not an ignition probability risk reduction program | N/A | N/A | Reduced impact of PSPS events | New Proposed in 2019 | N/A | 2019 WMP Memorandum Account | Exceeds standard engineering design | N/A | In evaluation phase; No specific program dollars assigned. See Section 5.3.3.8
2019 actual
2020
2021
2022
2020-2022 plan total
| 9. Installation of system automation equipment | 2019 plan | N/A | N/A | All - Regardless of cause, this program reduces that potential that a fault scenario results in an ignition event | N/A | N/A | N/A | New Proposed in 2019 | N/A | 2019 WMP Memorandum Account | N/A (exceeds standard design) | N/A | As these projects are not scoped on a line-mile basis, the values reported reflect projects
|  | 2019 actual | 10 | 271445.2
|  | 2020 | 31 | 97710.0968
|  | 2021 | 24 | 76375
|  | 2022 | 3 | 166666.6667
|  | 2020-2022 plan total | 58 | 92448.5
| 10. Maintenance, repair, and replacement of connectors, including hotline clamps | 2019 plan | PacifiCorp does not currently have a specific grid design and system hardening wildfire mitigation program focused on maintenance, repair, and replacement of connectors, including hotline clamps. Replacement of connectors, where applicable, is included in other programs such as installation of covered conductor.
2019 actual
2020
2021
2022
2020-2022 plan total
| 11. Mitigation of impact on customers and other residents affected during PSPS events | 2019 plan | PacifiCorp does not currently have an additional grid design and system hardening wildfire mitigation program focused on mitigation of impact on customers and other residents affected during PSPS event outside of the initiatives described in Section 5.3.3.8. Both of these programs are combined as relevant grid topology improvements pertaining to grid design and system hardening that reduce PSPS events inherently also mitigate the impact on customers. Furthermore, PacifiCorp’s additional programs or efforts to mitigate the impact on customers and other residents affected during a PSPS event are described in Section 4.4 and Section 5.6.2.
2019 actual
2020
2021
2022
2020-2022 plan total
| 12. Other corrective action | 2019 plan | At this time, PacifiCorp does not have any grid design and system hardening wildfire mitigation programs focused on other corrective action. PacifiCorp’s relevant corrective actions are included in the company’s Improvement of inspections in Section 5.3.4.3.
2019 actual
2020
2021
2022
2020-2022 plan total
| 13. Pole loading infrastructure hardening and replacement program based on pole loading assessment program | 2019 plan | Pole loading to accommodate safety factors and necessary specifications are included in PacifiCorp’s engineering and construction standards. At this time, PacifiCorp has piloted the use of LiDAR to create structural models to calculate pole loading capacity. In addition, specific pole loading assessment of in-service assets was included as a subset to the methodology of PacifiCorp’s pole replacement programs included in Section 5.3.3.6. Where appropriate, pole loading assessment of new construction has also been incorporated into the new standards developed included in Section 5.3.3.6.
2019 actual
2020
2021
2022
2020-2022 plan total
| 14. Transformers maintenance and replacement | 2019 plan | At this time, PacifiCorp does not have a specific grid design and system hardening wildfire mitigation program focused on transformer maintenance and replacement. Transformer replacement and maintenance is included in the company’s standard inspection, maintenance, and replacement protocols. Any enhanced inspections or accelerated correction timeframe/replacements are captured in Section 5.3.4.3, Improvement of inspections.
2019 actual
2020
2021
2022
2020-2022 plan total
| 15. Transmission tower maintenance and replacement | 2019 plan | PacifiCorp does not have a specific grid design and system hardening wildfire mitigation program focused on transmission tower maintenance and replacement outside of standard inspection and correction programs describes in Section 5.3.4 or transmission pole replacement as included in Section 5.3.3.6.
2019 actual
2020
2021
2022
2020-2022 plan total
| 16. Undergrounding of electric lines and/or equipment | 2019 plan | PacifiCorp recognizes that value may exist in installation of underground electrical equipment. However, at this time, PacifiCorp does not have any grid design and system hardening wildfire mitigation programs specifically focused on undergrounding of electric lines and/or equipment.
2019 actual
2020
2021
2022
2020-2022 plan total
| 17. Updates to grid topology to minimize risk of ignition in HFTDs | 2019 plan | At this time, PacifiCorp does not have any specific grid design and system hardening wildfire mitigation programs focus on updates to grid topology to minimize risk of ignition in HFTDs. PacifiCorp recognizes that, as weather patterns change and overall modeling and assessments evolve, updates to grid topology is something to continue to evaluate. Other grid design and system hardening programs include, as a component, grid topology improvements to minimize the risk of ignition in the HFTD. Similar to the company’s grid topology improvement to mitigate or reduce PSPS events described in Section 5.3.3.8, PacifiCorp recognizes that it is challenging to mitigate wildfire risk through grid topology changes alone. Therefore, PacifiCorp focuses more on augmentation of existing circuitry through system hardening efforts included throughout Section 5.3.3.
2019 actual
2020
2021
2022
2020-2022 plan total
| 18.Other - Replace small size Cu conductor | 2019 plan | N/A | N/A | All - Regardless of the cause, this program reduces that potential that a fault scenario results in an ignition event through advanced coordination | N/A | N/A | N/A | New Proposed in 2019 | N/A | 2019 WMP Memorandum Account | N/A (exceeds standard design) | N/A | Program facilitates enhanced coordination which reduces impact of all types of fault events and reduced potential of ignition
|  | 2019 actual | 0 | 0
|  | 2020 | 3 | 166000
|  | 2021 | 26 | 51923.0769
|  | 2022 | 13 | 75000
|  | 2020-2022 plan total | 42 | 67214.2857

## Table 24
CA 2020 WMP
Section | 5.3.4 | Detailed WMP programs
Table | 24 | Asset Management and Inspections
| Initiative activity | year | Line miles to be treated | Spend/treated line mile | Ignition probability drivers targeted | Risk reduction | risk-spend efficiency | Other risk drivers addressed | Existing/new | Existing: What proceeding has reviewed program | If new: Memorandum account | In/exceeding compliance with regulations | Cite associated rule | Comments
| 1. Detailed inspections of distribution electric lines and equipment | 2019 plan | N/A | N/A | All types of equipment failure; Contact from object | N/A | N/A | N/A | Existing | CA GO 95 & 165 | N/A | In Compliance with Regulation | CA GO 95 & 165 | Program incorporated new requirements in 2019
|  | 2019 actual | 473 | 382.6638
|  | 2020 | 605 | 424.7934
|  | 2021 | 486 | 528.8066
|  | 2022 | 480 | 535.4167
|  | 2020-2022 plan total | 1571 | 490.7702
| 2. Detailed inspections of transmission electric lines and equipment | 2019 plan | 62 | 516.129 | All types of equipment failure; Contact from object | N/A | N/A | N/A | Existing | CA GO 95 & 165 | N/A | In Compliance with Regulation | CA GO 95 & 165 | Program incorporated new requirements in 2019
|  | 2019 actual | 62 | 516.129
|  | 2020 | 122 | 483.6066
|  | 2021 | 236 | 250
|  | 2022 | 268 | 220.1493
|  | 2020-2022 plan total | 626 | 282.7476
| 3. Improvements of inspections | 2019 plan | N/A - Elements already captured in other relevant programs | N/A - Elements already captured in other relevant programs | All types of equipment failure; Contact from object | N/A | N/A | N/A | New in 2019 | CA GO 95 & 165 | N/A | In Compliance with Regulation | CA GO 95 & 165 | Program improvements already captured in other relevant programs
2019 actual
2020
2021
2022
2020-2022 plan total
| 4. Infrared inspections of distribution electric lines and equipment | 2019 plan | At this time, PacifiCorp does not have a specific asset management and inspections wildfire mitigation program focused on the infrared inspections of distribution electric lines and equipment. As a part of the company’s 2019 wildfire mitigation efforts, the use of infrared technology was applied to transmission lines which is further discussed in Section 5.3.4.4. Depending on the results of this pilot project, PacifiCorp may pursue an extension of this pilot project to include distribution lines. However, the collection methodology and quality of inspection difficulties will need to be evaluated as PacifiCorp’s distribution lines tend to be located in areas with a tree canopy, making efficient collection of valuable IR data challenging.
2019 actual
2020
2021
2022
2020-2022 plan total
| 5. Infrared inspections of transmission electric lines and equipment | 2019 plan | 784 | 153.0612 | All types of equipment failure; Contact from object | N/A | N/A | N/A | New in 2019 (Pilot) | N/A | 2019 WMP Memorandum Account | Exceeding Regulations | CA GO 95 & 165 | New pilot program planning to evolve; No clear values beyond 2020 yet
|  | 2019 actual | 1246 | 154.7352
|  | 2020 | 232 | 190.0862
|  | 2021 | TBD | TBD
|  | 2022 | TBD | TBD
|  | 2020-2022 plan total | TBD | TBD
| 6. Intrusive pole inspections | 2019 plan | 92 | 880.4348 | All types of equipment failure; | N/A | N/A | N/A | Existing | CA GO 165 | N/A | In Compliance with Regulation | CA GO 95 & 165 | Existing historic compliance based program
|  | 2019 actual | 92 | 880.4348
|  | 2020 | 150 | 1486.6667
|  | 2021 | 226 | 986.7257
|  | 2022 | 230 | 969.5652
|  | 2020-2022 plan total | 606 | 1103.9604
| 7. LiDAR inspections of distribution electric lines and equipment | 2019 plan | 250 | 520 | All types of equipment failure; Contact from object | N/A | N/A | N/A | New in 2019 (Pilot) | 2019 CA WMP | 2019 WMP Memorandum Account | Exceeding Regulations | CA GO 95 & 165 | New pilot program planning to evolve; No clear values beyond 2020
|  | 2019 actual | 376 | 491.3431
|  | 2020 | TBD | TBD
|  | 2021 | TBD | TBD
|  | 2022 | TBD | TBD
|  | 2020-2022 plan total | TBD | TBD
| 8. LiDAR inspections of transmission electric lines and equipment | 2019 plan | 0 | 0 | All types of equipment failure; Contact from object | N/A | N/A | N/A | New in 2019 (Pilot) | 2019 CA WMP | 2019 WMP Memorandum Account | Exceeding Regulations | CA GO 95 & 165 | New pilot program planning to evolve; No clear values beyond 2020
|  | 2019 actual | 548 | 491.3412
|  | 2020 | TBD | TBD
|  | 2021 | TBD | TBD
|  | 2022 | TBD | TBD
|  | 2020-2022 plan total | TBD | TBD
| 9. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations | 2019 plan | At this time, PacifiCorp does not have any specific asset management and inspections wildfire mitigation programs focused on other discretionally inspection of distribution lines not included in other programs.
2019 actual
2020
2021
2022
2020-2022 plan total
| 10. Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations | 2019 plan | At this time, PacifiCorp does not have any specific asset management and inspections wildfire mitigation programs focused on other discretionally inspection of transmission lines not included in other programs.
2019 actual
2020
2021
2022
2020-2022 plan total
| 11. Patrol inspections of distribution electric lines and equipment | 2019 plan | 2002 | 161.3387 | All types of equipment failure; Contact from object | N/A | N/A | N/A | Existing | CA GO 165 | N/A | In Compliance with Regulation | CA GO 95 & 165 | Program incorporated new requirements in 2019;
|  | 2019 actual | 2002 | 161.3387
|  | 2020 | 1941 | 134.982
|  | 2021 | 2018 | 129.8315
|  | 2022 | 1941 | 134.982
|  | 2020-2022 plan total | 5900 | 133.2203
| 12. Patrol inspections of transmission electric lines and equipment | 2019 plan | 681 | 287.812 | All types of equipment failure; Contact from object | N/A | N/A | N/A | Existing | CA GO 165 | N/A | In Compliance with Regulation | CA GO 95 & 165 | Program incorporated new requirements in 2019
|  | 2019 actual | 681 | 287.812
|  | 2020 | 657 | 298.3257
|  | 2021 | 767 | 255.5411
|  | 2022 | 767 | 255.5411
|  | 2020-2022 plan total | 2191 | 268.3706
| 13. Pole loading assessment program to determine safety factor | 2019 plan | Pole loading to accommodate safety factors and necessary specifications are included in PacifiCorp’s engineering and construction standards. At this time, PacifiCorp does not have a specific asset management and inspections wildfire mitigation program focused on pole loading assessment to determine safety factor of in-service assets. Specific pole loading assessment of in-service assets was included as a subset to the methodology of PacifiCorp’s pole replacement programs included in Section 5.3.3.6. Where appropriate, pole loading assessment of new construction has also been incorporated into the new standards developed included in Section 5.3.3.6.
2019 actual
2020
2021
2022
2020-2022 plan total
| 14. Quality assurance/ quality control of inspections | 2019 plan | N/A - Elements already captured in other relevant programs | N/A - Elements already captured in other relevant programs | All | N/A | N/A | N/A | Existing | N/A | N/A | N/A | N/A | General program and best practices applied to an accounted for in other relevant programs
2019 actual
2020
2021
2022
2020-2022 plan total
| 15. Substation inspections | 2019 plan | 444 | 405.4054 | All types of equipment failure; Contact from object | N/A | N/A | N/A | Existing | CA GO 174 | N/A | In Compliance with Regulation | CA GO 174 | Values reported indicate number of substation inspections completed or planned and $/inspection
|  | 2019 actual | 439 | 393.8551
|  | 2020 | 444 | 400
|  | 2021 | 444 | 400
|  | 2022 | 444 | 400
|  | 2020-2022 plan total | 1332 | 400
| 16.Other/not listen [only is an initiative cannot feasibly be classified within those listen above] | 2019 plan | PacifiCorp does not, at this time, have any other asset management and inspections wildfire mitigation programs.
2019 actual
2020
2021
2022
2020-2022 plan total

## Table 25
CA 2020 WMP
Section | 5.3.5 | Detailed WMP programs
Table | 25 | Vegetation management and inspections
| Initiative activity | year | Line miles to be treated | Spend/treated line mile | Ignition probability drivers targeted | Risk reduction | risk-spend efficiency | Other risk drivers addressed | Existing/new | Existing: What proceeding has reviewed program | If new: Memorandum account | In/exceeding compliance with regulations | Cite associated rule | Comments
| 1. Additional efforts to manage community and environmental impacts | 2019 plan | While collaboration such as this is critical to the overall reduction of wildfire risk in the state of CA, PacifiCorp, at this time, does not have a specific program dedicated to this effort. Instead, these efforts are on an as-needed basis and incorporate additional efforts to manage community environments within other programs, such as those included in Section 5.3.9 and Section 5.3.10.
2019 actual
2020
2021
2022
2020-2022 plan total
| 2. Detailed inspection of vegetation around distribution electric lines and equipment | 2019 plan | N/A | N/A | Contact from object | N/A | N/A | Reduces escalation should an ignition event occur through removal of fuel | Existing | 2018 GRC & 2019 WMP | N/A | In Compliance with Regulation | GO95 | Program incorporated new requirements in 2019
|  | 2019 actual | 825 | 1984.5567
|  | 2020 | 825 | 1724.5964
|  | 2021 | 825 | 1724.5964
|  | 2022 | 825 | 1724.5964
|  | 2020-2022 plan total | 2475 | 1724.5964
| 3. Detailed inspection of vegetation around transmission electric lines and equipment | 2019 plan | N/A | N/A | Contact from object | N/A | N/A | Reduces escalation should an ignition event occur through removal of fuel | Existing | 2018 GRC & 2019 WMP | N/A | In Compliance with Regulation | GO95 | Program incorporated new requirements in 2019
|  | 2019 actual | 345 | 3338.71
|  | 2020 | 345 | 2098.2522
|  | 2021 | 345 | 2098.2522
|  | 2022 | 345 | 2098.2522
|  | 2020-2022 plan total | 1035 | 2098.2522
| 4. Emergency response vegetation management due to red flag warning or other urgent conditions | 2019 plan | As these vegetation management specific components are critical to the success of PacifiCorp’s emergency response programs and grid operations and protocols, the emergency response vegetation management due to red flag warning or other urgent conditions is a subset and component of both the company’s general emergency response plans and the company’s grid operations and protocols wildfire mitigation program focused on personnel work procedures and training conditions of elevation fire risk. Therefore, PacifiCorp does not at this time have a specific vegetation management and inspections wildfire mitigation program focused on Emergency response vegetation management due to red flag warning or other urgent conditions. See Section 5.3.6.3 and Section 5.3.9.
2019 actual
2020
2021
2022
2020-2022 plan total
| 5. Fuel management and reduction of "slash: from vegetation management activities | 2019 plan | While critical to the success of PacifiCorp’s overall vegetation management and inspections wildfire mitigation strategy, the Fuel management and reduction of “slash” from vegetation management activities is a component of the company’s vegetation management to achieve clearances around electric lines and equipment. See Section 5.3.5.20.
2019 actual
2020
2021
2022
2020-2022 plan total
| 6. Improvement of inspections | 2019 plan | N/A - Elements already captured in other relevant programs | N/A - Elements already captured in other relevant programs | Contact from object | N/A | N/A | Reduces escalation should an ignition event occur through removal of fuel | Existing | 2018 GRC & 2019 WMP | N/A | In Compliance with Regulation | GO95 | Program incorporated new requirements in 2019
2019 actual
2020
2021
2022
2020-2022 plan total
| 7. LiDAR inspections of vegetation around distribution electric lines and equipment | 2019 plan | PacifiCorp does not have a specific vegetation management and inspections wildfire mitigation program focused on LiDAR inspections of vegetation around distribution electric lines and equipment. Instead, PacifiCorp incorporates, as a component, LiDAR inspections of vegetation around distribution lines and equipment in its LiDAR inspections of distribution electric lines and equipment program. See Section 5.3.4.7.
2019 actual
2020
2021
2022
2020-2022 plan total
| 8. LiDAR inspections of transmission electric lines and equipment | 2019 plan | PacifiCorp does not have a specific vegetation management and inspections wildfire mitigation program focused on LiDAR inspections of vegetation around transmission electric lines and equipment. Instead, PacifiCorp incorporates, as a component, LiDAR inspections of vegetation around transmission lines and equipment in its LiDAR inspections of transmission electric lines and equipment program. See Section 5.3.4.8.
2019 actual
2020
2021
2022
2020-2022 plan total
| 9. Other discretionary inspection of vegetation around distribution electric lines and equipment, beyond inspections mandated by rules and regulations | 2019 plan | At this time, PacifiCorp does not have any other discretionary inspection of vegetation around transmission electric lines and equipment, beyond inspections mandated by rules and regulations, and other described programs.
2019 actual
2020
2021
2022
2020-2022 plan total
| 10. Other discretionary inspection of vegetation around transmission electric lines and equipment, beyond inspections mandated by rules and regulations | 2019 plan | At this time, PacifiCorp does not have any other discretionary inspection of vegetation around transmission electric lines and equipment, beyond inspections mandated by rules and regulations, and other described programs.
2019 actual
2020
2021
2022
2020-2022 plan total
| 11. Patrol inspections of vegetation around transmission electric lines and equipment | 2019 plan | PacifiCorp’s description of patrol inspections of vegetation around distribution electric lines and equipment is included in the company’s description of detailed inspections of vegetation around distribution lines and equipment. See Section 5.3.5.2
2019 actual
2020
2021
2022
2020-2022 plan total
| 12. Patrol inspections of vegetation around transmission electric lines and equipment | 2019 plan | PacifiCorp’s description of patrol inspections of vegetation around transmission electric lines and equipment is included in the company’s description of detailed inspections of vegetation around transmission lines and equipment. See Section 5.3.5.3
2019 actual
2020
2021
2022
2020-2022 plan total
| 13. Quality assurance/ quality control of inspections | 2019 plan | N/A - Elements already captured in other relevant programs | N/A - Elements already captured in other relevant programs | Contact from object | N/A | N/A | Reduces escalation should an ignition event occur through removal of fuel | Existing | N/A | N/A | N/A | N/A | General program and best practices applied to an accounted for in other relevant programs
2019 actual
2020
2021
2022
2020-2022 plan total
| 14. Recruiting and training of vegetation management personnel | 2019 plan | PacifiCorp’s general approach to recruiting and training of vegetation management personnel can be found in chapter 1 of the company’s Transmission and Distribution Vegetation Management Program Standard Operating Procedures manual. In general, PacifiCorp takes advantage of training that is provided by the company and arboriculture industry and issues materials as needed, such as a High Risk Tree Identification presentation created in 2019 to educate inspectors on proper identification of defective trees that have the potential to strike the facilities. PacifiCorp at this time does not have a vegetation management and inspections wildfire mitigation program focused on recruiting and training of vegetation management personnel.
2019 actual
2020
2021
2022
2020-2022 plan total
| 15. Remediation of at-risk species | 2019 plan | Remediation of at-risk species is a subset to the company’s vegetation management to achieve clearances around electric lines and equipment program as it contains, as an element, the company’s practices procedures, and funding to remediate at-risk species. See Section 5.3.5.18.
2019 actual
2020
2021
2022
2020-2022 plan total
| 16. Removal and remediation of trees with strike potential to electric lines and equipment | 2019 plan | Removal and remediation of trees with strike potential to electric lines and equipment is a subset to the company’s vegetation management to achieve clearances around electric lines and equipment program as it contains, as an element, the company’s practices procedures, and funding to remove and remediate trees with strike potential to electric lines and equipment. See Section 5.3.5.18.
2019 actual
2020
2021
2022
2020-2022 plan total
| 17. Substation vegetation inspections | 2019 plan | PacifiCorp’s vegetation detailed inspection and correction program included in Sections 5.3.5.2 and 5.3.5.3, discretionary inspection included in 5.3.5.9, and overall management activities to achieve proper clearances in Section 5.3.5.20, include work in and around substations. Therefore, PacifiCorp does not have a specific vegetation management and inspections program focused on substation inspection. See Sections 5.3.5.2, 5.3.5.3, 5.3.5.9, and 5.3.5.20.
2019 actual
2020
2021
2022
2020-2022 plan total
| 18. Substation vegetation management | 2019 plan | PacifiCorp’s vegetation detailed inspection and correction program included in Sections 5.3.5.2 and 5.3.5.3, discretionary inspection included in 5.3.5.9, and overall management activities to achieve proper clearances in Section 5.3.5.20, include work in and around substations. Therefore, PacifiCorp does not have a specific vegetation management and inspections program focused on substation inspection. See Sections 5.3.5.2, 5.3.5.3, 5.3.5.9, and 5.3.5.20.
2019 actual
2020
2021
2022
2020-2022 plan total
| 19. Vegetation inventory system | 2019 plan | PacifiCorp recognizes the importance and value of creating and maintaining a vegetation inventory system. Such a system can help to assess risk, customize vegetation management programs, and optimize task assignment and execution. PacifiCorp does not have a defined vegetation inventory system program at this time. However, the company is currently evaluating required steps, funding, and technology requirements to develop, implement, and incorporate a new tree density inventory system targeted initially within the HFTD to inform risk assessment and prioritization of efforts. PacifiCorp is prioritizing this task, intends to evaluate in 2019, and provide an update and further program details in the next annual update.
2019 actual
2020
2021
2022
2020-2022 plan total
| 20. Vegetation management to achieve clearances around electric lines and equipment | 2019 plan | N/A | N/A | Contact from object | N/A | N/A | Reduces escalation should an ignition event occur through removal of fuel | Existing | 2018 GRC & 2019 WMP | N/A | In Compliance with Regulation | GO95 | Program incorporated new requirements in 2019
|  | 2019 actual | 3195 | 1195.9004
|  | 2020 | 3195 | 1029.4138
|  | 2021 | 3195 | 1029.4138
|  | 2022 | 3195 | 1029.4138
|  | 2020-2022 plan total | 9585 | 1029.4138
| 16.Other/not listed - Radial Pole Clearing | 2019 plan | N/A | N/A | N/A | N/A | N/A | Reduces escalation should an ignition event occur through removal of fuel | Existing | 2018 GRC & 2019 WMP | N/A | In Compliance with Regulation | GO95 | Similar to substation inspections, units are reported on a per pole basis
|  | 2019 actual | 14132 | 125.2579
|  | 2020 | 15060 | 117.5394
|  | 2021 | 15060 | 117.5394
|  | 2022 | 15060 | 117.5394
|  | 2020-2022 plan total | 45180 | 117.5394

## Table 26
CA 2020 WMP
Section | 5.3.6 | Detailed WMP programs
Table | 26 | Grid Operations and protocols
| Initiative activity | year | Line miles to be treated | Spend/treated line mile | Ignition probability drivers targeted | Risk reduction | risk-spend efficiency | Other risk drivers addressed | Existing/new | Existing: What proceeding has reviewed program | If new: Memorandum account | In/exceeding compliance with regulations | Cite associated rule | Comments
| 1. Automatic recloser operations | 2019 plan | N/A | N/A | All - Regardless of the cause, this program reduces that potential that a fault scenario results in an ignition event | N/A | N/A | Reduces escalation should an ignition event occur through removal of subsequent fault event | New in 2019 | N/A | 2019 WMP Memorandum Account | Non-standard operating practice | N/A | Program is applicable to all HFTD OH lines
|  | 2019 actual | 1200 | 0
|  | 2020 | 1200 | 500
|  | 2021 | 1200 | 500
|  | 2022 | 1200 | 500
|  | 2020-2022 plan total | 3600 | 500
| 2. Crew-accompanying ignition prevention and suppression resources and services | 2019 plan | PacifiCorp does not currently deploy crew-accompanying ignition prevention and suppression resources and services as part of its routine operational practices. When an emergency occurs, PacifiCorp communicates and collaborates with local emergency response teams as described in Section 5.3.9, which can include crew-accompanying ignition prevention and suppression resources and services. Additionally, during elevated risk conditions or during fire season, PacifiCorp leverages specific work practices and protocols and makes available specific resources and tools for use by operations personnel as included in Section 5.3.6.6. However, PacifiCorp does not currently have a specific grid operations and protocols wildfire mitigation program focused on crew-accompanying ignition prevention and suppression resources and services. As part of the annual WMP review process the use of these services will be re-evaluated and considered for future incorporation.
2019 actual
2020
2021
2022
2020-2022 plan total
| 3. Personnel work procedures and training in conditions of elevated risk | 2019 plan | N/A | N/A | Equipment related ignition | N/A | N/A | Reduces escalation should an ignition event occur through removal of subsequent fault event | New in 2019 | N/A | 2019 WMP Memorandum Account | Non-standard operating practice | N/A | Program is applicable to all HFTD OH lines
|  | 2019 actual | 1200 | 0
|  | 2020 | 1200 | 916.6667
|  | 2021 | 1200 | 916.6667
|  | 2022 | 1200 | 916.6667
|  | 2020-2022 plan total | 3600 | 916.6667
| 4. Protocols for PSPS re-energization | 2019 plan | PacifiCorp considers re-energization after a PSPS event to be a subset of outage restoration / re-energization protocols included in Section 5.3.6.3. Therefore, PacifiCorp does not have a separate protocol for PSPS.
2019 actual
2020
2021
2022
2020-2022 plan total
| 5. PSPS events and mitigation of PSPS impacts | 2019 plan | At this time, PacifiCorp does not have an additional grid operations and protocols wildfire mitigation program not already included and discussed in Section 4.4 and Section 5.6.2.
2019 actual
2020
2021
2022
2020-2022 plan total
| 6. Stationed and on-call ignition prevention and suppression resources and services | 2019 plan | N/A | N/A | N/A | N/A | N/A | Reduces escalation should an ignition event occur | New in 2019 | N/A | 2019 WMP Memorandum Account | Non-standard operating practice | N/A | Program is applicable to all HFTD OH lines
|  | 2019 actual | 1200 | 250
|  | 2020 | 1200 | 250
|  | 2021 | 1200 | 250
|  | 2022 | 1200 | 250
|  | 2020-2022 plan total | 3600 | 250
| 7.Other/not listen [only is an initiative cannot feasibly be classified within those listen above] | 2019 plan | At this time, PacifiCorp does not have any additional grid operations and protocols wildfire mitigation programs.
2019 actual
2020
2021
2022
2020-2022 plan total

## Table 27
CA 2020 WMP
Section | 5.3.7 | Detailed WMP programs
Table | 27 | Data governance
| Initiative activity | year | Line miles to be treated | Spend/treated line mile | Ignition probability drivers targeted | Risk reduction | risk-spend efficiency | Other risk drivers addressed | Existing/new | Existing: What proceeding has reviewed program | If new: Memorandum account | In/exceeding compliance with regulations | Cite associated rule | Comments
| 1. Centralized repository for data | 2019 plan | PacifiCorp, at this time, does not have a specific data governance wildfire mitigation program focused on a centralized repository for data that maps to the tracking and level of details requested in this table. Additional details regarding PacifiCorp's plan and approach are included in Section 5.3.7.1.
2019 actual
2020
2021
2022
2020-2022 plan total
| 2. Collaborative research on utility ignition and/or wildfire | 2019 plan | PacifiCorp, at this time, does not have a specific data governance wildfire mitigation program focused on a collaborative research on utility ignition and/or wildfire that maps to the tracking and level of details requested in this table. Additional details regarding PacifiCorp's plan and approach are included in Section 5.3.7.2.
2019 actual
2020
2021
2022
2020-2022 plan total
| 3. Documentation and disclosure of wildfire-related data and algorithms | 2019 plan | PacifiCorp, at this time, does not have a specific data governance wildfire mitigation program focused on a documentation and disclosure of wildfire-related data and algorithms that maps to the tracking and level of details requested in this table. Additional details regarding PacifiCorp's plan and approach are included in Section 5.3.7.3.
2019 actual
2020
2021
2022
2020-2022 plan total
| 4. Tracking and analysis of near miss data | 2019 plan | PacifiCorp, at this time, does not have a specific data governance wildfire mitigation program focused on the tracking and analysis of near miss data that maps to the tracking and level of details requested in this table. Additional details regarding PacifiCorp's plan and approach are included in Section 5.3.7.4.
2019 actual
2020
2021
2022
2020-2022 plan total
| 5.Other/not listen [only is an initiative cannot feasibly be classified within those listen above] | 2019 plan | PacifiCorp does not have any other data governance other wildfire mitigation programs.
2019 actual
2020
2021
2022
2020-2022 plan total

## Table 28
CA 2020 WMP
Section | 5.3.8 | Detailed WMP programs
Table | 28 | Resource allocation methodology
| Initiative activity | year | Line miles to be treated | Spend/treated line mile | Ignition probability drivers targeted | Risk reduction | risk-spend efficiency | Other risk drivers addressed | Existing/new | Existing: What proceeding has reviewed program | If new: Memorandum account | In/exceeding compliance with regulations | Cite associated rule | Comments
| 1. Allocation methodology development and application | 2019 plan | N/A - While PacifiCorp remains fully committed to the continued development and improvement of the company’s risk based decision making framework, many of the elements requested in this 2020 CA WMP filing may not be applicable to PacifiCorp, specifically many of the components requested in this section. At the guidance of the Wildfire Safety Division of the California Public Utilities Commission, these elements are marked “does not apply” or “not applicable” throughout the company’s filing.
2019 actual
2020
2021
2022
2020-2022 plan total
| 2. Risk reduction scenario development and analysis | 2019 plan | N/A - While PacifiCorp remains fully committed to the continued development and improvement of the company’s risk based decision making framework, many of the elements requested in this 2020 CA WMP filing may not be applicable to PacifiCorp, specifically many of the components requested in this section. At the guidance of the Wildfire Safety Division of the California Public Utilities Commission, these elements are marked “does not apply” or “not applicable” throughout the company’s filing.
2019 actual
2020
2021
2022
2020-2022 plan total
| 3. Risk spend efficiency analysis | 2019 plan | N/A - While PacifiCorp remains fully committed to the continued development and improvement of the company’s risk based decision making framework, many of the elements requested in this 2020 CA WMP filing may not be applicable to PacifiCorp, specifically many of the components requested in this section. At the guidance of the Wildfire Safety Division of the California Public Utilities Commission, these elements are marked “does not apply” or “not applicable” throughout the company’s filing.
2019 actual
2020
2021
2022
2020-2022 plan total
| 4.Other/not listen [only is an initiative cannot feasibly be classified within those listen above] | 2019 plan | N/A - While PacifiCorp remains fully committed to the continued development and improvement of the company’s risk based decision making framework, many of the elements requested in this 2020 CA WMP filing may not be applicable to PacifiCorp, specifically many of the components requested in this section. At the guidance of the Wildfire Safety Division of the California Public Utilities Commission, these elements are marked “does not apply” or “not applicable” throughout the company’s filing.
2019 actual
2020
2021
2022
2020-2022 plan total

## Table 29
CA 2020 WMP
Section | 5.3.9 | Detailed WMP programs
Table | 29 | Emergency planning and preparedness
| Initiative activity | year | Line miles to be treated | Spend/treated line mile | Ignition probability drivers targeted | Risk reduction | risk-spend efficiency | Other risk drivers addressed | Existing/new | Existing: What proceeding has reviewed program | If new: Memorandum account | In/exceeding compliance with regulations | Cite associated rule | Comments | Internal Assignment
| 1. Adequate and trained workforce for service restoration | 2019 plan | N/A - System Wide | N/A - Not a specifically budgeted program | N/A - Response related | N/A | N/A | Reduces risk of escalation; Supports accelerated restoration to reduced impact of an event on communities | Existing with wildfire specific modifications | GRC | N/A | N/A | GO 166 | Program is an extension of existing emergency management programs | Jeff Bolton
2019 actual
2020
2021
2022
2020-2022 plan total
| 2. Community outreach, public awareness, and communication efforts | 2019 plan | N/A - System Wide | N/A - Not a specifically budgeted program | Contact from objects | N/A | N/A | Reduces risk of escalation; Supports accelerated restoration to reduced impact of an event on communities | Existing with wildfire specific modifications | GRC | N/A | N/A | GO 166 | Community outreach reduces the potential of third party contact and supports restoration | Melissa Nottingham
2019 actual
2020
2021
2022
2020-2022 plan total
| 3. Customer support in emergencies | 2019 plan | N/A - System Wide | N/A - Not a specifically budgeted program | N/A - Response related | N/A | N/A | Reduces risk of escalation; Supports accelerated restoration to reduced impact of an event on communities | Existing with wildfire specific modifications | GRC | N/A | N/A | R.18-12-005 | Program is an extension of existing emergency management programs | Melissa Nottingham
2019 actual
2020
2021
2022
2020-2022 plan total
| 4. Disaster and emergency preparedness plan | 2019 plan | N/A - System Wide | N/A - Not a specifically budgeted program | N/A - Response related | N/A | N/A | Reduces risk of escalation; Supports accelerated restoration to reduced impact of an event on communities | Existing with wildfire specific modifications | GRC | N/A | N/A | GO 166 | Program is an extension of existing emergency management programs | Jeff Bolton
2019 actual
2020
2021
2022
2020-2022 plan total
| 5. Preparedness and planning for service restoration | 2019 plan | N/A - System Wide | N/A - Not a specifically budgeted program | N/A - Response related | N/A | N/A | Reduces risk of escalation; Supports accelerated restoration to reduced impact of an event on communities | Existing with wildfire specific modifications | GRC | N/A | N/A | GO 166 | Program is an extension of existing emergency management programs | Jeff Bolton
2019 actual
2020
2021
2022
2020-2022 plan total
| 6. Protocols in place to learn from wildfire events | 2019 plan | PacifiCorp’s leverages existing systems and processes included in the company’s Emergency Response Plan to learn from wildfire events in the same manner PacifiCorp learns from any emergency event. Therefore, PacifiCorp does not have a specific program for incorporation of lessons learned that is not already covered in a previous program. | [11 empty] | Jeff Bolton
2019 actual
2020
2021
2022
2020-2022 plan total
| 7.Other/not listen [only is an initiative cannot feasibly be classified within those listen above] | 2019 plan | PacifiCorp does not, at this time, have any other emergency planning and preparedness wildfire mitigation programs | [11 empty] | Jeff Bolton
2019 actual
2020
2021
2022
2020-2022 plan total

## Table 30
CA 2020 WMP
Section | 5.3.10 | Detailed WMP programs
Table | 30 | Stakeholder cooperation and community engagement
| Initiative activity | year | Line miles to be treated | Spend/treated line mile | Ignition probability drivers targeted | Risk reduction | risk-spend efficiency | Other risk drivers addressed | Existing/new | Existing: What proceeding has reviewed program | If new: Memorandum account | In/exceeding compliance with regulations | Cite associated rule | Comments
| 1. Community engagement | 2019 plan | However, at this time, PacifiCorp does not have a specific stakeholder cooperation and community engagement wildfire mitigation program focused on community engagement. While PacifiCorp values community engagement as a wildfire risk mitigation strategy, the company has incorporated, as an element, stakeholder cooperation and community engagement as a component of its overall Emergency Response Programs as included in Section 5.3.9.2.
2019 actual
2020
2021
2022
2020-2022 plan total
| 2. Cooperation and best practice sharing with agencies outside of CA | 2019 plan | N/A - System Wide | N/A - Not a specifically budgeted program | All | N/A | N/A | Reduces risk of escalation through support of accelerated restoration | Existing | N/A | N/A | N/A | N/A | N/A
2019 actual
2020
2021
2022
2020-2022 plan total
| 3. Cooperation with suppression agencies | 2019 plan | In times of emergencies, PacifiCorp’s emergency management group interfaces and maintains relationships with federal and state emergency responders and mutual assistance groups, including fire suppression agencies. The emergency manager has contact information for state, county and tribal emergency managers, the state’s Emergency Operations Center Emergency Support Functions (ESF) personnel, and the Geographic Area Coordination Centers dispatch centers for fire-related emergency response. Therefore, as opposed to having a separate program, at this time, PacifiCorp views cooperation with suppression agencies as a component of the company’s emergency planning and preparedness programs outlined in Section 5.3.9.
2019 actual
2020
2021
2022
2020-2022 plan total
| 4. Forest service and fuel reduction cooperation and joint roadmap | 2019 plan | While collaboration such as this is critical to the overall reduction of wildfire risk in the state of CA, PacifiCorp, at this time, does not have a specific program dedicated to this effort. Instead, PacifiCorp views these efforts on an as-needed basis and incorporates additional efforts to manage community environments within other programs, such as those included in Section 5.3.9.2 and Section 5.3.10.1 and the company’s overall vegetation management and inspections programs described in Section 5.3.5.
2019 actual
2020
2021
2022
2020-2022 plan total
| 5.Other/not listen [only is an initiative cannot feasibly be classified within those listen above] | 2019 plan | At this time, PacifiCorp does not have any other stakeholder cooperation and community engagement programs.
2019 actual
2020
2021
2022
2020-2022 plan total

## Table 31
CA 2020 WMP
Section | 5.6.1 | Expected outcome of 3-yr plan - Planned utility infrastructure construction and upgrades
Table | 30 | Change in drivers of ignition probability taking into account planned initiatives, for each year of plan
| Incident type by ignition probability driver | Detailed risk driver | Are near missed tracked? | Number of incidents per year |  |  | Average percentage likelihood of ignition per incident |  |  | Number of ignitions per year
|  |  |  | 2020 | 2021 | 2022 | 2020 | 2021 | 2022 | 2020 | 2021 | 2022
| Contact from object | Animal contact | n | Number of incidents per year 2020: No discrete data available; General reducing trend anticipated specific to fire season within PacifiCorp's service territory within the HFTD
|  | Balloon contact | n
|  | Other | n
|  | Unknown | n
|  | Veg. contact | n
|  | Vehicle contact | n
| Contamination |  | n | Number of incidents per year 2020: No discrete data available; General reducing trend anticipated specific to fire season within PacifiCorp's service territory within the HFTD
| All types of equipment/ facility failure | All types | n | Number of incidents per year 2020: No discrete data available; General reducing trend anticipated specific to fire season within PacifiCorp's service territory within the HFTD
|  | Conductor | n
|  | Crossarm | n
|  | Fuse | n
|  | Insulator | n
|  | Lightning arrestor | n
|  | Other | n
|  | Pole | n
|  | Sectionalizer | n
|  | Splice/clamp/connector | n
|  | Switch | n
|  | Transformer | n
|  | Voltage regulator | n
| Normal Operations |  | n | Number of incidents per year 2020: No discrete data available; General reducing trend anticipated specific to fire season within PacifiCorp's service territory within the HFTD
| Other |  | n | Number of incidents per year 2020: No discrete data available; General reducing trend anticipated specific to fire season within PacifiCorp's service territory within the HFTD
| Unknown |  | n | Number of incidents per year 2020: No discrete data available; General reducing trend anticipated specific to fire season within PacifiCorp's service territory within the HFTD
| Vandalism/Theft |  | n | Number of incidents per year 2020: No discrete data available; General reducing trend anticipated specific to fire season within PacifiCorp's service territory within the HFTD
| Wire-to-wire contact |  | n | Number of incidents per year 2020: No discrete data available; General reducing trend anticipated specific to fire season within PacifiCorp's service territory within the HFTD
| Contact from 3rd party |  | n | Number of incidents per year 2020: No discrete data available; General reducing trend anticipated specific to fire season within PacifiCorp's service territory within the HFTD