## Initiative Template
UtilityID | InitiativeID | InitiativeName | InitiativeSpend | InitiativeRSE | InitiativeStatus | InitiativeCategory | InitiativeStartYear | InitiativeStartDate | InitiativePredictedDurationDays | InitiativeActualDurationDays | InitiativeDurationPredictionError | SubinitiativeID | SubinitiativeName | SubinitiativeSpend | SubinitiativeStatus | SubinitiativeSubcategoryID1 | SubinitiativeSubcategoryID2 | SubinitiativeLocationID | UniqueID | SubinitiativeLocationName | SubinitiativeLocationType | SubinitiativeLocationHFTDClass | SubinitiativeLocationLatitude | SubinitiativeLocationLongitude | FeatureClass
PG&E | 123 | Infrastructure Hardening - Sacramento | 100000.00 | 0.05 | Complete | Grid Hardening | 2020 | 2020-10-02 | 30 | 60 | -30 | 1 | Install conductor covers | 40000.00 | Complete | 15 | 16,22 | 1 | PG&E_123_1_1 | Sacramento | Municipality | Outside | 38.5804 | -121.4818 | Point
PG&E | 123 | Infrastructure Hardening - Sacramento | 100000.00 | 0.05 | Complete | Grid Hardening | 2020 | 2020-10-02 | 30 | 60 | -30 | 1 | Install conductor covers | 40000.00 | In progress | 15 | 16,22 | 2 | PG&E_123_1_2 | Davis | Municipality | Outside | 38.548190 | -121.741015 | Point
PG&E | 123 | Infrastructure Hardening - Sacramento | 100000.00 | 0.05 | Complete | Grid Hardening | 2020 | 2020-10-02 | 30 | 60 | -30 | 2 | Pole replacement | 20000.00 | Complete | 18 | N/A | 1 | PG&E_123_2_1 | Rancho Cordova | Municipality | Outside | 38.586436 | -121.300525 | Point
PG&E | 234 | Tree Trimming - San Francisco | 50000.00 | 0.1 | Not started | Veg management | 2021 | 2021-01-01 | 14 | N/A | N/A | 1 | Trim around Golden Gate Park | 25000.00 | Not started | 62 | 64,55 | 1 | PG&E_234_1_1 | Golden Gate Park | Park | Outside | 37.7695 | -122.486 | Point
PG&E | 234 | Tree Trimming - San Francisco | 50000.00 | 0.1 | Not started | Veg management | 2021 | 2021-01-01 | 14 | N/A | N/A | 2 | Trim around Lands End | 25000.00 | Not started | 64 | 62,55 | 2 | PG&E_234_1_2 | Lands End Lookout | Park | Outside | 37.7798 | -122.5119 | Point

## Initiative Data Dictionary
Planning Level | Category | Field Name Shapefile | Field Name Long Form | Field Description | Field Type | Priority
Initiative | Unique Identifier | UtilityID | UtilityID | A standardized identification name of the utility - ["PG&E", "SDG&E", "SCE"] | String | Highest
Initiative | Unique Identifier | InitID | InitiativeID | UniqueID of initiative | String | Highest
Initiative | Unique Identifier | InitName | InitiativeName | Unique Name of Initiative | String | Highest
Initiative | Context | InitSpend | InitiativeSpend | Spend amount dedicated as a part of the initiative, in dollars | Float/Decimal | Highest
Initiative | Context | InitiRSE | InitiativeRSE | Modeled risk-spend-efficiency for project (% projected reduction in ignitions for every 1000's spent) | Float/Decimal | High
Initiative | Context | InitStatus | InitiativeStatus | The current state of the initiative - ["Not started", "In progress", "Complete", "Cancelled"] - "Complete" should only be selected if all Implementation subinitiative components are complete | String | Highest
Initiative | Context | InitCateg | InitiativeCategory | Overarching category of the initiative. Can be a mix of two different categories. (if so, list in 'comma separated' format) "Veg management" - related to vegetation clearance or other management "Grid hardening" - any asset activities related to strengthing grid, such as capital improvement projects "Asset management" - maintanence and other asset-related work "Risk-mapping and situational awareness" - spending towards risk modelling and weather stations | String | Highest
Initiative | Date and Duration | IStartYr | InitiativeStartYear | The actual or planned start year of the initiative's implementation | Integer | Highest
Initiative | Date and Duration | IStartDate | InitiativeStartDate | The actual or planned start date of the initiative's implementation, in isodate format: "YYYY-MM-DD" - https://en.wikipedia.org/wiki/ISO_8601#Calendar_dates | String | Highest
Initiative | Date and Duration | IPrdDrDays | InitiativePredictedDurationDays | number of days the initiative is planned to last | Integer | High
Initiative | Date and Duration | IActDrDays | InitiativeActualDurationDays | number of days the initiative actually lasted (only fill if complete) | Integer | High
Initiative | Date and Duration | IDrPredErr | InitiativeDurationPredictionError | "InitiativePredictedDurationDays" minus "InitiativeActualDurationDays" - positive values indicate shorter than expected implementation, negative values indicate longer than expected implementation (only fill if complete) | Integer | High
Implemented Subinitiative | Unique Identifier | SiID | SubinitiativeID | A unique ID associated with the initiative's component subinitiative | String | Highest
Implemented Subinitiative | Unique Identifier | SiName | SubinitiativeName | A unique name associated with the initiative's component subinitiative | String | Highest
Implemented Subinitiative | Context | SiDesc | SubinitiativeDescription | Description of work performed at the subinitiative site | String | Highest
Implemented Subinitiative | Context | SiSpend | SubinitiativeSpend | Specific spend (in dollars) attached to subinitiative record, all subinitiaive records for an initiative should total to InitiativeSpend. If unknown, evenly distribute InitiativeSpend across component subinitiatives | Float/Decimal | Highest
Implemented Subinitiative | Context | SiStatus | SubinitiativeStatus | The current state of the subinitiative - ["Not started", "In progress", "Complete", "Cancelled"] | String | Highest
Implemented Subinitiative | Context | SiSubctID1 | SubinitiativeSubcategoryID1 | The primary purpose of the subinitiative. Select ONE subcategory ID in the included "Subcategory Lookup" tab to represent the subinitiative theme | String | Highest
Implemented Subinitiative | Context | SiSubctID2 | SubinitiativeSubcategoryID2 | All other subcategory IDs that might apply, in comma delimited format - (for example: "1,2,3,4") | String | Highest
Implemented Subinitiative | Location | SiLocID | SubinitiativeLocationID | A unique ID associated with the subinitiative site location - If an asset, then should correspond to that specific asset's ID | String | Highest
Implemented Subinitiative | Location | UniqueID | UniqueID | An underscore delimited, concatenation of "UtilityID"+"_"+"InitiativeID"+"_"+"SubinitiativeID"+"_"+"SubinitiativeLocationID" - should be unique to this dataset | String | Highest
Implemented Subinitiative | Location | SiLocName | SubinitiativeLocationName | The name of the subinitiative site location - as detailed as possible (examples are - municipality name, asset ID, circuitt ID, county name) | String | Highest
Implemented Subinitiative | Location | SiLocDesc | SubinitiativeLocationDescription | A description of the subinitiative site location - as detailed as possible | String | Highest
Implemented Subinitiative | Location | SiLocType | SubinitiativeLocationType | What does the provided lat/lon coordinates provided refer to? Exact location, city, county, etc.? Pick one - ["Asset site coordinates", "Distribution/Transmission asset Centroid", "Census Tract Centroid", "Zip Code Centroid, Municipality/City Centroid", "County Centroid"] | String | Highest
Implemented Subinitiative | Location | SiLocHFTD | SubinitiativeLocationHFTDClass | The highest threat category intersecting with the location of the subinitiative - ["Zone 1", "Tier 2", "Tier 3", "Outside"] | String | Highest
Implemented Subinitiative | Location | SiLocLat | SubinitiativeLocationLatitude | Latitude Coordinate of Subinitiative Site - in decimal degrees | Float/Decimal | Highest
Implemented Subinitiative | Location | SiLocLon | SubinitiativeLocationLongitude | Longitude Coordinate of Subinitiative Site - in decimal degrees | Float/Decimal | Highest
Implemented Subinitiative | Spatial Mapping | FeatureClass | FeatureClass | Point FeatureClass representing the coordinate pair of SubinitiativeLocationLatitude and SubinitiativeLocationLongitude | Point | Highest

## Subcategory Lookup
Subcategory ID | Subcategory Description
1 | A summarized risk map showing the overall ignition probability and estimated wildfire consequence along electric lines and equipment
2 | Climate-driven risk map and modelling based on various relevant weather scenarios
3 | Ignition probability mapping showing the probability of ignition along the electric lines and equipment
4 | Initiative mapping and estimation of wildfire and PSPS risk-reduction impact
5 | Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment
6 | Weather-driven risk map and modelling based on various relevant weather scenarios
7 | Advanced weather monitoring and weather stations
8 | Continuous monitoring sensors
9 | Fault indicators for detecting faults on electric lines and equipment
10 | Forecast of a fire risk index, fire potential index, or similar
11 | Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions
12 | Weather forecasting and estimating impacts on electric lines and equipment
13 | Capacitor maintenance and replacement program
14 | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
15 | Covered conductor installation
16 | Covered conductor maintenance
17 | Crossarm maintenance, repair, and replacement
18 | Distribution pole replacement and reinforcement, including with composite poles
19 | Expulsion fuse replacement
20 | Grid topology improvements to mitigate or reduce PSPS events
21 | Installation of system automation equipment
22 | Maintenance, repair, and replacement of connectors, including hotline clamps
23 | Mitigation of impact on customers and other residents affected during PSPS event
24 | Other corrective action
25 | Pole loading infrastructure hardening and replacement program based on pole loading assessment program
26 | Transformers maintenance and replacement
27 | Transmission tower maintenance and replacement
28 | Undergrounding of electric lines and/or equipment
29 | Updates to grid topology to minimize risk of ignition in HFTDs
30 | Detailed inspections of distribution electric lines and equipment
31 | Detailed inspections of transmission electric lines and equipment
32 | Improvement of inspections
33 | Infrared inspections of distribution electric lines and equipment
34 | Infrared inspections of transmission electric lines and equipment
35 | Intrusive pole inspections
36 | LiDAR inspections of distribution electric lines and equipment
37 | LiDAR inspections of transmission electric lines and equipment
38 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
39 | Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations
40 | Patrol inspections of distribution electric lines and equipment
41 | Patrol inspections of transmission electric lines and equipment
42 | Pole loading assessment program to determine safety factor
43 | Quality assurance / quality control of inspections
44 | Substation inspections
45 | Additional efforts to manage community and environmental impacts
46 | Detailed inspections of vegetation around distribution electric lines and equipment
47 | Detailed inspections of vegetation around transmission electric lines and equipment
48 | Emergency response vegetation management due to red flag warning or other urgent conditions
49 | Fuel management and reduction of “slash” from vegetation management activities
50 | Improvement of inspections
51 | LiDAR inspections of vegetation around distribution electric lines and equipment
52 | LiDAR inspections of vegetation around transmission electric lines and equipment
53 | Other discretionary inspection of vegetation around distribution electric lines and equipment, beyond inspections mandated by rules and regulations
54 | Other discretionary inspection of vegetation around transmission electric lines and equipment, beyond inspections mandated by rules and regulations
55 | Patrol inspections of vegetation around distribution electric lines and equipment
56 | Patrol inspections of vegetation around transmission electric lines and equipment
57 | Quality assurance / quality control of inspections
58 | Recruiting and training of vegetation management personnel
59 | Remediation of at-risk species
60 | Removal and remediation of trees with strike potential to electric lines and equipment
61 | Substation inspections
62 | Substation vegetation management
63 | Vegetation inventory system
64 | Vegetation management to achieve clearances around electric lines and equipment
65 | Automatic recloser operations
66 | Crew-accompanying ignition prevention and suppression resources and services
67 | Personnel work procedures and training in conditions of elevated fire risk
68 | Protocols for PSPS re-energization
69 | PSPS events and mitigation of PSPS impacts
70 | Stationed and on-call ignition prevention and suppression resources and services
71 | Centralized repository for data
72 | Collaborative research on utility ignition and/or wildfire
73 | Documentation and disclosure of wildfire-related data and algorithms
74 | Tracking and analysis of near miss data
75 | Allocation methodology development and application
76 | Risk reduction scenario development and analysis
77 | Risk spend efficiency analysis
78 | Adequate and trained workforce for service restoration
79 | Community outreach, public awareness, and communications efforts
80 | Customer support in emergencies
81 | Disaster and emergency preparedness plan
82 | Preparedness and planning for service restoration
83 | Protocols in place to learn from wildfire events
84 | Community engagement
85 | Cooperation and best practice sharing with agencies outside CA
86 | Cooperation with suppression agencies
87 | Forest service and fuel reduction cooperation and joint roadmap
88 | Other / not listed [only if an initiative cannot feasibly be classified within those listed above]