## DOR EPC
Activity Description | Conceptual Engineering | Detailed Design | Equipment Procurement | Construction | Comments
SITE ACQUISITION
ENGINEERING AND DESIGN SERVICES
Plot Plan & Arrangement Drawings
Resource (Wind or Solar) Optimization
One-Line Drawings
Drawing Schedule
Commissioning, Start-up & Operating Manuals
Maintenance Manual
Spare Parts Manual
Design Criteria | P
Construction Support Services, Resident Eng.
Functional Specification of Major Equipment
Lightning Study
Arc-Flash Study
Corrosion Protection Concept
Fire Protection Concept
Design Plant
Calculations Plant/Drawings Plant/PE Stamp
As-Built Drawings
Purchasing Support/Equipment and Material Specification
Review and Approval of Vendor Drwgs.
Procurement Schedule
Design Reviews | __ / P | __ / P | __ / P | __ / P
PERMITTING & DEVELOPMENT RELATED
Federal Permits, Licenses and approvals |  |  |  |  | Review by PacifiCorp
State Permits, Licenses and approvals |  |  |  |  | Review by PacifiCorp
Environmental Assessment |  |  |  |  | Review by PacifiCorp
Zoning Board Approvals |  |  |  |  | Review by PacifiCorp
Building & Construction Permits |  |  |  |  | Review by PacifiCorp
Coordination of the Local Building Inspector's Inspections |  |  |  |  | Review by PacifiCorp
Transmission Interconnection Request & Studies |  |  |  |  | Review by PacifiCorp
Permanent Plant Phone System
Telephone and data service to site
SITE WORK
Site survey/access right of way & easements
Geotechnical Study and recommendations
Clearing and Grubbing
Earthwork
Grading and Drainage
Sedimentation and Erosion Control Plans
Roads/Paving/Surfacing/all required surfaces
Fencing/Gates
Final Landscaping
CIVIL WORK
Building Foundations
Operations and Maintenance Building
Parking Lots
Trenches, Duct Banks & Manholes
Piers, footings and pads
EQUIPMENT PROCUREMENT AND SUPPLY
Solar panels
Racking
Inverters
Junction Boxes (includes mounting pads, connectors, boots, etc.)
Collector Cables
Cable, Conduit, Bus, Tray & Grounding
Intermediate Transformers
Main Step-up Transformer(s)
Auxiliary Transformer(s)
Switchyard
Emergency Generators (if required)
Transmission line from Transmission Provider's substation to Point Of Interconnection | T | T | T | T
Transmission line from Point Of Interconnection to switchyard / stepup transformer
Low Voltage Switchgear
Station Grounding system
Outdoor Lighting
UPS System
DC Station Battery
Station Battery Charger
Cathodic Protection
Ground Fault Protection System
Revenue Metering |  |  |  |  | Contractor to coordinate with Transmission Provider. In accordance with Interconnection Agreement.
BOP System Protection - Relays
Interconnection Protection - Relays | T | __ / T | __ / T |  | Contractor to coordinate with Transmission Provider. In accordance with Interconnection Agreement.
Grid Interconnection | __ / T | __ / T | __ / T | __ / T | Contractor to coordinate with Transmission Provider. In accordance with Interconnection Agreement.
CONTROL/DATA ACQUISITION
Data Acquisition and SCADA
Solar Farm Control (if applicable)
BOP Data Acquisition
Historian Interface and Hardware for OSI-PI
PROJECT SERVICES
Project Management
Project Master Schedule
Drawing Schedules
Equipment Delivery Schedules
Construction Schedules
Overall Project Status Reports
Factory Tests Reports
Performance Test Procedure And Final Report
Transportation Risk Insurance
Operating and Maintenance Personnel Training Program
Quality Assurance/Quality Control
MISC
Security system infrastructure
Security hardware and software
PAINTING, COLOR CODING AND IDENTIFICATION
Prime Coating of Equipment
Prime Coating of BOP
Final Painting
SPARE PARTS
Commissioning Spares
Operational Spares and Special Tools
TEMPORARY FACILITIES
Construction Facilities for Labor such as Toilets, Shelters, Change Rooms, etc.
Laydown Area, (establish, Control & restore)
Site Construction Office
First Aid Station, Safety and health facilities
Site Security
Fire Prevention and Fighting
Temporary Water supply and distribution
Temporary Electrical supply and distribution
Temporary Site Telephone/Communications facilities
Temporary sewage collection
Dirt and mud control
Housekeeping for On-Site Facilities
Clean-up and Removal of Temporary Facilities
Training Facilities (on site or off site)
Site warehouse and storage
LOGISTICS
Transportation of Equipment to Construction Site
Receive and unload equipment and materials
Local Registration Fee, Licenses, etc.
Rights of Ways/Clearance for special shipments
Equipment Unloading and Handling
Equipment and Materials Receiving, Inspection, Inventorizing, Shipment Damage Claim Processing
Comprehensive General Liability Insurance (Vehicles)
Automobile Insurance
Insurance of Temporary Facilities, Tools, Construction Equipment, Etc.
Builder's All Risk (BAR) Insurance Coverage
Construction equipment, tools, instruments and aids
Technical Advisors (TAs)
Supervision and Labor Reports
START-UP AND COMMISSIONING:
Lead Organization
Start-up & Initial operations mgt. & scheduling
Start-up Advisor
Consumables
Craft Labor
Reports
Standard Test Instruments, Tools & Equipment
Special Test Instruments, Tools & Equipment
Documentation, Test and Data Records
Equipment, Component, System Walk-throughs & Turnovers | __ / P | __ / P | __ / P | __ / P | PacifiCorp to participate in walk-throughs and may review turnover documents
Permanent Plant Backfeed for Station Service | T | T | T | T
PLANT PERFORMANCE TESTS: |  |  |  |  | Independent engineer by PacifiCorp may witness testing
Lead Organization
Consumables
Data Reporters
Test Advisors
Craft Labor and Supervision Support
TA Services
Final Report
Guarantee Responsibility