## EPC
Activity Description | Conceptual Engineering | Detailed Design | Equipment Procurement | Construction | Comments
SITE ACQUISITION
ENGINEERING AND DESIGN SERVICES
Plot Plan & Arrangement Drawings
Resource (Wind, Solar, or Energy Storage) Optimization
One-Line Drawings
Drawing Schedule
Commissioning, Start-up & Operating Manuals
Maintenance Manual
Spare Parts Manual
Design Criteria | P
Construction Support Services, Resident Eng.
Functional Specification of Major Equipment
Lightning Study
Arc-Flash Study
Corrosion Protection Concept
Fire Protection Concept
Design Plant
Calculations Plant/Drawings Plant/PE Stamp
As-Built Drawings
Purchasing Support/Equipment and Material Specification
Review and Approval of Vendor Drwgs.
Procurement Schedule
Design Reviews | __ / P | __ / P | __ / P | __ / P
PERMITTING & DEVELOPMENT RELATED
Federal Permits, Licenses and approvals |  |  |  |  | Review by PacifiCorp
State Permits, Licenses and approvals |  |  |  |  | Review by PacifiCorp
Environmental Assessment |  |  |  |  | Review by PacifiCorp
Zoning Board Approvals |  |  |  |  | Review by PacifiCorp
Building & Construction Permits |  |  |  |  | Review by PacifiCorp
Coordination of the Local Building Inspector's Inspections |  |  |  |  | Review by PacifiCorp
Transmission Interconnection Request & Studies |  |  |  |  | Review by PacifiCorp
Permanent Plant Phone System
Telephone and data service to site
SITE WORK
Site survey/access right of way & easements
Geotechnical Study and recommendations
Clearing and Grubbing
Earthwork
Grading and Drainage
Sedimentation and Erosion Control Plans
Roads/Paving/Surfacing/all required surfaces
Fencing/Gates
Final Landscaping
CIVIL WORK
Building Foundations
Operations and Maintenance Building
Parking Lots
Trenches, Duct Banks & Manholes
Piers, footings and pads
Wind Turbine Foundations |  |  |  |  | Wind resources
SOLAR RACK MOUNTS/TRACKING
Steel Support Posts |  |  |  |  | Solar resources
Racking |  |  |  |  | Solar resources
Wiring and associated controls for racking (as required) |  |  |  |  | Solar resources
EQUIPMENT PROCUREMENT AND SUPPLY
Solar Modules |  |  |  |  | Solar resources
DC Wiring |  |  |  |  | Solar & Energy Storage resources
Combiner Boxes (includes DC fuses, ground lugs, lightning arresters, etc.) |  |  |  |  | Solar & Energy Storage resources
DC Disconnect Switches |  |  |  |  | Solar & Energy Storage resources
Master Fuse Boxes for collection of Main DC Source Circuits to enter inverters |  |  |  |  | Solar & Energy Storage resources
Inverters |  |  |  |  | Solar & Energy Storage resources
AC Wiring |  |  |  |  | Solar & Energy Storage resources
Tracker interconnection (if required) |  |  |  |  | Solar resources
Wind Turbines (including gearboxes, generators, switchgear, controls, raceways, safety equipment, etc.) |  |  |  |  | Wind resources
Wind Turbine Grounding |  |  |  |  | Wind resources
FAA Lighting |  |  |  |  | Wind resources
Turbine communications |  |  |  |  | Wind resources
Junction Boxes (includes mounting pads, connectors, boots, etc.) |  |  |  |  | Wind resources
Collector Cables |  |  |  |  | Wind resources
Cable, Conduit, Bus, Tray & Grounding
Intermediate Transformers
Main Step-up Transformer(s)
Auxiliary Transformer(s)
Switchyard
Emergency Generators (if required)
Transmission line from Transmission Provider's substation to Point Of Interconnection | T | T | T | T
Transmission line from Point Of Interconnection to switchyard / stepup transformer
Low Voltage Switchgear
Station Grounding system
Outdoor Lighting
UPS System
DC Station Battery
Station Battery Charger
Cathodic Protection
Ground Fault Protection System
Revenue Metering |  |  |  |  | Contractor to coordinate with Transmission Provider. In accodance with Interconnection Agreement.
BOP System Protection - Relays
Interconnection Protection - Relays | T | __ / T | __ / T |  | Contractor to coordinate with Transmission Provider. In accodance with Interconnection Agreement.
Grid Interconnection | __ / T | __ / T | __ / T | __ / T | Contractor to coordinate with Transmission Provider. In accodance with Interconnection Agreement.
CONTROL/DATA ACQUISITION
Data Acquisition and SCADA
Wind Farm Control |  |  |  |  | Wind resources
Energy Storage System Control |  |  |  |  | Energy Storage resources
Battery Management Sytem |  |  |  |  | Energy Storage resources
BOP Data Acquisition
Historian Interface and Hardware for OSI-PI
PROJECT SERVICES
Project Management
Project Master Schedule
Drawing Schedules
Equipment Delivery Schedules
Construction Schedules
Overall Project Status Reports
Factory Tests Reports
Performance Test Procedure And Final Report
Transportation Risk Insurance
Operating and Maintenance Personnel Training Program
Quality Assurance/Quality Control
MISC
Security system infrastructure
Security hardware and software
PAINTING, COLOR CODING AND IDENTIFICATION
Prime Coating of Equipment
Prime Coating of BOP
Final Painting
SPARE PARTS
Commissioning Spares
Operational Spares and Special Tools
TEMPORARY FACILITIES
Construction Facilities for Labor such as Toilets, Shelters, Change Rooms, etc.
Laydown Area, (establish, Control & restore)
Site Construction Office
First Aid Station, Safety and health facilities
Site Security
Fire Prevention and Fighting
Temporary Water supply and distribution
Temporary Electrical supply and distribution
Temporary Site Telephone/Communications facilities
Temporary sewage collection
Dirt, dust and mud control
Housekeeping for On-Site Facilities
Clean-up and Removal of Temporary Facilities
Training Facilities (on site or off site)
Site warehouse and storage
LOGISTICS
Transportation of Equipment to Construction Site
Receive and unload equipment and materials
Local Registration Fee, Licenses, etc.
Rights of Ways/Clearance for special shipments
Equipment Unloading and Handling
Equipment and Materials Receiving, Inspection, Inventorizing, Shipment Damage Claim Processing
Comprehensive General Liability Insurance (Vehicles)
Automobile Insurance
Insurance of Temporary Facilities, Tools, Construction Equipment, Etc.
Builder's All Risk (BAR) Insurance Coverage
Construction equipment, tools, instruments and aids
Construction and Erection Tests
Technical Advisors (TAs)
Supervision and Labor Reports
START-UP AND COMMISSIONING:
Lead Organization
Start-up & Initial operations mgt. & scheduling
Start-up Advisor
Consumables
Craft Labor
Reports
Standard Test Instruments, Tools & Equipment
Special Test Instruments, Tools & Equipment
Documentation, Test and Data Records
Equipment, Component, System Walk-throughs & Turnovers | __ / P | __ / P | __ / P | __ / P | PacifiCorp to participate in walk-throughs and may review turnover documents
Permanent Plant Backfeed for Station Service | T | T | T | T
Operator training
PLANT PERFORMANCE TESTS: |  |  |  |  | Independent engineer by PacifiCorp may witness testing
Lead Organization
Consumables
Data Reporters
Test Advisors
Craft Labor and Supervision Support
TA Services
Final Report
Guarantee Responsibility
Legend
PacifiCorp | P
Transmission Provider | T

## SCADA (Solar)
SCADA Responsibility Matrix - Solar
| Device/Cable/Task | Design | Purchase & Assemble | Install Onsite | Program & Configure | Verification | QA Certify & Commission | Document
O&M SCADA ROOM | UPS (2 hour back up, additional by Owner if needed) | SCADA Supplier | SCADA Supplier | EPC | SCADA Supplier | SCADA Supplier | SCADA Supplier | SCADA Supplier
| SCADA Cabinet | SCADA Supplier | SCADA Supplier | EPC | SCADA Supplier | SCADA Supplier | SCADA Supplier | SCADA Supplier
| Owner Network Switch | Owner | Owner | Owner | Owner | Owner | Owner | Owner
| Phone network equipment | O&M Subcontractor | O&M Subcontractor | O&M Subcontractor | O&M Subcontractor | O&M Subcontractor | O&M Subcontractor | O&M Subcontractor
| EPC switches, routers, media converters | SCADA Supplier | SCADA Supplier | EPC | SCADA Supplier | SCADA Supplier | SCADA Supplier | SCADA Supplier
| Owner T1 | Owner | Owner | Owner | Owner | Owner | Owner | Owner
| Site Network Design | EPC | NA | NA | NA | EPC | EPC | EPC
| Auxillary Power | O&M Subcontractor | O&M Subcontractor | O&M Subcontractor | O&M Subcontractor | O&M Subcontractor | O&M Subcontractor | O&M Subcontractor
| Remote Access for EPC, ERCOT, Suppliers | EPC | EPC | NA | EPC | EPC | EPC | EPC
| Remote Access for Owner | Owner | Owner | NA | Owner | Owner | Owner | Owner
| External Internet/phone operations for EPC | EPC | EPC | EPC | EPC | EPC | EPC | EPC
| Ethernet cable | O&M Subcontractor | O&M Subcontractor | O&M Subcontractor | NA | O&M Subcontractor | O&M Subcontractor | O&M Subcontractor
| Fiber Link to Substation | EPC | EPC | EPC | NA | EPC | EPC | EPC
| Ethernet and phone jacks within O&M building | O&M Subcontractor | O&M Subcontractor | O&M Subcontractor | NA | O&M Subcontractor | O&M Subcontractor | O&M Subcontractor
| EPC Firewall | SCADA Supplier | SCADA Supplier | EPC | SCADA Supplier | SCADA Supplier | SCADA Supplier | SCADA Supplier
| Owner Firewall | Owner | Owner | Owner | Owner | Owner | Owner | Owner
| Historian Server with OPC, second NIC for Southern, EPC to program Southern IP, EPC to provide username/password for Southern use | SCADA Provider/Owner | SCADA Supplier | EPC | SCADA Supplier | SCADA Provider/Owner | SCADA Provider/Owner | SCADA Supplier
| EPC T1 | EPC | EPC | EPC | EPC | EPC | EPC | EPC
| AspenTech CIMIO software for Historian Server | Owner | SCADA Supplier | Owner | Owner | Owner | Owner | Owner
MET Stations | Media Converters/Switches | EPC | EPC | EPC | EPC | EPC | EPC | EPC
| Connectivity/Fiber links | EPC | EPC | EPC | NA | EPC | EPC | EPC
| Power | EPC | EPC | EPC | NA | EPC | EPC | EPC
| Instrumentation and Data Logger | EPC | EPC | EPC | EPC | EPC | EPC | EPC
| Structure | EPC | EPC | EPC | NA | EPC | EPC | EPC
| Foundation | EPC | EPC | EPC | NA | EPC | EPC | EPC
| Fiber Patch Panel | EPC | EPC | EPC | NA | EPC | EPC | EPC
Substation | Communication Switches/ Media Converters | SCADA Supplier | SCADA Supplier | EPC | SCADA Supplier | SCADA Supplier | SCADA Supplier | SCADA Supplier
| Fiber Optic Patch Panel | SCADA Supplier | SCADA Supplier | EPC | SCADA Supplier | SCADA Supplier | SCADA Supplier | SCADA Supplier
| UPS | SCADA Supplier | SCADA Supplier | EPC | SCADA Supplier | SCADA Supplier | SCADA Supplier | SCADA Supplier
| ERCOT Testing/Testing with Utility | NA | NA | NA | NA | SCADA Supplier | SCADA Supplier | SCADA Supplier
| Auxillary Power | EPC | EPC | EPC | EPC | EPC | EPC | EPC
| RTU | EPC | EPC | EPC | EPC | EPC | EPC | EPC
| HMI and HMI Server | SCADA Supplier | SCADA Supplier | EPC | SCADA Supplier | SCADA Supplier | SCADA Supplier | SCADA Supplier
| Power to devices | EPC | EPC | EPC | EPC | EPC | EPC | EPC
| Fiber/Conduit - Inverters to SS and OTDR testing | EPC | EPC | EPC | NA | EPC | EPC | EPC
| Fiber / Conduit- T-Line to SS and OTDR testing | EPC | EPC | EPC | NA | EPC | EPC | EPC
| Meter | EPC | EPC | EPC | EPC | EPC | EPC | EPC
| Relays | EPC | EPC | EPC | EPC | EPC | EPC | EPC
| GPS Clock | EPC | EPC | EPC | EPC | EPC | EPC | EPC
| Phone network equipment | EPC | EPC | EPC | EPC | EPC | EPC | EPC
| Physical Security | EPC | EPC | EPC | EPC | EPC | EPC | EPC
| Power Plant Controller | SCADA Supplier | SCADA Supplier | EPC | SCADA Supplier | SCADA Supplier | SCADA Supplier | SCADA Supplier
| SCADA Cabinet Rack | SCADA Supplier | SCADA Supplier | EPC | SCADA Supplier | SCADA Supplier | SCADA Supplier | SCADA Supplier
Collection/ Inverters | Inverter Patch Panels | EPC | EPC | EPC | NA | EPC | EPC | EPC
| Collection Splicing | EPC | EPC | EPC | NA | EPC | EPC | EPC
| Collection Fiber and OTDR testing | EPC | EPC | EPC | NA | EPC | EPC | EPC
| Inverter Switches/Media converters | EPC | EPC | EPC | EPC | EPC | EPC | EPC
| Tracker Controllers | Tracker Supplier | EPC | EPC | Tracker Supplier | Tracker Supplier | Tracker Supplier | Tracker Supplier
| Tracker Network Units | Tracker Supplier | EPC | EPC | Tracker Supplier | Tracker Supplier | Tracker Supplier | Tracker Supplier
Owner's Office | Historian for Owner's remote office | Owner | Owner | Owner | Owner | Owner | Owner | Owner
| Owner | PacifiCorp
| All other responsibilities | Seller

## SCADA (Wind)
SCADA Responsibility Matrix - Wind
| Task/Item | Completion Date | Owner SOW | Substation SOW | O&M SOW | T-Line SOW | Interconnect Substation SOW | MET Station SOW | Collector Fiber SOW | WTG SOW | SCADA Integrator SOW | Telecom Provider
O&M SCADA ROOM | O&M Fiber Splice Box (purchase, install) | must be before installation begins | [6 empty] | X
| O&M Fiber Splice Box (configure & commission) | must be before installation begins | [6 empty] | X
| O&M Fiber wall mounted Patch panel (configure & commission) | must be before installation begins | [6 empty] | X
| O&M Fiber wall mounted Patch Panel (purchase, install) | must be before installation begins |  |  | X
| Communications Cabinet rack mounted Fiber Panel (purchase, install, configure, & commission) | installation started after UPS | [8 empty] | X
| Power to UPS in Communications Cabinet (connect power to the plug on the Smart UPS in the cabinet) | before installation of scada equipment |  |  | X
| Installation of Communications Cabinet (purchase, install, configure, program, & commission) | Same time as the installation of the Smart UPS | [8 empty] | X
| Installation of Corporate Cabinet (purchase, install, configure, program & commission) | started after communications cabinet is installed | [8 empty] | X
| RJ45 wall mounted Patch Panel – on the telecommunications panel (purchase, install, configure, & connectivity test) | must be before installation begins |  |  | X
| RJ11 wall Mounted Patch Panel – on the telecommunications panel (purchase, install, configure, & connectivity test) | must be before installation begins |  |  | X
| Communications Cabinet rack mounted RJ45 panel | installation started after UPS | [8 empty] | X
| Overhead Cable Management System (purchase & install) | must be before installation begins |  |  | X
| POTS Junction Box | must be before installation begins | [9 empty] | X
| Fiber Fusion Splices at Splice Box | must be before installation begins | [6 empty] | X
| Telecom Network Interface Unit (NIU) | must be before installation begins | [9 empty] | X
| Fiber Terminations to wall mounted Patch Panel from splice box | must be before installation begins | [6 empty] | X
| WTG SCADA (purchase, install, configure, program, & commission) | WTG should install same time as the communications cabinet begins | [7 empty] | X
| WTG OPC Server | WTG should install same time as the communications cabinet begins | [7 empty] | X
| Purchase, install, configure Servers, Routers and Firewalls (communications cabinet) | after Smart UPS is installed and configured | [8 empty] | X
| Purchase, install, configure Servers, Routers and Firewalls (corporate cabinet) | After Corporate Cabinet is installed | [8 empty] | X
| Purchase, Install, Configure, & Program Historian Database & Servers, (communications cabinet, not to be confused with the PI Server at Substation) | After all routers and servers are installed and configured | [8 empty] | X
| Purchase, Install, Configure, and Program Workstations and HMI interface | Completed after corporate cabinets | [8 empty] | X
| Develop and Distribute IP Scheme (must be approved by client before installation) | must be before installation begins | [8 empty] | X
| Provide Owner, Operator, & Technical Manuals | ongoing, refer to SCADA SOW | [8 empty] | X
| 2 CISCO 3010 fiber optic compatible Ethernet Switches for communications cabinet (purchase, install, configure, program, & commission) | installed & configured during communications cabinet installation | [8 empty] | X
| 1 fiber Multiplexer - located in O&M Communications Cabinet and Substation Communications cabinets (purchase, install, configure, program, & commission) | installed & configured during communications cabinet installation | [8 empty] | X
| 2 Ethernet to fiber media Converters for communications cabinet (purchase, install, configure, program, & commission) | installed & configured during communications cabinet installation | [8 empty] | X
| 1 Serial to Fiber Media Converter for communications cabinet (purchase, install, configure, program, & commission) | installed & configured during communications cabinet installation | [8 empty] | X
| 2 CheckPoint 2200 Series Firewall for Communications and Corporate Cabinets (purchase, install, configure, program, & commission) | installed & configured during communications cabinet installation | [8 empty] | X
| 1 SCADA T1 Internet Connection (includes router and tele-modem) | must be before installation begins | [9 empty] | X
| 1 WTG T1 Internet Connection (includes router and tele-modem) | must be before installation begins | [9 empty] | X
| 1 EGP T1 Internet Connection (includes router and tele-modem) | must be before installation begins | [9 empty] | X
| Eaton Smart UPS with minimum of two battery units (purchase, install, configure, program, & commission) | Same time as the installation of the corporate cabinet | [9 empty] | X
| QA-QC of SCADA installation | ongoing | [8 empty] | X
| QA-QC of O&M SCADA Room | must be before installation begins | [8 empty] | X
| Training with original materials (coordinated with substation and WTGs and not to be confused with requirement to provide manuals) | provided at completion, refer to SCADA SOW |  | X | [5 empty] | X | X
| Provide VPN access List & Requiremetns | must be before installation begins | X
| Provide Site Specific IT Requirements | must be before installation begins | X
| Provide Power Generation Reliability Commissioning Points List, Documentation& Format Requirements for submission and approval | must be before installation begins | X
| Configure and Program HMI at O&M Building (if required) | When Servers are configured. | [8 empty] | X
| Security System Requiremetns | TBD |  |  | X | [5 empty] | X
| Provide Site Acceptibility Test Point List & Requirements | must be before installation begins | X
MET Station | Met Station Patch Panel | After H-Frame installation | [5 empty] | X
| MET Station Fiber Terminations | After Patch Panel and Fiber Cable installation | [6 empty] | X
| 1 IP managed Met Station Media Converter (purchase, install, configure, program, & commission) | After H-Frame and Data Logger Installation | [7 empty] | X
| MET Station Data Logger (purchase, install, configure, program, & commission) | After H-Frame installation | [5 empty] | X |  | X
| MET Station Power to H-Frame and Tower | Before Met Station installation | [5 empty] | X
| SCADA QA-QC | Ongoing throughout, reference SCADA SOW | [8 empty] | X
| MET Station Data Points List | Before Installlation of MET Station & Tower | X | [6 empty] | X
| Training with materials (coordinated with WTG supplier and not to be confused with SCADA SOW training requirements) | Upon completion, Reference Substation SOW | [7 empty] | X | X
Substation | Fiber Terminations to wall mounted patch panel from splice box | started immediately after wall mounted patch panel is installed | [6 empty] | X
| Fiber Fusion Splices at Splice Box (Fiber circuits & O&M) | When collection, OPGW, & O&M cables are installed | [6 empty] | X
| Fiber from Substation to Interconnect Substation | Installed during T-Line Install |  |  |  | X
| Fiber termination at Interconnection Substation | Immediately when terminating T-Line at that location. |  |  |  | X
| Terminations at OPGW splice Box | Immediately after T-Line and H-Frame Splice Box is installed |  |  |  | X
| Attenuation (OTDR) report - Substation to Interconnect Substation | Immediately after fiber terminations |  |  |  | X
| Provide Media Converter Information from Interconnection Substation | Before T-Line installation |  |  |  |  | X
| Attenuation (OTDR) Report - (coordinated with substation, WTGs, EPC, etc.) | Immediately after Fiber Terminations |  | X | [6 empty] | X
| Wind Farm PPC (purchase, install, configure, program, & commission) | Immediately when substation control room is available. | [7 empty] | X
| Wind Farm GMS (purchase, install, configure, program, & commission) | Immediately when substation control room is available. | [7 empty] | X
| Relay, RTU, RTAC, check-meters, etc. (purchase, install, configure, program, & COMMISSION) | Immediately when substation control room is available. |  | X
| Purchase, install, configure, program and commission the communications Cabinet (includes media converters, Mux, Ethernet Switch, SEL3355, telephone, etc) | Immediately when substation control room is available. |  | X
| 2 IP Managed Ethernet to Fiber Media Converts- communications with O&M (purchase, install, configure, program, & commission) | Immediately when substation control room is available. |  | X
| 1 IP Managed Serial to Fiber Media Convert - communicates with O&M (purchase, install, configure, program, & commission) | Immediately when substation control room is available. |  | X
| 1 Fiber Multiplexer - communicates with mulitplexer at the O&M (purchase, install, configure, program, & commission) | Immediately when substation control room is available. |  | X
| 1 Cisco 3010 Ethernet Switch - communicates with Cisco 3010 in O&M (purchase, install, configure, program, & commission) | Immediately when substation control room is available. |  | X
| SEL3530 RTAC (purchase, install, configure, program, & COMMISSIONED) | Immediately when substation control room is available. |  | X
| SEL3355 (purchase, install, configure, program, & COMMISSIONED) | Immediately when substation control room is available. |  | X
| ION7650 Check Meter(purchase, install, configure, program, & COMMISSIONED) | Immediately when substation control room is available. |  | X
| SCADA QA-QC | Ongoing throughout, reference SCADA SOW | [8 empty] | X
| Training with materials (substation training not be confussed with SCADA SOW & training requirements) | Upon completion, Reference Substation SOW |  | X
| Purchase, Install, Program, & Configure Media Converter for communications with the Interconnection Substation | Immediately when substation control room is available. |  | X
| PI Server (Purchase, Install, Program, Configure, & Commission) | When RTAC & ION7650 is installed |  | X
Turbines | Fiber Terminations in Turbines (4 fibers minimum, preferrably all fiber ends are terminated) | During Tower installation | [7 empty] | X
| Fiber terminations outside the turbine (fiber box) | During MV cable and Fiber Junction Box installation | [6 empty] | X
| Attenuation/OTDR report (coordinated between WTG & EPC) | Immediately upon completion | [6 empty] | X | X
| Design optical path diagram (coordinated with EPC) | Before 100% Engineering Review | [7 empty] | X
| Optical Path installation | Ongoing during MV and Fiber cable installaions | [7 empty] | X
| SCADA QA-QC | Ongoing throughout, reference SCADA SOW | [8 empty] | X
| Fiber Commissioning | Immediately upon completion and before Engergization | [7 empty] | X
Fiber | Pigtail terminations from wall mounted fiber fusion splice box to corporate and VOB devices and communications cabinet patch panel | Immediately after wall mounted fiber spice box and VOB installation | [6 empty] | X
| Fiber installation | Ongoing during turbine, Substation, and O&M installations | [6 empty] | X
| Attenuation (OTDR) Report (coordinated with substation & WTG) | Immediately upon completion | [6 empty] | X
| Terminations in J-boxes | Immediately upon J-Box and Fiber cable installation | [6 empty] | X
| Termination of Fibers at MET station | Immediately upon installation of Fiber Cable & Met Station | [6 empty] | X
| Fiber Design Specs and Drawings for SS to O&M | By 100% Drawging review | [8 empty] | X
| Fiber Design Specks & Drawings for Turbine Collection Circuits | By 100% Drawging review | [7 empty] | X
| SCADA QA-QC | Ongoing throughout, reference SCADA SOW | [8 empty] | X
| Owner | PacifiCorp
| All other responsibilities | Seller

## SCADA (BESS)
BESS SCADA Division of Responsibility
Description | Procure | Design | Install | Program | Quality Check | Commission
Location: SCADA Integration & Building Control Room
External Switches/Routers | EPC Contractor | Owner | EPC Contractor | Owner | Owner | Owner
Firewall | EPC Contractor | Owner | EPC Contractor | Owner | Owner | Owner
Internal Switches/Routers | EPC Contractor | Owner | EPC Contractor | Owner | Owner | Owner
Fiber Patch Panel | EPC Contractor | BESS Engineer | EPC Contractor | BESS Engineer | BESS Engineer | BESS Engineer
Telecommunications for External Connections including backup connections | EPC Contractor | Owner | EPC Contractor | Owner | Owner | Owner
Remote access to Battery, PCS, SCADA and Control suppliers during warranty phase | Owner | Owner | Owner | Owner | Owner | Owner
Remote access for Control supplier during operational phase | Owner | Owner | Owner | Owner | Owner | Owner
Network IP assignments/subnet mask/port assignments of switches/routers and LAN configurations | Owner | Owner | Owner | Owner | Owner | Owner
Coordinate site data back to operations center for remote operation | Owner | Owner | Owner | Owner | Owner | Owner
Coordinate with all internal and external parties | - | BESS Engineer | - | - | BESS Engineer | BESS Engineer
Building RTAC | EPC Contractor | BESS Engineer | EPC Contractor | BESS Engineer | BESS Engineer | BESS Engineer
Building Master Points List | - | BESS Engineer | - | BESS Engineer | BESS Engineer | BESS Engineer
CAT 6/fiber cables/conduit between equipment and for external communications to telecom demarcation. | EPC Contractor | BESS Engineer | EPC Contractor | EPC Contractor | EPC Contractor | BESS Engineer
BESS Master Controller | Control | Control | EPC Contractor | Control | Control | Control
Data connection with Market Participant | - | Control | EPC Contractor | Control | Control | Control
Master HMI Server | Control | Control | EPC Contractor | Control | Control | Control
BESS SCADA Server | Control | Control | EPC Contractor | Control | Control | Control
Media Converters As Required | EPC Contractor | BESS Engineer | EPC Contractor | BESS Engineer | BESS Engineer | BESS Engineer
Communication routing design within the control room | EPC Contractor | BESS Engineer | EPC Contractor | BESS Engineer | BESS Engineer | BESS Engineer
Fiber routing/path/terminations/splice /OTDR report within control room | EPC Contractor | BESS Engineer | EPC Contractor | BESS Engineer | BESS Engineer | BESS Engineer
Communication between BESS RTAC and SS RTAC | EPC Contractor | BESS Engineer & SS Engineer | EPC Contractor | BESS Engineer & SS Engineer | BESS Engineer & SS Engineer | BESS Engineer & SS Engineer
Location: BESS SCADA & Misc. Equipment
Managed Switches | EPC Contractor | Owner | EPC Contractor | Owner | Owner | Owner
Security cameras, DVR storage size, and camera directions | EPC Contractor | BESS Engineer | EPC Contractor | BESS Engineer | BESS Engineer | BESS Engineer
CAT 6/fiber cables/2-Wire between BMS, PCS, thermal and fire management | EPC Contractor | BESS Engineer | EPC Contractor | BESS Engineer | BESS Engineer | BESS Engineer
Firewall configuration for remote access by external parties | EPC Contractor | Owner | EPC Contractor | Owner | Owner | Owner
Auxiliary Power | EPC Contractor | BESS Engineer | EPC Contractor | EPC Contractor | EPC Contractor | EPC Contractor
Modbus Communication from controller to BMS | EPC Contractor | BESS Engineer | EPC Contractor | Control | Control | Control
Modbus Communication from controller to Power Conversion Systems | EPC Contractor | BESS Engineer | EPC Contractor | Control | Control | Control
Location: General Facility Design
Modules, MBMS, RBMS, SBMS | Owner | Owner/ BESS Engineer | EPC Contractor | Owner | Owner | Owner/ BESS Engineer
SCADA integration with Power Conversion Systems | EPC Contractor | BESS Engineer/ Control | EPC Contractor | EPC Contractor/ Control | EPC Contractor | BESS Engineer/Control
LV Power Distribution Units | EPC Contractor | BESS Engineer | EPC Contractor | - | EPC Contractor | EPC Contractor
DC and MV Power Distribution | EPC Contractor | BESS Engineer | EPC Contractor | - | EPC Contractor | EPC Contractor
Thermal Management | EPC Contractor | Mechanical | EPC Contractor | EPC Contractor | EPC Contractor | EPC Contractor
Fire Protection/Life Safety | EPC Contractor | Mechanical | EPC Contractor | EPC Contractor | EPC Contractor | EPC Contractor
Fiber routing/path/terminations/splice /OTDR report | EPC Contractor | BESS Engineer | EPC Contractor | EPC Contractor | EPC Contractor | BESS Engineer
Location: Substation & Control Building
Meter | EPC Contractor | SS Engineer | EPC Contractor | SS Engineer | SS Engineer | SS Engineer
MPT IEDs | EPC Contractor | SS Engineer | EPC Contractor | SS Engineer | SS Engineer | SS Engineer
Relays | EPC Contractor | SS Engineer | EPC Contractor | SS Engineer | SS Engineer | SS Engineer
Fiber Patch Panel | EPC Contractor | SS Engineer | EPC Contractor | - | SS Engineer | SS Engineer
Auxillary Power | EPC Contractor | SS Engineer | EPC Contractor | - | SS Engineer | SS Engineer
SS HMI Server | EPC Contractor | SS Engineer | EPC Contractor | SS Engineer | SS Engineer | SS Engineer
SS RTAC | EPC Contractor | SS Engineer | EPC Contractor | SS Engineer | SS Engineer | SS Engineer
SS Master Points List | - | SS Engineer | - | SS Engineer | SS Engineer | SS Engineer
P&C and RTAC Cabinets | EPC Contractor | SS Engineer | EPC Contractor | SS Engineer | SS Engineer | SS Engineer
GPS Clock | EPC Contractor | SS Engineer | EPC Contractor | SS Engineer | SS Engineer | SS Engineer
Media Converters As Required | EPC Contractor | SS Engineer | EPC Contractor | - | SS Engineer | SS Engineer
Communication within the Substation | EPC Contractor | SS Engineer | EPC Contractor | - | SS Engineer | SS Engineer
Data connection with TSP |  | SS Engineer | - | SS Engineer | SS Engineer | SS Engineer
Fiber routing/path/terminations/splice /OTDR report within Substation | EPC Contractor | SS Engineer | EPC Contractor | - | SS Engineer | SS Engineer
Owner | PacifiCorp
EPC Contractor | TBD
BESS Engineer | TBD
SS Engineer | TBD
Control | TBD
Mechanical | TBD