## Sheet1
PacifiCorp 2025 WA Situs RFP |  | Completed by:________________________________
| Agency | Permit or Action Required | Information Regarding Permit or Action Requirements | Status | Expected Completion Date
Federal
| Environmental Protection Agency (EPA) in coordination with the State Regulatory Authority | Phase I Environmental Site Assessment (which must not be dated earlier than 180 days prior to the Closing Date); Phase II Environmental Site Assessment (if warranted based on Phase I RECs) | A report must be prepared for a real estate holding that identifies potential or existing environmental contamination liabilities. No submittal required to EPA.
|  | Spill Prevention Control and Countermeasure Plan (SPCC) | Develop and implement SPCC plan.
|  | National Pollutant Discharge Elimination System Stormwater Permit | Obtain NPDES construction stormwater permit and Stormwater Pollution Prevention Plan (SWPPP) must be obtained and implemented.
| Federal Communications Commission (FCC) | Microwave Study | Identify any beam path issues and resolve prior to final project design/construction.
| Department of Commerce / NTIA | National Telecommunications and Information Administration (NTIA) Filing | Identify and manage any telecoms issues, if applicable.
| Federal Emergency Management Agency (FEMA) | Flood Plain Designations | Determine flood plain designation.
|  | Flood Plain Development Permitting | Develop and submit Floodplain Development Permit, if applicable.
| Federal Energy Regulatory Commission (FERC) | Exempt Wholesale Generator Certificate (EWG) | Self-Certification if applicable.
|  | Market-Based Rate Authorization (MBA) | Determine if MBA is required/applicable.
|  | Other FERC filings | N/A
| Federal Land Manager (BLM, USBR, Forest Service) | Right-of-Way Crossing | Obtain Right-of-Way grant over Federal lands if applicable.
| National Historic Preservation Act | Federal Section 106, Class I Literature Review / Class II Architectural Survey/ Class III Cultural Field Survey | Section 106 of the National Historic Preservation Act (NHPA) may be invoked by a Federal Agency if the Project requires federal land, funding, or permits. Seller to complete preliminary Class I literature review of National and State registered sites, and Class II or Class III field survey for preliminary turbine, collection line, and access road layout. No submittal to National Historic Preservation Act required.
| U.S. Army Corps of Engineers (USACE) | Wetland Delineation | Perform desktop review and preliminary field wetland delineation per 1987 Corps Wetland Delineation Manual and Regional Supplements to determine extent of USACE jurisdiction, quantify impacts based on the preliminary turbine, collection line, and access road design (only the intersection between preliminary design and identified wetland features will be delineated).
|  | Wetland and Grassland Easement Permit | Obtain the permit needed for easement through wetlands and measures to ensure that construction, operation and maintenance will only temporarily drain or fill easement wetlands, if applicable.
|  | Final Wetland Delineation and Documentation of Impacts | Perform any additional field wetland delineations per 1987 Corps Wetland Delineation Manual and Regional Supplements as necessary due to final design changes, and document avoidance during construction.
|  | Jurisdictional Determination | Determine eligibility for a Letter of No Jurisdiction based on limited wetland impacts.
|  | Preconstruction Notice (PCN) | Submit PCN for wind farm which includes facility construction, expansion or modification, if required.
|  | Federal Clean Water Act Section 404 and Section 10 Permit(s) | Required for the discharge of dredged or fill material into waters of U.S. Minimal levels of fill may be covered under existing General Permits/Letters of Permission.
|  | Conservation / Grassland / and Wetland Easement Reserve Program: Existing Filing(s) | Determine if program is applicable to proposed project.
| U.S. Department of Agriculture | Farm Service Agency (FSA) Conservation / Grassland / Wetland Easement and Reserve Program (CRP) Releases and Consents | Obtain all CRP land location and contract data, to include CRP-1, Appendix CRP-1 and Conservation Plan.
|  | FSA Mortgage Subordinations & Site-Specific Environmental Assessments | Perform assessments if applicable.
| U.S. Fish and Wildlife Service (USFWS) | Communications and Data | Communications with USFWS per Land-Based Wind Energy Guidelines and Eagle Conservation Plan Guidance.
|  | Wetland and Grassland Easements | Identify any wetland or grassland easements purchased by USFWS from landowners.
|  | Land-Based Wind Energy Guidelines Tier 1 Preliminary site evaluation (Eagle Conservation Plan Guidance Stage 1) | Review Guidelines and implemented applicable guidance.
|  | Land-Based Wind Energy Guidelines Tier 2: Site characterization (Eagle Conservation Plan Guidance Stage 1) | • Assess potential presence of species of concern, including species of habitat fragmentation concern • Assess potential presence of plant communities present on site that may provide habitat for species of concern • Assess potential presence of critical congregation areas for species of concern
|  | Land-Based Wind Energy Guidelines Tier 3: Field studies (Eagle Conservation Plan Guidance Stage 2) | • Discuss extent and design of field studies to conduct with the Service • Conduct biological studies • Communicate results of all studies to Service field office
|  | Eagle or Protected Species Take Permit, based on results found in Tier 3 Studies | An application for incidental take by certain hazards of wind farms to any ESA-listed species; All projects must apply for an eagle take permit if eagles are likely to be present at the site.
|  | Tier 4: Post construction studies to estimate impacts | Conduct post-construction studies to assess fatalities and habitat-related impacts.
|  | Tier 5: Other post-construction studies and research | • Conduct appropriate studies as needed • Identify potential mitigation strategies to reduce impacts
| Federal Aviation Administration (FAA) | Notice of Proposed Construction or Alteration (Form 7460-1) | Determination of No Hazard to Air Navigation needed for each structure over 200 feet tall via form 7460-1. (Includes cranes, turbines, MET towers, etc.).
|  | Notice of Actual Construction (Form 7460-2) | File 7460-2 within 5 days after the structure reaches its greatest height (includes cranes, turbines, MET towers, etc.).
| U.S. Department of Defense | Federal airways and airspace review near military bases | If the proposed facilities are near military bases.
| U.S. Department of Transportation | Utility Line Crossing License | Needed if transmission/collection crosses a federal highway.
State
| Department of Transportation | Highway Crossings/turning lanes/traffic control installations; Obtain State Road Use Agreement (RUP); Port of Entry permits; Oversized/overweight permits; etc.) | Required for facilities crossing over or under highways, turning lanes, traffic control devices and highway entrances.
| Department of Environmental Quality | State Industrial Siting Council (or similar) Approval (Certificate, Finding of Facts/Conclusion, etc.) | Gather all needed information for the State level operating permit, if applicable.
|  | Pollutant Discharge Elimination System Large Construction General Permit (Water Quality) | Obtain and manage pollution discharge permit.
|  | Turbidity Permit (Water Quality) | Obtain permit and manage if applicable.
|  | General Permit for Temporary Discharge (Water Quality) | Obtain permit and manage if applicable.
|  | Temporary / Portable Source Air Permit (Air Quality) (Includes fugitive dust control) | Obtain permit and manage if applicable.
|  | Wastewater Facilities Permit and/or Well Water Permit for Construction and/or Operations of site facilities | Obtain permit and manage if applicable.
|  | Water Quality – Section 401 Certification | Obtain permit and manage if applicable.
| State Historic Preservation Office | Cultural and Historic Resources Review of State and National Register of Historic Sites and Archeological Survey | Complete Class I literature review and Class II or Class III field survey for preliminary turbine, collection system, and access road layout.
|  | Cultural Properties Review Committee | May be implicated if there are cultural resources that will be impacted, or unmarked burials encountered during construction.
| Game and Fish Department | Communication and Data | Coordination and agreements with state/local wildlife agencies.
| State Engineer Office | Permit to appropriate groundwater or lease of existing adjudicated source by temporary water use agreement | Obtain permit and manage if applicable.
| Office of State Lands & Investments | Special Use Lease for wind energy | Required only to the extent that state lands are within the area of the Projects.
| Public Service Commission | Certificate of Public Convenience and Necessity (CPCN) | Provide all documents and draft CPCN necessary for buyer/operator to submit and obtain the CPCN.
County
| County/City | Conditional Use Permit (CUP), Zoning Permit/Certificate, and/or Wind Energy Conversion Systems (WECS) | Prepare all documents, hold meetings/open houses with applicable agencies and the public to obtain CUP, zoning permit/certificate, and/or WECS permit(s) and approvals.
| County/City | Building permits | Obtain all building permits prior to construction and manage permit compliance/closeout.
| County/City | County Road Permits | Obtain permit and manage if applicable.
| County/City | Road use agreements | Obtain RUP and manage if applicable.
| County/City | Development agreements | Obtain permit and manage if applicable.
Miscellaneous
| Wildlife Management | Observation tower(s) | Consult with PacifiCorp on location, specifications, and operational/communications needs for siting, construction, and operations of observation tower.
| Wildlife Management | Lease agreements/Site Management | Consult with PacifiCorp on grazing areas/rights, removal of carrion, no build zones, etc.
| Hunter Management | Lease agreements/Site Management | Consult with PacifiCorp on hunting rights and setbacks from wind turbines. No hunting within 1,000 feet of project turbines.