## List
Attachment 1B - Project Document Deliverables
Project Description: | [8 empty] | Project Manager:
Plant: | [8 empty] | Plant Project Team:
Unit No.: | [8 empty] | Project Start Date:
WBS No.: | [8 empty] | Project End Date:
No. of Hard Copies | No. of Electronic Copies | COMPANY: Plant to provide EXAMPLE | COMPANY: Corporate to provide EXAMPLE | Required | STAGE |  |  | Deliverable |  | Description | Company Submittal Schedule | Contractor Proposed Submittal Schedule | Submittal Disc(s)
[5 empty] | Review | Construction | As-Built/As-Installed
|  |  |  | X |  |  | X | Project Closure | 0 | Issued as "as-installed" procedures (engineering, environmental, maintenance, operations, safety, etc.) (provided in Company format) | PTFP |  | Non-drawing
|  |  |  | X |  |  | X | Project Closure | 0 | Reports: critical lift plan, engineering, EPA, geotechnical, final inspection, noise dosimetry, system turnover packages, etc. | PTFP |  | Non-drawing
|  |  |  | X |  |  | X | Project Closure | 0 | Specifications | PTFP |  | Non-drawing
|  |  |  | X |  |  | X | Project Closure | 0 | Training documents | PTFP |  | Non-drawing
|  |  |  | X |  |  | X | Project Closure | 0 | Drawings: cable, wire, panel, conduit schedules, etc. | PTFP |  | Drawing
|  |  |  | X |  |  | X | Project Closure | 0 | Issued as "as-built" delivery all engineering drawings created for the project | PTFP |  | Drawing
|  |  |  | X |  |  | X | Project Closure | 0 | Issued as "as-installed" all lists and data sheets supporting project systems and equipment | PTFP |  | Non-drawing
|  |  |  | X |  |  | X | Project Closure | 0 | Issued as "as-installed" all certificates warranties and test reports | PTFP |  | Non-drawing
|  |  |  | X |  |  | X | Project Closure | 0 | Issued as "as-installed" all vendor manuals documentation | PTFP |  | Non-drawing
|  |  |  | X |  |  | X | Project Closure | 0 | Issued as "as-built" all project drawings | PTFP |  | Drawing
|  |  |  | X |  |  | X | Project Closure | 0 | Issued as "as-installed" all spare parts lists OEM | PTFP |  | Non-drawing
|  |  |  | X |  |  | X | Project Closure | 0 | Issued as "as-installed" all maintenance instruction pm's | PTFP |  | Non-drawing
|  |  |  | X |  |  | X | Project Closure | 0 | Issued as "as-installed" project overview "turnover books" | PTFP |  | Non-drawing
[8 empty] | Project Management and Control Procedure(s) | 1 | Project organization with individuals areas of responsibility and contact information | 8AA
[8 empty] | Project Management and Control Procedure(s) | 1 | Communications plan | 8AA
[8 empty] | Project Management and Control Procedure(s) | 1 | Procedure for design, review, comment and approvals
[8 empty] | Project Management and Control Procedure(s) | 1 | Document control, project filing system, distribution and action tracking (including sub-contractors) | 8AA
[8 empty] | Project Management and Control Procedure(s) | 1 | Compliance and understanding agreement to Company drawing and documentation standards | 8AA
[8 empty] | Project Management and Control Procedure(s) | 1 | System list and equipment numbering schemes | 8AA
[8 empty] | Project Management and Control Procedure(s) | 1 | Drawing and document numbering scheme | 8AA
[8 empty] | Project Management and Control Procedure(s) | 1 | Minutes of meetings records and follow up procedure | 8AA
[8 empty] | Project Management and Control Procedure(s) | 1 | Procurement specification, procedures and log | 8AA
[8 empty] | Project Management and Control Procedure(s) | 1 | Billing and payment procedures | 8AA
[8 empty] | Project Management and Control Procedure(s) | 1 | Scheduling plan to include engineering, procurement, construction and integrated path schedule (See EPC Appencis B Critical Path Requirement) | 8AA plan / reports monthly
[8 empty] | Project Management and Control Procedure(s) | 1 | Progress report plan | 8AA plan / reports monthly
[8 empty] | Project Management and Control Procedure(s) | 1 | Notice of termination | 1D
[8 empty] | Project Management and Control Procedure(s) | 1 | Punch list and close out plan
[8 empty] | Construction Plan and Procedure(s) | 2 | Notice of intent | 10DBF
[8 empty] | Construction Plan and Procedure(s) | 2 | Reference to contract statement of work | 8AA
[8 empty] | Construction Plan and Procedure(s) | 2 | Testing requirements/policy and procedure (including performance guarantee test plans) | 8AA
[8 empty] | Construction Plan and Procedure(s) | 2 | Electrical test programs and acceptance test procedures | 8AA
[8 empty] | Construction Plan and Procedure(s) | 2 | Erection and installation specifications | 8AA
[8 empty] | Construction Plan and Procedure(s) | 2 | Calibration of instruments policy and procedure | 8AA
[8 empty] | Construction Plan and Procedure(s) | 2 | Inspections policy and procedure | 8AA
[8 empty] | Construction Plan and Procedure(s) | 2 | Reporting non-conformance policy and procedure | 8AAplan / ?D report
[8 empty] | Construction Plan and Procedure(s) | 2 | Field changes policy and procedure | 8AAplan/ ?D report
[8 empty] | Construction Plan and Procedure(s) | 2 | As-builds policy and procedure | 8AA
[8 empty] | Construction Plan and Procedure(s) | 2 | All performance guarantee test plans and procedures including correction curves | 8AA
[8 empty] | Construction Plan and Procedure(s) | 2 | Punch list and close out policy and procedure | 8AA
[8 empty] | Construction Plan and Procedure(s) | 2 | Construction permits | 8AA
[8 empty] | Start-Up Plan and Procedure(s) | 3 | Start-up schedule
[8 empty] | Start-Up Plan and Procedure(s) | 3 | Start up organization chart
[8 empty] | Start-Up Plan and Procedure(s) | 3 | Start-up work responsibility matrix
[8 empty] | Start-Up Plan and Procedure(s) | 3 | Start-up administrative procedure
[8 empty] | Start-Up Plan and Procedure(s) | 3 | Start-up test procedures for each mechanical completion, performance and equipment demonstration test items
[8 empty] | Start-Up Plan and Procedure(s) | 3 | Start-up safety clearance procedure
[8 empty] | Start-Up Plan and Procedure(s) | 3 | Start-up turn over sequences and procedures
[8 empty] | Safety Plan and Procedure(s) | 4 | Material safety data sheets | 4BD
[8 empty] | Safety Plan and Procedure(s) | 4 | Construction safety reports
[8 empty] | Environmental Plan and Procedure(s) | 5 | Fugitive dust plan | 12AA
[8 empty] | Environmental Plan and Procedure(s) | 5 | Hazardous material plan | 12AA
[8 empty] | Environmental Plan and Procedure(s) | 5 | Strom water management runoff/detention (pollution prevention) | 12AA plan / 12BF report
[8 empty] | Environmental Plan and Procedure(s) | 5 | Scrap removal management plan and procedure | 12AA
[8 empty] | Environmental Plan and Procedure(s) | 5 | Environmental permits | 12BF
[8 empty] | QA/QC Plan and Procedure(s) | 6 | QC inspection point program | 8AA
[8 empty] | QA/QC Plan and Procedure(s) | 6 | All performance guarantee test plans and procedures including correction curves | 8AA ?
[8 empty] | QA/QC Plan and Procedure(s) | 6 | Welding and qualification procedure | 8AA
[8 empty] | QA/QC Plan and Procedure(s) | 6 | Test procedures as per ASME, ANSI, IEEE, API, HEI, NEMA, ASTM, etc. | 8AA
[8 empty] | QA/QC Plan and Procedure(s) | 6 | Plan for handling, storage and pre-operational and operational maintenance of equipment | 8AA / 8BD record
[8 empty] | QA/QC Plan and Procedure(s) | 6 | Special handling procedures for stainless steel or other sensitive materials | 8AA
[8 empty] | QA/QC Plan and Procedure(s) | 6 | Special process i.e., heat treating, plating, cladding, shot peening, etc. | 8AA
[8 empty] | QA/QC Plan and Procedure(s) | 6 | Interior and exterior finish and color paint samples | 4AA
[8 empty] | QA/QC Plan and Procedure(s) | 6 | Cleaning, painting and packaging procedures | 8AA
[8 empty] | QA/QC Plan and Procedure(s) | 6 | Deviation records and approved deviation reports | 8AA plan / 10BF
[8 empty] | QA/QC Plan and Procedure(s) | 6 | Test records plans to submit for owner review and acceptance | 8AA plan / 10D record
[8 empty] | QA/QC Plan and Procedure(s) | 6 | Manufacturer's data reports | 8AA plan / 10D record
[8 empty] | QA/QC Plan and Procedure(s) | 6 | Non-destructive examination procedures and personnel qualifications | 8AA
[8 empty] | QA/QC Plan and Procedure(s) | 6 | Inspection and non-destructive examination records | 8AA plan / 10D record
[8 empty] | QA/QC Plan and Procedure(s) | 6 | Material certifications, including filler metal certifications and test reporting | 8AA plan / 4BF record
[8 empty] | QA/QC Plan and Procedure(s) | 6 | Third party QA/QC analysis and reporting | 8AA plan
[8 empty] | QA/QC Plan and Procedure(s) | 6 | Acceptance procedure | 8AA plan / 6BF record
[8 empty] | Training Plan and Procedure(s) | 7 | Written training program | 12B
[8 empty] | Training Plan and Procedure(s) | 7 | Training material | submit 9 months prior to anticipated mechanical completion date; allow 45 days to review
[8 empty] | Training Plan and Procedure(s) | 7 | Preliminary operations procedures (provided in Company format)
[8 empty] | Design Data | 8 | System descriptions including principle and mode of operation, required interlocks, hydraulic gradients, etc. | 8AA
[8 empty] | Design Data | 8 | System flow and elementary diagrams-preliminary | 8AA
[8 empty] | Design Data | 8 | Equipment descriptions
[8 empty] | Design Data | 8 | Cable specification and codes
[8 empty] | Design Data | 8 | Cable tray specifications and codes
[8 empty] | Design Data | 8 | Access requirements | 8AA
[8 empty] | Design Data | 8 | Material lists including equivalent standard if different than those initially specified | 8AA
[8 empty] | Design Data | 8 | Control system specification
[8 empty] | Design Data | 8 | DCS graphics and logic design and implementation process plan | 8AA
[8 empty] | Design Data | 8 | Instrumentation specifications
[8 empty] | Design Data | 8 | Overall performance data | 8AA
[8 empty] | Design Data | 8 | Electrical load list | 8AA
[8 empty] | Design Data | 8 | Erection information including lifting points, loads and storage requirements
[8 empty] | Design Data | 8 | Fire suppression specification
[8 empty] | Design Data | 8 | HVAC specification
[8 empty] | Survey's and Studies | 9 | General survey | 8AA
[8 empty] | Survey's and Studies | 9 | Geotechnical investigation report | 8AA
[8 empty] | Survey's and Studies | 9 | Noise study | 8AA
[8 empty] | Survey's and Studies | 9 | Arc flash study | 8BP
[8 empty] | Survey's and Studies | 9 | Arc flash labels
[8 empty] | Survey's and Studies | 9 | Breaker coordination study | 2W
[8 empty] | Equipment and Instrumentation Documents | 10 | Specifications | 4BP
[8 empty] | Equipment and Instrumentation Documents | 10 | Description/design criteria (equipment and instrumentation data sheets as required with lists) | 4BP
[8 empty] | Equipment and Instrumentation Documents | 10 | Manufacture's product sheet | 4BP
[8 empty] | Equipment and Instrumentation Documents | 10 | Protective coatings and preservatives | 4BD
[8 empty] | Equipment and Instrumentation Documents | 10 | Inspection and test data (to include shop test data) | 8BF
[8 empty] | Equipment and Instrumentation Documents | 10 | Installation instructions drawings and details
[8 empty] | Equipment and Instrumentation Documents | 10 | Spare parts list (with OEM references, part numbers and pricing) | 6 months prior to start-up
[8 empty] | Equipment and Instrumentation Documents | 10 | Equipment start-up and commissioning plan | 6 months prior to start-up
[8 empty] | Equipment and Instrumentation Documents | 10 | Operating, maintenance and installation instruction manuals and materials from manufacturer to include complete operations, troubleshooting and maintenance instruction | 6 months prior to start-up
[8 empty] | Equipment and Instrumentation Documents | 10 | Nameplate information and shop order numbers for each item of equipment and components
[8 empty] | Equipment and Instrumentation Documents | 10 | Operating procedures and instructions for commissioning, startup, normal operation, shut downs, standby, emergency conditions and special safety precautions for individual items of equipment or system
[8 empty] | Equipment and Instrumentation Documents | 10 | Listing of any start-up prerequisites
[8 empty] | Equipment and Instrumentation Documents | 10 | Normal range of system variables
[8 empty] | Equipment and Instrumentation Documents | 10 | Operating limits and hazards for all equipment and the system including alarm and trip set points for all devices
[8 empty] | Equipment and Instrumentation Documents | 10 | Testing and checking requirements
[8 empty] | Equipment and Instrumentation Documents | 10 | Effect of loss of normal power
[8 empty] | Equipment and Instrumentation Documents | 10 | Tolerance of electrical supply frequency variation
[8 empty] | Equipment and Instrumentation Documents | 10 | Performance warranty data
[8 empty] | Equipment and Instrumentation Documents | 10 | Final performance curves (include test data and test curves)
[8 empty] | Equipment and Instrumentation Documents | 10 | Preventive maintenance schedule and maintenance instruction for equipment including standard and safety precautions | 6 months prior to start-up
[8 empty] | Equipment and Instrumentation Documents | 10 | Lubrication schedule (showing initial fill levels, requirements and specifications for lubricants) | 4BD
[8 empty] | Equipment and Instrumentation Documents | 10 | Cleaning and conservation procedures
[8 empty] | Equipment and Instrumentation Documents | 10 | Dismantling and assembly procedures for equipment with associated tests and checks prior to returning equipment to service (including the detailed assembly drawings)
[8 empty] | Equipment and Instrumentation Documents | 10 | Setting and running clearances and tolerances
[8 empty] | Equipment and Instrumentation Documents | 10 | Drawing showing space needed for equipment maintenance and any fixed equipment
[8 empty] | Equipment and Instrumentation Documents | 10 | Anchor bolt/base pattern, mounting information, etc.
[8 empty] | Equipment and Instrumentation Documents | 10 | Erection information, including lifting points, loads, overall dimensions, etc.
[8 empty] | Equipment and Instrumentation Documents | 10 | Instrument vibration requirements and procedures
[8 empty] | Equipment and Instrumentation Documents | 10 | Methods for trouble shooting
[8 empty] | Equipment and Instrumentation Documents | 10 | List of maintenance tools furnished with equipment (See EPC Appendix O)
[8 empty] | Equipment and Instrumentation Documents | 10 | Equipment and material instruction bulletins and cut sheets
[8 empty] | Equipment and Instrumentation Documents | 10 | Vendor supplied data sheets
[8 empty] | Equipment and Instrumentation Documents | 10 | Vendor specification sheets
[8 empty] | Equipment and Instrumentation Documents | 10 | Vendor supplied test information
[8 empty] | Equipment and Instrumentation Documents | 10 | Vendor supplied certifications and inspections
[8 empty] | General Arrangement Drawings/Documents | 11 | Site plan general arrangement drawings | 4AA
[8 empty] | Architectural Drawings/Documents | 12 | Floor plan interior layout and details | 4AA
[8 empty] | Architectural Drawings/Documents | 12 | Lighting and electrical plan | 8BF
[8 empty] | Architectural Drawings/Documents | 12 | HVAC | 8BF
[8 empty] | Architectural Drawings/Documents | 12 | Plumbing and sanitary drain piping | 8BF
[8 empty] | Architectural Drawings/Documents | 12 | Elevations | 8BF
[8 empty] | Architectural Drawings/Documents | 12 | Siding and roofing details | 8BF
[8 empty] | Architectural Drawings/Documents | 12 | Foundation plan | 8BF
[8 empty] | Civil Drawings/Documents | 13 | Construction site development including fences, gates, lay down and fabrication area, crane placement and temporary roads buildings and facilities, etc. | 4BF
[8 empty] | Civil Drawings/Documents | 13 | Survey, grading and contour plot locating structures and monuments referenced to plant and state plane coordinates | 4BF
[8 empty] | Civil Drawings/Documents | 13 | Construction storm water management, drainage and sediment control plan | 4BF
[8 empty] | Civil Drawings/Documents | 13 | "as-built" site storm water management and drainage plan including underground storm water piping, catch basins, manholes and interconnects to existing piping systems | 4BF
[8 empty] | Civil Drawings/Documents | 13 | Underground oily and sanitary waste drain piping | 4BF
[8 empty] | Civil Drawings/Documents | 13 | Sanitary and waste drain piping | 4BF
[8 empty] | Civil Drawings/Documents | 13 | Underground process piping and drains | 4BF
[8 empty] | Civil Drawings/Documents | 13 | "as-built" site plan including paved and graveled roads, paved areas, parking, curbs, bollards, fences, gates and structures, etc. | 4BF
[8 empty] | Civil Drawings/Documents | 13 | Pond/basin drawings | 4BF
[8 empty] | Civil Drawings/Documents | 13 | Aerial surveys | 4BF
[8 empty] | Structural Drawings/Documents | 14 | Proposed building plans, elevations and interior layout | 4AA
[8 empty] | Structural Drawings/Documents | 14 | Wall, pier and grade beams | 4BF
[8 empty] | Structural Drawings/Documents | 14 | Equipment foundations | 4BF
[8 empty] | Structural Drawings/Documents | 14 | Ground floor slabs, sumps, trenches, trench covers, containments | 4BF
[8 empty] | Structural Drawings/Documents | 14 | Paving and containment plans | 4AA
[8 empty] | Structural Drawings/Documents | 14 | Stair, platform and ladder location and design | 4BF
[8 empty] | Structural Drawings/Documents | 14 | Rebar design, anchor bolts and patterns | 2BF
[8 empty] | Structural Drawings/Documents | 14 | Settlement records
[8 empty] | Structural Drawings/Documents | 14 | Test reports and certifications | 1AC
[8 empty] | Mechanical Drawings/Documents | 15 | Equipment lists to include tag ID | 4AA
[8 empty] | Mechanical Drawings/Documents | 15 | Equipment data sheets to include type and technical requirements | 4BP
[8 empty] | Mechanical Drawings/Documents | 15 | Outline and arrangement of mechanical equipment including outline plan and elevation, dimensions, clearance requirements, terminal connector locations, sizes ratings, empty and full weights, etc. | 4AA
[8 empty] | Mechanical Drawings/Documents | 15 | HVAC drawings
[8 empty] | Electrical Drawings/Documents | 16 | Electrical load list (total connected and total coincidental) | 8BP
[8 empty] | Electrical Drawings/Documents | 16 | Cable list tabulation (circuit schedules) to included to and from, tag number, size, length, routing and schematic references | 4AA / monthly
[8 empty] | Electrical Drawings/Documents | 16 | Cable tray and conduit lists and routing
[8 empty] | Electrical Drawings/Documents | 16 | Heat tracing schedule
[8 empty] | Electrical Drawings/Documents | 16 | Electrical schematics and logic, point-to-point wiring diagrams and interconnection diagrams between electrical/control components | 8BF
[8 empty] | Electrical Drawings/Documents | 16 | Internal schematics and point-to-point wiring diagrams of all panels, instrument racks and junction boxes | 8BF
[8 empty] | Electrical Drawings/Documents | 16 | Outline and arrangement drawings of electrical equipment including outline plan and elevation dimensions; physical arrangements including EEB internal layout; clearance requirements; terminal connection locations, sizes and ratings; empty and full weights, etc. | 12AA
[8 empty] | Electrical Drawings/Documents | 16 | Lighting plan and area illumination levels | 4BP
[8 empty] | Electrical Drawings/Documents | 16 | Yard electrical plot plan
[8 empty] | Electrical Drawings/Documents | 16 | Electrical trench and underground conduit plan
[8 empty] | Electrical Drawings/Documents | 16 | Battery pack location drawing | WD
[8 empty] | Electrical Drawings/Documents | 16 | Fiber optic cable tests | WD
[8 empty] | Electrical Drawings/Documents | 16 | Cable insulation test reports | WD
[8 empty] | Electrical Drawings/Documents | 16 | Transformer test reports | WD
[8 empty] | Electrical Drawings/Documents | 16 | Switchgear test reports | WD
[8 empty] | Electrical Drawings/Documents | 16 | Battery test reports | WD
[8 empty] | Electrical Drawings/Documents | 16 | Power system single line drawings | 8AA
[8 empty] | Electrical Drawings/Documents | 16 | Power system three line drawings | 12AA
[8 empty] | Electrical Drawings/Documents | 16 | Transformer outline and nameplate drawings | 8BF
[8 empty] | Electrical Drawings/Documents | 16 | Key diagrams for each bus (480v and above) | 8AA
[8 empty] | Electrical Drawings/Documents | 16 | Terminal block arrangements | 8BF
[8 empty] | Electrical Drawings/Documents | 16 | Switchgear, MCC nameplate drawings | 8BF
[8 empty] | Electrical Drawings/Documents | 16 | Uat and rat location | 8AA
[8 empty] | Electrical Drawings/Documents | 16 | Duct bank and underground conduit and direct buried cable | 12AA
[8 empty] | Electrical Drawings/Documents | 16 | Cable tray, tray hanger/support location and conduit routing | 12AA
[8 empty] | Electrical Drawings/Documents | 16 | Lighting and welding receptacle locations | 12AA
[8 empty] | Electrical Drawings/Documents | 16 | Communications | 8BP
[8 empty] | Electrical Drawings/Documents | 16 | Fiber and LAN connections | 4BF
[8 empty] | Electrical Drawings/Documents | 16 | Grounding | 12AA
[8 empty] | Electrical Drawings/Documents | 16 | Heat tracing | 4BF
[8 empty] | Electrical Drawings/Documents | 16 | Cathodic protection | 4BF
[8 empty] | I&C Drawings/Documents | 17 | PLC device list (programmable logic controller device list)
[8 empty] | I&C Drawings/Documents | 17 | Input/output quantities (I/O list) | 8BP
[8 empty] | I&C Drawings/Documents | 17 | Instrument list | 10BP
[8 empty] | I&C Drawings/Documents | 17 | Instrument data sheets including materials of construction, pressure and temperature ratings, range or calibration, set points, type of housing and mounting, power consumption, supplier, tag and documentation reference(s) | 8BP
[8 empty] | I&C Drawings/Documents | 17 | Input/output list (including set point and alarm) | 8BP
[8 empty] | I&C Drawings/Documents | 17 | DCS functional description including operating, indication and alarm philosophies, graphic screens and control and alarm set points | 16BF
[8 empty] | I&C Drawings/Documents | 17 | DCS interface details | 20BF
[8 empty] | I&C Drawings/Documents | 17 | DCS graphic layout sketches | 16BF
[8 empty] | I&C Drawings/Documents | 17 | DCS factory acceptance test (FAT) procedure | 4BF
[8 empty] | I&C Drawings/Documents | 17 | Instrument/device/test port location | 8BF
[8 empty] | I&C Drawings/Documents | 17 | Control system architecture | 20BF
[8 empty] | I&C Drawings/Documents | 17 | DCS graphic displays | 12BF
[8 empty] | I&C Drawings/Documents | 17 | Control logic diagrams | 16BF
[8 empty] | I&C Drawings/Documents | 17 | Panel arrangements
[8 empty] | Process Piping/Drawings |  | Process flow diagrams
[8 empty] | Process Piping/Drawings | 18 | Safety/relief valve data sheets | 4BP
[8 empty] | Process Piping/Drawings | 18 | Heat tracing list | 4BP

## Submittal Schedule Legend
Legend for Documentation and Deliverables Punch List
#BP | Number # of weeks Before Procurement
Proc. | Procurement
#AA | Number # of weeks After Award
#BF | Number # of weeks Before Fabrication or before construction when no fabrication is required
#DBF | Number # of working Days Before Fabrication, or before construction if no fabrication is required
Fab. | Fabrication
Con. | Construction
#AC | Number # of weeks After Construction
#BD | Number # of weeks Before Delivery
WD | With Delivery
#B | Number # of weeks prior to performing task
#H | Number # of working Hours after completion of task
#D | Number # of working Days after completion of task
#W | Number # of working Weeks after completion of task
SPEC | See referenced specification section for additional requirements
CTS | Contractor to Supply
PTFP | Prior to Final Payment

## Revision History
Rev No. | Rev Date | Rev Description
0 | 2013-03-05 | Ready for use
1 | 2013-04-04 | Added header information and new items to list
2 | 2014-04-03 | Removed Auxiliary from Single & Three Line (Rows 230 & 231). Added row 264, (Process Flow Diagrams.)
3 | 2014-07-02 | Added "Trench covers" & "Containments" to current line 192. Removed line 199 "Trench covers" and added current line 209, "Fabrication and erection drawings and supporting documentation".
4 | 2014-07-28 | Modified to contractual language
5 | 2014-09-09 | Modified Main Heading