## Sheet1
[11 empty] | Cost | Effectiveness | Inverse value | 5 | 4.5 | 4 | 3.5 | 3 | 2.5 | 2 | 1.5
[10 empty] | Maintain Resilient Electric Equipment |  |  |  | 4.5 | 4 | 3.5 | 3 | 2.5 | 2 | 1.5 | 1
Trans | Dist | Cap | Maint | [6 empty] | Base Case Risk/Resilience Programs |  |  |  | Quite Expensive | Very Expensive | Moderately Expensive | Pretty Expensive | Pretty Inexpensive | Moderately Inexpensive | Very Inexpensive | Quite Inexpensive
| x | x |  | 53 | Base Case Risk/Resilience Programs | Resilience Conductor & Splice Program | BC.RC.1 | Historic Program | BC.RC.1:Age-Based Underground Conductor Replacement | Age-Based Underground Conductor Replacement | 4.99 | 1.01 | 4.99 | 1.01
x | x |  | x | 52 | Base Case Risk/Resilience Programs | Resilience Conductor & Splice Program | BC.RC.2 | Historic Program | BC.RC.2:Infrared Poorly Performing Circuits | Infrared Poorly Performing Circuits | 3.1 | 4 | 2 |  |  |  | 4
x | x | x |  | 51 | Base Case Risk/Resilience Programs | Resilience Conductor & Splice Program | BC.RC.3 | Historic Program | BC.RC.3:Load Modeling/Circuit Protective Coordination to Avoid Heat Stress | Load Modeling/Circuit Protective Coordination to Avoid Heat Stress | 3.5 | 4.2 | 1.8 |  |  | 4.2
| x | x |  | 50 | Base Case Risk/Resilience Programs | Resilience Conductor & Splice Program | BC.RC.4 | Historic Program | BC.RC.4:Outage-Triggered Underground Failed Conductor Remediation | Outage-Triggered Underground Failed Conductor Remediation | 3.6 | 4.4 | 1.6 |  |  | 4.4
x | x |  | x | 49 | Base Case Risk/Resilience Programs | Resilience Conductor & Splice Program | BC.RC.5 | Historic Program | BC.RC.5:RF Inspection | RF Inspection | 4.2 | 1.3 | 4.7 |  | 1.3
x | x |  | x | 48 | Base Case Risk/Resilience Programs | Resilience Conductor & Splice Program | BC.RC.6 | Historic Program | BC.RC.6:Targeted Suspect Splice Assessment Program | Targeted Suspect Splice Assessment Program | 1.6 | 3.7 | 2.3 | [6 empty] | 3.7
x | x | x |  | 47 | Base Case Risk/Resilience Programs | Pole Loading Management Program | BC.PL.1 | Historic Program | BC.PL.1:Bad Order Pole Replacement Program | Bad Order Pole Replacement Program | 3.8 | 2.5 | 3.5 |  |  | 2.5
| x |  | x | 46 | Base Case Risk/Resilience Programs | Pole Loading Management Program | BC.PL.2 | Historic Program | BC.PL.2:Joint Use Permit Review for Distribution Poles | Joint Use Permit Review for Distribution Poles | 1.2 | 3.6 | 2.4 | [7 empty] | 3.6
x |  | x |  | 45 | Base Case Risk/Resilience Programs | Pole Loading Management Program | BC.PL.3 | Historic Program | BC.PL.3:Joint Use Transmission Pole Loading Modeling | Joint Use Transmission Pole Loading Modeling | 1.3 | 4.8 | 1.2 | [7 empty] | 4.8
x | x | x |  | 44 | Base Case Risk/Resilience Programs | Pole Loading Management Program | BC.PL.4 | Historic Program | BC.PL.4:Pole Loading Software Usage for Pole Replacements | Pole Loading Software Usage for Pole Replacements | 2.5 | 3.6 | 2.4 |  |  |  |  | 3.6
| x |  | x | 43 | Base Case Risk/Resilience Programs | Pole Loading Management Program | BC.PL.5 | Historic Program | BC.PL.5:Pole Strength Results Data Sharing | Pole Strength Results Data Sharing | 1.5 | 2.2 | 3.8 | [6 empty] | 2.2
| x |  | x | 42 | Base Case Risk/Resilience Programs | Damage Prevention Program | BC.DP.1 | Historic Program | BC.DP.1:Damage Prevention Program | Damage Prevention Program | 1.9 | 2.9 | 3.1 | [6 empty] | 2.9
x |  |  | x | 41 | Base Case Risk/Resilience Programs | Code Inspection Program | BC.CI.1 | Historic Program | BC.CI.1:Aerial Patrol for Inaccessible Facilities (transmission) | Aerial Patrol for Inaccessible Facilities (transmission) | 2.3 | 1.8 | 4.2 | [5 empty] | 1.8
x | x |  | x | 40 | Base Case Risk/Resilience Programs | Code Inspection Program | BC.CI.2 | Historic Program | BC.CI.2:Detail Inspections | Detail Inspections | 4.8 | 2.1 | 3.9 | 2.1
x | x |  | x | 39 | Base Case Risk/Resilience Programs | Code Inspection Program | BC.CI.3 | Historic Program | BC.CI.3:Intrusive Pole Testing Program | Intrusive Pole Testing Program | 4.6 | 2.4 | 3.6 | 2.4
x |  |  | x | 38 | Base Case Risk/Resilience Programs | Code Inspection Program | BC.CI.4 | Historic Program | BC.CI.4:LiDAR for NERC Facility Ratings & Clearance Reliability Standards | LiDAR for NERC Facility Ratings & Clearance Reliability Standards | 4.9 | 4.4 | 1.6 | 4.4
x | x |  | x | 37 | Base Case Risk/Resilience Programs | Code Inspection Program | BC.CI.5 | Historic Program | BC.CI.5:Patrol Inspections | Patrol Inspections | 3.2 | 3.3 | 2.7 |  |  |  | 3.3
x | x |  | x | 36 | Base Case Risk/Resilience Programs | Code Inspection Program | BC.CI.6 | Historic Program | BC.CI.6:Substation Inspections | Substation Inspections | 2.1 | 4.3 | 1.7 | [5 empty] | 4.3
|  |  |  | 35 | Base Case Risk/Resilience Programs | Code Inspection Program | BC.CI.7 | Historic Program | BC.CI.7:Transmission Line Patrol | Transmission Line Patrol | 3.4 | 3.8 | 2.2 |  |  |  | 3.8
x | x |  | x | 34 | Base Case Risk/Resilience Programs | Vegetation Management | BC.VM.1 | Historic Program | BC.VM.1:Radial Clearing of Subject Poles (PRC 4293) | Radial Clearing of Subject Poles (PRC 4293) | 3.1 | 4.5 | 1.5 |  |  |  | 4.5
x | x |  | x | 33 | Base Case Risk/Resilience Programs | Vegetation Management | BC.VM.2 | Historic Program | BC.VM.2:Vegetation Clearance in SRA (PRC 4292) | Vegetation Clearance in SRA (PRC 4292) | 4.6 | 4.4 | 1.6 | 4.4
x | x |  | x | 32 | Base Case Risk/Resilience Programs | Vegetation Management | BC.VM.3 | Historic Program | BC.VM.3:Vegetation Clearance Program (GO 95 Rule 35) | Vegetation Clearance Program (GO 95 Rule 35) | 4.1 | 4.6 | 1.4 |  | 4.6
x | x | x | x | 31 | Base Case Risk/Resilience Programs | Substation Maintenance Program | BC.SM.1 | Historic Program | BC.SM.1:Spill Containment Protection Program | Spill Containment Protection Program | 2.8 | 4.1 | 1.9 |  |  |  |  | 4.1
x | x | x |  | 30 | Base Case Risk/Resilience Programs | Substation Maintenance Program | BC.SM.2 | Historic Program | BC.SM.2:Substation Equipment & Material Replacement Program | Substation Equipment & Material Replacement Program | 4.4 | 4.99 | 1.01 |  | 4.99
x | x |  | x | 29 | Base Case Risk/Resilience Programs | Substation Maintenance Program | BC.SM.3 | Historic Program | BC.SM.3:Substation Testing & Functional Operation Program | Substation Testing & Functional Operation Program | 2.6 | 4.3 | 1.7 |  |  |  |  | 4.3
x | x |  | x | 28 | Operational Risk Reduction Programs |  | ORR.1 | Historic Program | ORR.1:Fire Response Coordination | Fire Response Coordination | 1.4 | 4.9 | 1.1 | [7 empty] | 4.9
x | x |  | x | 27 | Operational Risk Reduction Programs |  | ORR.2 | Historic Program | ORR.2:Fire Suppression Equipment on Line Trucks | Fire Suppression Equipment on Line Trucks | 2.1 | 4.8 | 1.2 | [5 empty] | 4.8
x | x |  | x | 26 | Operational Risk Reduction Programs |  | ORR.3 | Historic Program | ORR.3:Hazard Tree Training Program (for non-Veg employees) | Hazard Tree Training Program (for non-Veg employees) | 1.2 | 3.2 | 2.8 | [7 empty] | 3.2
x | x |  | x | 25 | Operational Risk Reduction Programs |  | ORR.4 | Historic Program | ORR.4:No-Test Re-energization Procedure | No-Test Re-energization Procedure | 1.3 | 4.95 | 1.05 | [7 empty] | 4.95
x | x |  | x | 24 | Operational Risk Reduction Programs |  | ORR.5 | Historic Program | ORR.5:On-Demand Pole Cladding | On-Demand Pole Cladding | 2.4 | 3.2 | 2.8 | [5 empty] | 3.2
x | x |  | x | 23 | Drought-Triggered Risk/Resilience Programs |  | DP.8 | Drought Triggered Program | DP.8:Tree Mortality Zones near Electric Equipment (2014-2017 observations) | Tree Mortality Zones near Electric Equipment (2014-2017 observations) | 3.2 | 4.7 | 1.3 |  |  |  | 4.7
x | x |  | x | 22 | Drought-Triggered Risk/Resilience Programs |  | DP.7 | Drought Triggered Program | DP.7:Reclosing Device Interrogation Program (download operational events during stress periods) | Reclosing Device Interrogation Program (download operational events during stress periods) | 1.2 | 3 | 3 | [7 empty] | 3
x | x |  | x | 21 | Drought-Triggered Risk/Resilience Programs |  | DP.6 | Drought Triggered Program | DP.6:Mid-Growing Season Vegetation Patrol During Fire Season | Mid-Growing Season Vegetation Patrol During Fire Season | 3.1 | 4.5 | 1.5 |  |  |  | 4.5
x |  | x |  | 20 | Drought-Triggered Risk/Resilience Programs |  | DP.5 | Drought Triggered Program | DP.5:Install Fault Detection Equipment: Highest Priority Transmission Lines | Install Fault Detection Equipment: Highest Priority Transmission Lines | 2.7 | 4.9 | 1.1 |  |  |  |  | 4.9
x | x |  | x | 19 | Drought-Triggered Risk/Resilience Programs |  | DP.4 | Drought Triggered Program | DP.4:Enhanced Vegetation Patrols in Advance of Fire Season | Enhanced Vegetation Patrols in Advance of Fire Season | 3.2 | 4.6 | 1.4 |  |  |  | 4.6
x | x |  | x | 18 | Drought-Triggered Risk/Resilience Programs |  | DP.3 | Drought Triggered Program | DP.3:Enhanced Line Patrols in Advance of Fire Season | Enhanced Line Patrols in Advance of Fire Season | 3.3 | 4.3 | 1.7 |  |  |  | 4.3
x | x |  | x | 17 | Drought-Triggered Risk/Resilience Programs |  | DP.2 | Drought Triggered Program | DP.2:Drought-Prone Additional Vegetation Clearance | Drought-Prone Additional Vegetation Clearance | 4.1 | 4.8 | 1.2 |  | 4.8
x | x | x | x | 16 | Drought-Triggered Risk/Resilience Programs |  | DP.1 | Drought Triggered Program | DP.1:Accelerate Particular Condition Codes in Advance of Fire Season | Accelerate Particular Condition Codes in Advance of Fire Season | 2.3 | 4.7 | 1.3 | [5 empty] | 4.7
x | x |  | x | 15 | Enhanced Fire Mitigation Programs |  | EFM.10 | New Fire Regulation Program | EFM.10:Tree Mortality Zones near Electric Equipment (annual observations) | Tree Mortality Zones near Electric Equipment (annual observations) | 3.3 | 4.7 | 1.3 |  |  |  | 4.7
x | x | x |  | 14 | Enhanced Fire Mitigation Programs |  | EFM.9 | New Fire Regulation Program | EFM.9:Replace Legacy Devices to Capture Additional Operational Events | Replace Legacy Devices to Capture Additional Operational Events | 4.1 | 3.4 | 2.6 |  | 3.4
x | x | x |  | 13 | Enhanced Fire Mitigation Programs |  | EFM.8 | New Fire Regulation Program | EFM.8:Pilot Remote Protective System Reconfiguration in Tier 3 | Pilot Remote Protective System Reconfiguration in Tier 3 | 4.8 | 4.7 | 1.3 | 4.7
x |  | x |  | 12 | Enhanced Fire Mitigation Programs |  | EFM.7 | New Fire Regulation Program | EFM.7:Install Fault Detection Equipment: High Priority Transmission Lines | Install Fault Detection Equipment: High Priority Transmission Lines | 3.4 | 4.75 | 1.25 |  |  |  | 4.75
| x | x |  | 11 | Enhanced Fire Mitigation Programs |  | EFM.6 | New Fire Regulation Program | EFM.6:Install Fault Detection Equipment: High Priority Distribution Lines | Install Fault Detection Equipment: High Priority Distribution Lines | 3.8 | 4.7 | 1.3 |  |  | 4.7
| x |  | x | 10 | Enhanced Fire Mitigation Programs |  | EFM.5 | New Fire Regulation Program | EFM.5:Increase Vegetation Clearances at End of Cycle in Tiers 2 & 3 | Increase Vegetation Clearances at End of Cycle in Tiers 2 & 3 | 4.2 | 4.5 | 1.5 |  | 4.5
| x |  | x | 9 | Enhanced Fire Mitigation Programs |  | EFM.4 | New Fire Regulation Program | EFM.4:Increase Frequency of GO 165 Patrols in Rural Areas (Annual) (Fire Threat Patrol) | Increase Frequency of GO 165 Patrols in Rural Areas (Annual) (Fire Threat Patrol) | 4.6 | 4.4 | 1.6 | 4.4
x | x |  | x | 8 | Enhanced Fire Mitigation Programs |  | EFM.3 | New Fire Regulation Program | EFM.3:Develop Fire Prevention Plan | Develop Fire Prevention Plan | 1.8 | 4.8 | 1.2 | [6 empty] | 4.8
x | x | x | x | 7 | Enhanced Fire Mitigation Programs |  | EFM.2 | New Fire Regulation Program | EFM.2:Accelerate Fire Threat Condition Correction in Tier 3 (within six months) | Accelerate Fire Threat Condition Correction in Tier 3 (within six months) | 2.3 | 4.4 | 1.6 | [5 empty] | 4.4
x | x | x | x | 6 | Enhanced Fire Mitigation Programs |  | EFM.1 | New Fire Regulation Program | EFM.1:Accelerate Fire Threat Condition Correction in Tier 2 (within 12 months) | Accelerate Fire Threat Condition Correction in Tier 2 (within 12 months) | 2.1 | 4.5 | 1.5 | [5 empty] | 4.5
| x | x |  | 5 | Enhance Risk Assessment Program |  | ERAP.5 | New Risk Reduction Program | ERAP.5:Pilot Legacy Recloser Replacement with Pulse-Sensing Fault Detection Equipment | Pilot Legacy Recloser Replacement with Pulse-Sensing Fault Detection Equipment | 1.2 | 4.5 | 1.5 | [7 empty] | 4.5
x | x |  | x | 4 | Enhance Risk Assessment Program |  | ERAP.4 | New Risk Reduction Program | ERAP.4:LiDAR Inspection to Attain Vegetation/Conductor Clearance | LiDAR Inspection to Attain Vegetation/Conductor Clearance | 3.2 | 3.5 | 2.5 |  |  |  | 3.5
x | x | x |  | 3 | Enhance Risk Assessment Program |  | ERAP.3 | New Risk Reduction Program | ERAP.3:Integrating Cause/Condition/Impacts into Advance Asset Health Index | Integrating Cause/Condition/Impacts into Advance Asset Health Index | 2.8 | 4.99 | 1.01 |  |  |  |  | 4.99
x | x |  | x | 2 | Enhance Risk Assessment Program |  | ERAP.2 | New Risk Reduction Program | ERAP.2:Drone Inspection to Assess Facility Details | Drone Inspection to Assess Facility Details | 4.1 | 4.2 | 1.8 |  | 4.2
| x | x |  | 1 | Enhance Risk Assessment Program |  | ERAP.1 | New Risk Reduction Program | ERAP.1:Downed Wire Fault Detection | Downed Wire Fault Detection | 2.8 | 4.7 | 1.3 |  |  |  |  | 4.7